## Slide 1
3-Week Lookahead Schedule
Free Gantt chart template · gantts.app

## Slide 2
3-Week Lookahead Schedule
Aug 3
Aug 17
Week 1 — committed work
Slab formwork grid A–D
Underslab MEP rough-in
◆ Underground inspection
Rebar install grid A–D
Backfill & compaction
◆ Pre-pour rebar inspection
Week 2 — ready work
Slab pour grid A–D
Slab cure & strip
Formwork grid E–H
Rebar install grid E–H
Site electrical trenching
◆ Pre-pour inspection E–H
Week 3 — planned work
Slab pour grid E–H
Crane mobilization
Steel erection — bay 1
Column baseplate survey
◆ Structural steel inspection
Constraints & lead times
Steel shop drawings approved
Structural steel delivery
Elevator submittal review
Switchgear order confirmation
Crane permit — street closure
◆ Crane permit issued
Weekly refresh
Monday coordination meeting
Constraint log review
Roll window forward one week
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Week 1 — committed work |  | 2026-08-02 | 2026-08-06 | 5 | 60%
1.1 | Slab formwork grid A–D | Concrete | 2026-08-02 | 2026-08-04 | 3 | 100%
1.2 | Underslab MEP rough-in | Mechanical | 2026-08-02 | 2026-08-03 | 2 | 100%
2 | Underground inspection |  | 2026-08-04 | 2026-08-04 | — | —
2.1 | Rebar install grid A–D | Concrete | 2026-08-04 | 2026-08-05 | 2 | 70%
2.2 | Backfill & compaction | Earthworks | 2026-08-05 | 2026-08-06 | 2 | 40%
3 | Pre-pour rebar inspection |  | 2026-08-06 | 2026-08-06 | — | —
4 | Week 2 — ready work |  | 2026-08-09 | 2026-08-13 | 5 | 0%
4.1 | Slab pour grid A–D | Concrete | 2026-08-09 | 2026-08-09 | 1 | 0%
4.2 | Slab cure & strip | Concrete | 2026-08-10 | 2026-08-12 | 3 | 0%
4.3 | Formwork grid E–H | Concrete | 2026-08-09 | 2026-08-11 | 3 | 0%
4.4 | Rebar install grid E–H | Concrete | 2026-08-11 | 2026-08-12 | 2 | 0%
4.5 | Site electrical trenching | Electrical | 2026-08-10 | 2026-08-13 | 4 | 0%
5 | Pre-pour inspection E–H |  | 2026-08-13 | 2026-08-13 | — | —
6 | Week 3 — planned work |  | 2026-08-16 | 2026-08-20 | 5 | 0%
6.1 | Slab pour grid E–H | Concrete | 2026-08-16 | 2026-08-16 | 1 | 0%
6.2 | Crane mobilization | Steel sub | 2026-08-16 | 2026-08-16 | 1 | 0%
6.3 | Steel erection — bay 1 | Steel sub | 2026-08-17 | 2026-08-20 | 4 | 0%
6.4 | Column baseplate survey | Surveyor | 2026-08-16 | 2026-08-17 | 2 | 0%
7 | Structural steel inspection |  | 2026-08-21 | 2026-08-21 | — | —
8 | Constraints & lead times |  | 2026-08-02 | 2026-08-17 | 16 | 45%

## Slide 4
8.1 | Steel shop drawings approved | Engineer | 2026-08-02 | 2026-08-05 | 4 | 100%
8.2 | Structural steel delivery | Fabricator | 2026-08-11 | 2026-08-11 | 1 | 0%
8.3 | Elevator submittal review | Architect | 2026-08-05 | 2026-08-12 | 8 | 40%
8.4 | Switchgear order confirmation | Procurement | 2026-08-07 | 2026-08-09 | 3 | 60%
8.5 | Crane permit — street closure | Site manager | 2026-08-09 | 2026-08-14 | 6 | 20%
9 | Crane permit issued |  | 2026-08-15 | 2026-08-15 | — | —
10 | Weekly refresh |  | 2026-08-02 | 2026-08-22 | 21 | 30%
10.1 | Monday coordination meeting | Superintendent | 2026-08-02 | 2026-08-02 | 1 | 100%
10.2 | Constraint log review | Superintendent | 2026-08-09 | 2026-08-09 | 1 | 0%
10.3 | Roll window forward one week | Planner | 2026-08-16 | 2026-08-16 | 1 | 0%