## Gantt
3-Week Lookahead Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24
1 | Week 1 — committed work |  | 2026-08-02 | 2026-08-06 | 5
1.1 | Slab formwork grid A–D | Concrete | 2026-08-02 | 2026-08-04 | 3
1.2 | Underslab MEP rough-in | Mechanical | 2026-08-02 | 2026-08-03 | 2
2 | ◆ Underground inspection |  | 2026-08-04 | 2026-08-04 |  | ◆
2.1 | Rebar install grid A–D | Concrete | 2026-08-04 | 2026-08-05 | 2
2.2 | Backfill & compaction | Earthworks | 2026-08-05 | 2026-08-06 | 2
3 | ◆ Pre-pour rebar inspection |  | 2026-08-06 | 2026-08-06 |  | ◆
4 | Week 2 — ready work |  | 2026-08-09 | 2026-08-13 | 5
4.1 | Slab pour grid A–D | Concrete | 2026-08-09 | 2026-08-09 | 1
4.2 | Slab cure & strip | Concrete | 2026-08-10 | 2026-08-12 | 3
4.3 | Formwork grid E–H | Concrete | 2026-08-09 | 2026-08-11 | 3
4.4 | Rebar install grid E–H | Concrete | 2026-08-11 | 2026-08-12 | 2
4.5 | Site electrical trenching | Electrical | 2026-08-10 | 2026-08-13 | 4
5 | ◆ Pre-pour inspection E–H |  | 2026-08-13 | 2026-08-13 |  |  | ◆
6 | Week 3 — planned work |  | 2026-08-16 | 2026-08-20 | 5
6.1 | Slab pour grid E–H | Concrete | 2026-08-16 | 2026-08-16 | 1
6.2 | Crane mobilization | Steel sub | 2026-08-16 | 2026-08-16 | 1
6.3 | Steel erection — bay 1 | Steel sub | 2026-08-17 | 2026-08-20 | 4
6.4 | Column baseplate survey | Surveyor | 2026-08-16 | 2026-08-17 | 2
7 | ◆ Structural steel inspection |  | 2026-08-21 | 2026-08-21 |  |  |  | ◆
8 | Constraints & lead times |  | 2026-08-02 | 2026-08-17 | 16
8.1 | Steel shop drawings approved | Engineer | 2026-08-02 | 2026-08-05 | 4
8.2 | Structural steel delivery | Fabricator | 2026-08-11 | 2026-08-11 | 1
8.3 | Elevator submittal review | Architect | 2026-08-05 | 2026-08-12 | 8
8.4 | Switchgear order confirmation | Procurement | 2026-08-07 | 2026-08-09 | 3
8.5 | Crane permit — street closure | Site manager | 2026-08-09 | 2026-08-14 | 6
9 | ◆ Crane permit issued |  | 2026-08-15 | 2026-08-15 |  |  | ◆
10 | Weekly refresh |  | 2026-08-02 | 2026-08-22 | 21
10.1 | Monday coordination meeting | Superintendent | 2026-08-02 | 2026-08-02 | 1
10.2 | Constraint log review | Superintendent | 2026-08-09 | 2026-08-09 | 1
10.3 | Roll window forward one week | Planner | 2026-08-16 | 2026-08-16 | 1