## Slide 1
Apparel Production Calendar
Free Gantt chart template · gantts.app

## Slide 2
Apparel Production Calendar
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Concept & design
Range plan & design freeze
◆ Tech pack issued
Sampling
Proto sample
Fit sample & comments
PP sample
◆ PP sample approved
Materials
Fabric booking & lab dips
Bulk fabric production & transit
◆ Fabric in-house
Pre-production
Marker, grading & size set
PP meeting & line release
Bulk production
Cutting
Sewing & in-line QC
Finishing & pressing
Finishing & shipment
Final inspection & packing
◆ Ex-factory
Transit to delivery window
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Concept & design |  | 2026-08-02 | 2026-08-31 | 30 | 100%
1.1 | Range plan & design freeze | Design | 2026-08-02 | 2026-08-19 | 18 | 100%
2 | Tech pack issued |  | 2026-09-01 | 2026-09-01 | — | —
3 | Sampling |  | 2026-09-01 | 2026-11-14 | 75 | 60%
3.1 | Proto sample | Sampling | 2026-09-01 | 2026-09-22 | 22 | 100%
3.2 | Fit sample & comments | Sampling | 2026-09-23 | 2026-10-17 | 25 | 60%
3.3 | PP sample | Sampling | 2026-10-18 | 2026-11-14 | 28 | 20%
4 | PP sample approved |  | 2026-11-15 | 2026-11-15 | — | —
5 | Materials |  | 2026-09-06 | 2026-11-24 | 80 | 50%
5.1 | Fabric booking & lab dips | Sourcing | 2026-09-06 | 2026-10-10 | 35 | 90%
5.2 | Bulk fabric production & transit | Mill | 2026-10-11 | 2026-11-24 | 45 | 30%
6 | Fabric in-house |  | 2026-11-25 | 2026-11-25 | — | —
7 | Pre-production |  | 2026-11-15 | 2026-12-06 | 22 | 0%
7.1 | Marker, grading & size set | Production | 2026-11-15 | 2026-11-29 | 15 | 0%
7.2 | PP meeting & line release | Production | 2026-11-30 | 2026-12-06 | 7 | 0%
8 | Bulk production |  | 2026-12-07 | 2027-01-20 | 45 | 0%
8.1 | Cutting | Factory | 2026-12-07 | 2026-12-16 | 10 | 0%
8.2 | Sewing & in-line QC | Factory | 2026-12-17 | 2027-01-13 | 28 | 0%
8.3 | Finishing & pressing | Factory | 2027-01-09 | 2027-01-20 | 12 | 0%
9 | Finishing & shipment |  | 2027-01-21 | 2027-02-14 | 25 | 0%
9.1 | Final inspection & packing | QA | 2027-01-21 | 2027-01-30 | 10 | 0%

## Slide 4
10 | Ex-factory |  | 2027-02-03 | 2027-02-03 | — | —
10.1 | Transit to delivery window | Logistics | 2027-02-03 | 2027-02-14 | 12 | 0%