## Slide 1
Battery Gigafactory Construction
Free Gantt chart template · gantts.app

## Slide 2
Battery Gigafactory Construction
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Aug 28
Sep 11
Sep 25
Oct 9
Oct 23
Nov 6
Nov 20
Dec 4
Dec 18
Jan 1
Jan 15
Jan 29
Feb 12
Feb 26
Mar 12
Mar 26
Apr 9
Apr 23
Site, permits & cell process design
Site selection & grid connection agreement
Cell format & chemistry freeze
Environmental permit & hazardous materials licence
Process flow & line capacity basis of design
Long-lead equipment purchase orders placed
◆ Cell format frozen
◆ Permits granted
Building shell & dry room construction
Piling, slab & structural steel
Envelope, roof & building dry-in
Vapour barrier & dry room envelope sealing
Dry room airlocks, gowning & material entry
Electrode & assembly hall floor flatness survey
◆ Building dry-in complete
Utilities, dehumidification & dry room qualification
Substation energisation & power distribution
Desiccant dehumidification plant installation
Compressed dry air, nitrogen & process cooling
Solvent recovery & NMP abatement system
Dry room pull-down to target dew point
Dew point hold test & envelope leak survey
◆ Dry room qualified at dew point
Equipment move-in, install & qualification
Electrode coater & calender move-in
Slitting, vacuum drying & winding line install
Stacking, tab welding & can sealing line install
Electrolyte filling & degassing equipment install
Formation & aging rack installation
Station-by-station site acceptance testing
◆ Equipment qualification complete
Line commissioning, first cell & formation
MES, traceability & line control integration
Dry room operating discipline & training
Electrode coating trials & web quality tuning
◆ First assembled cell off the line
Formation cycling of first cell batches
Aging & self-discharge screening window
Teardown, metrology & failure analysis loop
Yield ramp & customer qualification
Process capability & SPC baseline per station
Scrap rate reduction — electrode to assembly
A-sample cells shipped to customer
Abuse, safety & transport certification testing
Customer B-sample qualification & PPAP
◆ Yield target reached for saleable output
Ramp to nameplate capacity
◆ Start of production declared
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Site, permits & cell process design |  | 2026-08-02 | 2027-02-17 | 200 | 100%
1.1 | Site selection & grid connection agreement | Client | 2026-08-02 | 2026-09-30 | 60 | 100%
1.2 | Cell format & chemistry freeze | Process | 2026-08-22 | 2026-10-15 | 55 | 100%
1.3 | Environmental permit & hazardous materials licence | Regulatory | 2026-09-16 | 2027-01-13 | 120 | 100%
1.4 | Process flow & line capacity basis of design | Process | 2026-10-16 | 2026-12-14 | 60 | 100%
1.5 | Long-lead equipment purchase orders placed | Procurement | 2026-11-30 | 2027-02-17 | 80 | 90%
2 | Cell format frozen |  | 2026-10-16 | 2026-10-16 | — | —
3 | Permits granted |  | 2027-01-14 | 2027-01-14 | — | —
4 | Building shell & dry room construction |  | 2027-01-14 | 2027-09-30 | 260 | 45%
4.1 | Piling, slab & structural steel | Civils | 2027-01-14 | 2027-04-13 | 90 | 100%
4.2 | Envelope, roof & building dry-in | Structural | 2027-04-04 | 2027-06-12 | 70 | 70%
4.3 | Vapour barrier & dry room envelope sealing | Dry room | 2027-05-29 | 2027-08-01 | 65 | 30%
4.4 | Dry room airlocks, gowning & material entry | Dry room | 2027-07-18 | 2027-08-31 | 45 | 10%
4.5 | Electrode & assembly hall floor flatness survey | Civils | 2027-07-08 | 2027-08-06 | 30 | 0%
5 | Building dry-in complete |  | 2027-06-13 | 2027-06-13 | — | —
6 | Utilities, dehumidification & dry room qualification |  | 2027-05-29 | 2027-12-14 | 200 | 10%
6.1 | Substation energisation & power distribution | Electrical | 2027-05-29 | 2027-08-16 | 80 | 20%
6.2 | Desiccant dehumidification plant installation | Facilities | 2027-06-28 | 2027-09-20 | 85 | 0%
6.3 | Compressed dry air, | Facilities | 2027-07-18 | 2027-09-25 | 70 | 0%

## Slide 4
 | nitrogen & process cooling |  |  |  |  | 
6.4 | Solvent recovery & NMP abatement system | Facilities | 2027-07-23 | 2027-10-10 | 80 | 0%
6.5 | Dry room pull-down to target dew point | Dry room | 2027-09-21 | 2027-10-25 | 35 | 0%
6.6 | Dew point hold test & envelope leak survey | Commissioning | 2027-10-26 | 2027-11-24 | 30 | 0%
7 | Dry room qualified at dew point |  | 2027-11-25 | 2027-11-25 | — | —
8 | Equipment move-in, install & qualification |  | 2027-09-26 | 2028-04-22 | 210 | 0%
8.1 | Electrode coater & calender move-in | Tool install | 2027-09-26 | 2027-11-19 | 55 | 0%
8.2 | Slitting, vacuum drying & winding line install | Tool install | 2027-11-05 | 2028-01-03 | 60 | 0%
8.3 | Stacking, tab welding & can sealing line install | Tool install | 2027-12-05 | 2028-02-02 | 60 | 0%
8.4 | Electrolyte filling & degassing equipment install | Tool install | 2028-01-04 | 2028-02-17 | 45 | 0%
8.5 | Formation & aging rack installation | Tool install | 2027-12-20 | 2028-02-27 | 70 | 0%
8.6 | Station-by-station site acceptance testing | Vendor | 2028-02-18 | 2028-04-12 | 55 | 0%
9 | Equipment qualification complete |  | 2028-04-23 | 2028-04-23 | — | —
10 | Line commissioning, first cell & formation |  | 2028-03-24 | 2028-09-29 | 190 | 0%
10.1 | MES, traceability & line control integration | IT | 2028-03-24 | 2028-05-22 | 60 | 0%
10.2 | Dry room operating discipline & training | Operations | 2028-04-13 | 2028-05-17 | 35 | 0%
10.3 | Electrode coating trials & web quality tuning | Process | 2028-04-23 | 2028-06-06 | 45 | 0%
11 | First assembled cell off the line |  | 2028-06-22 | 2028-06-22 | — | —
11.1 | Formation cycling of first cell batches | Process | 2028-06-22 | 2028-07-31 | 40 | 0%
11.2 | Aging & self-discharge screening window | Quality | 2028-07-22 | 2028-09-04 | 45 | 0%
11.3 | Teardown, metrology & failure analysis loop | Quality | 2028-08-11 | 2028-09-29 | 50 | 0%
12 | Yield ramp & customer qualification |  | 2028-09-05 | 2029-04-27 | 235 | 0%
12.1 | Process capability & | Process | 2028-09-05 | 2028-11-03 | 60 | 0%

## Slide 5
 | SPC baseline per station |  |  |  |  | 
12.2 | Scrap rate reduction — electrode to assembly | Process | 2028-10-10 | 2029-01-27 | 110 | 0%
12.3 | A-sample cells shipped to customer | Quality | 2028-11-09 | 2028-12-08 | 30 | 0%
12.4 | Abuse, safety & transport certification testing | Quality | 2028-11-29 | 2029-01-22 | 55 | 0%
12.5 | Customer B-sample qualification & PPAP | Quality | 2029-01-23 | 2029-03-28 | 65 | 0%
13 | Yield target reached for saleable output |  | 2029-03-29 | 2029-03-29 | — | —
13.1 | Ramp to nameplate capacity | Operations | 2029-03-29 | 2029-04-27 | 30 | 0%
14 | Start of production declared |  | 2029-04-28 | 2029-04-28 | — | —