## Slide 1
Book Launch Plan
Free Gantt chart template · gantts.app

## Slide 2
Book Launch Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Manuscript
Finalize first draft
Self-edit pass
◆ Manuscript complete
Editing
Developmental edit
Copyedit
Proofread
◆ Manuscript final
Production
Cover design
Interior formatting & typesetting
ISBN & metadata
◆ Files print-ready
Pre-launch
Recruit ARC & beta readers
Send ARCs & gather blurbs
Set up pre-order
◆ Pre-order live
Marketing
Build author platform & email list
Assemble launch team
Book promos & ads
Launch week & follow-up
◆ Book released
Launch-week promotions
Chase reviews & ratings
Post-launch review
◆ Launch complete
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Manuscript |  | 2026-08-02 | 2026-09-10 | 40 | 100%
1.1 | Finalize first draft | Author | 2026-08-02 | 2026-08-31 | 30 | 100%
1.2 | Self-edit pass | Author | 2026-09-01 | 2026-09-10 | 10 | 100%
2 | Manuscript complete |  | 2026-09-11 | 2026-09-11 | , | ,
3 | Editing |  | 2026-09-11 | 2026-10-25 | 45 | 45%
3.1 | Developmental edit | Editor | 2026-09-11 | 2026-09-30 | 20 | 100%
3.2 | Copyedit | Copyeditor | 2026-10-01 | 2026-10-15 | 15 | 40%
3.3 | Proofread | Proofreader | 2026-10-16 | 2026-10-25 | 10 | 0%
4 | Manuscript final |  | 2026-10-26 | 2026-10-26 | , | ,
5 | Production |  | 2026-10-11 | 2026-11-19 | 40 | 15%
5.1 | Cover design | Designer | 2026-10-11 | 2026-10-31 | 21 | 30%
5.2 | Interior formatting & typesetting | Formatter | 2026-10-26 | 2026-11-08 | 14 | 0%
5.3 | ISBN & metadata | Author | 2026-10-26 | 2026-10-30 | 5 | 0%
6 | Files print-ready |  | 2026-11-20 | 2026-11-20 | , | ,
7 | Pre-launch |  | 2026-10-31 | 2026-12-14 | 45 | 0%
7.1 | Recruit ARC & beta readers | Author | 2026-10-31 | 2026-11-13 | 14 | 0%
7.2 | Send ARCs & gather blurbs | Author | 2026-11-14 | 2026-12-04 | 21 | 0%
7.3 | Set up pre-order | Author | 2026-11-20 | 2026-11-26 | 7 | 0%
8 | Pre-order live |  | 2026-11-27 | 2026-11-27 | , | ,
9 | Marketing |  | 2026-11-10 | 2027-01-03 | 55 | 0%
9.1 | Build author platform & email list | Author | 2026-11-10 | 2026-12-14 | 35 | 0%

## Slide 4
9.2 | Assemble launch team | Author | 2026-11-30 | 2026-12-13 | 14 | 0%
9.3 | Book promos & ads | Marketing | 2026-12-15 | 2027-01-03 | 20 | 0%
10 | Launch week & follow-up |  | 2027-01-04 | 2027-01-24 | 21 | 0%
11 | Book released |  | 2027-01-04 | 2027-01-04 | , | ,
11.1 | Launch-week promotions | Marketing | 2027-01-04 | 2027-01-10 | 7 | 0%
11.2 | Chase reviews & ratings | Author | 2027-01-11 | 2027-01-22 | 12 | 0%
11.3 | Post-launch review | Author | 2027-01-23 | 2027-01-29 | 7 | 0%
12 | Launch complete |  | 2027-01-30 | 2027-01-30 | , | ,