## Gantt
Book Launch Plan
Made free at gantts.app, edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1
1 | Manuscript |  | 2026-08-02 | 2026-09-10 | 40
1.1 | Finalize first draft | Author | 2026-08-02 | 2026-08-31 | 30
1.2 | Self-edit pass | Author | 2026-09-01 | 2026-09-10 | 10
2 | ◆ Manuscript complete |  | 2026-09-11 | 2026-09-11 | [6 empty] | ◆
3 | Editing |  | 2026-09-11 | 2026-10-25 | 45
3.1 | Developmental edit | Editor | 2026-09-11 | 2026-09-30 | 20
3.2 | Copyedit | Copyeditor | 2026-10-01 | 2026-10-15 | 15
3.3 | Proofread | Proofreader | 2026-10-16 | 2026-10-25 | 10
4 | ◆ Manuscript final |  | 2026-10-26 | 2026-10-26 | [13 empty] | ◆
5 | Production |  | 2026-10-11 | 2026-11-19 | 40
5.1 | Cover design | Designer | 2026-10-11 | 2026-10-31 | 21
5.2 | Interior formatting & typesetting | Formatter | 2026-10-26 | 2026-11-08 | 14
5.3 | ISBN & metadata | Author | 2026-10-26 | 2026-10-30 | 5
6 | ◆ Files print-ready |  | 2026-11-20 | 2026-11-20 | [16 empty] | ◆
7 | Pre-launch |  | 2026-10-31 | 2026-12-14 | 45
7.1 | Recruit ARC & beta readers | Author | 2026-10-31 | 2026-11-13 | 14
7.2 | Send ARCs & gather blurbs | Author | 2026-11-14 | 2026-12-04 | 21
7.3 | Set up pre-order | Author | 2026-11-20 | 2026-11-26 | 7
8 | ◆ Pre-order live |  | 2026-11-27 | 2026-11-27 | [17 empty] | ◆
9 | Marketing |  | 2026-11-10 | 2027-01-03 | 55
9.1 | Build author platform & email list | Author | 2026-11-10 | 2026-12-14 | 35
9.2 | Assemble launch team | Author | 2026-11-30 | 2026-12-13 | 14
9.3 | Book promos & ads | Marketing | 2026-12-15 | 2027-01-03 | 20
10 | Launch week & follow-up |  | 2027-01-04 | 2027-01-24 | 21
11 | ◆ Book released |  | 2027-01-04 | 2027-01-04 | [23 empty] | ◆
11.1 | Launch-week promotions | Marketing | 2027-01-04 | 2027-01-10 | 7
11.2 | Chase reviews & ratings | Author | 2027-01-11 | 2027-01-22 | 12
11.3 | Post-launch review | Author | 2027-01-23 | 2027-01-29 | 7
12 | ◆ Launch complete |  | 2027-01-30 | 2027-01-30 | [26 empty] | ◆