## Slide 1
Brand Relaunch Plan
Free Gantt chart template · gantts.app

## Slide 2
Brand Relaunch Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Strategy, positioning & naming
Brand audit & equity research
Positioning & narrative platform
Name generation & shortlist
Linguistic & cultural screening of shortlist
◆ Name shortlist agreed for clearance
Trademark clearance & registration
Knockout trademark searches on shortlist
Full clearance search in priority markets
Counsel risk opinion & name decision
Secure domains & social handles quietly
File trademark applications by class & market
Monitor examination & opposition periods
◆ Name cleared and applications filed
Identity design & approval
Design territories explored
Logo, wordmark & core identity refined
Colour, type & motion system defined
Accessibility & legibility checks
Executive and board approval of identity
◆ Identity approved and locked
Asset production & system build
Brand guidelines & asset library published
Website rebuild on the new identity
Product UI theming & component updates
Email templates & transactional messaging
Packaging artwork & print production
Signage, vehicle livery & uniform production
◆ Core assets production complete
Switchover readiness & rehearsal
Build the switchover checklist by surface
Legal entity, invoicing & contract naming review
Third-party listings & marketplace profiles prepared
Redirects, SEO mapping & analytics continuity
Switchover rehearsal in staging
◆ Switchover rehearsed and go decision made
Reveal day & the long tail
Reveal day — simultaneous switch of owned surfaces
Press, customer and partner announcement
Social handle migration & profile updates
Signage installation programme across sites
Packaging changeover as old stock depletes
Third-party and partner surface chase list
Old brand asset retirement & takedown audit
◆ Long tail closed and old brand retired
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Strategy, positioning & naming |  | 2026-08-02 | 2026-10-10 | 70 | 100%
1.1 | Brand audit & equity research | Insights | 2026-08-02 | 2026-08-26 | 25 | 100%
1.2 | Positioning & narrative platform | Brand lead | 2026-08-22 | 2026-09-15 | 25 | 100%
1.3 | Name generation & shortlist | Brand lead | 2026-09-06 | 2026-09-25 | 20 | 100%
1.4 | Linguistic & cultural screening of shortlist | Agency | 2026-09-19 | 2026-10-03 | 15 | 100%
2 | Name shortlist agreed for clearance |  | 2026-10-11 | 2026-10-11 | — | —
3 | Trademark clearance & registration |  | 2026-10-11 | 2027-04-28 | 200 | 40%
3.1 | Knockout trademark searches on shortlist | Trademark counsel | 2026-10-11 | 2026-10-30 | 20 | 100%
3.2 | Full clearance search in priority markets | Trademark counsel | 2026-10-26 | 2026-11-29 | 35 | 60%
3.3 | Counsel risk opinion & name decision | Trademark counsel | 2026-11-25 | 2026-12-09 | 15 | 20%
3.4 | Secure domains & social handles quietly | Digital | 2026-12-05 | 2026-12-24 | 20 | 0%
3.5 | File trademark applications by class & market | Trademark counsel | 2026-12-10 | 2027-01-03 | 25 | 0%
3.6 | Monitor examination & opposition periods | Trademark counsel | 2027-01-09 | 2027-04-28 | 110 | 0%
4 | Name cleared and applications filed |  | 2027-01-09 | 2027-01-09 | — | —
5 | Identity design & approval |  | 2026-12-10 | 2027-03-09 | 90 | 0%
5.1 | Design territories explored | Design | 2026-12-10 | 2027-01-03 | 25 | 0%
5.2 | Logo, wordmark & core identity refined | Design | 2027-01-04 | 2027-02-02 | 30 | 0%
5.3 | Colour, type & motion system defined | Design | 2027-01-24 | 2027-02-17 | 25 | 0%
5.4 | Accessibility & legibility checks | Design | 2027-02-08 | 2027-02-19 | 12 | 0%
5.5 | Executive and board approval of identity | Exec | 2027-02-23 | 2027-03-09 | 15 | 0%
6 | Identity approved and |  | 2027-03-10 | 2027-03-10 | — | —

## Slide 4
 | locked |  |  |  |  | 
7 | Asset production & system build |  | 2027-03-10 | 2027-07-07 | 120 | 0%
7.1 | Brand guidelines & asset library published | Brand lead | 2027-03-10 | 2027-04-13 | 35 | 0%
7.2 | Website rebuild on the new identity | Digital | 2027-03-15 | 2027-06-12 | 90 | 0%
7.3 | Product UI theming & component updates | Product | 2027-03-20 | 2027-06-12 | 85 | 0%
7.4 | Email templates & transactional messaging | Marketing ops | 2027-04-19 | 2027-05-28 | 40 | 0%
7.5 | Packaging artwork & print production | Packaging | 2027-04-04 | 2027-06-22 | 80 | 0%
7.6 | Signage, vehicle livery & uniform production | Facilities | 2027-04-09 | 2027-07-02 | 85 | 0%
8 | Core assets production complete |  | 2027-07-08 | 2027-07-08 | — | —
9 | Switchover readiness & rehearsal |  | 2027-05-29 | 2027-08-06 | 70 | 0%
9.1 | Build the switchover checklist by surface | Programme lead | 2027-05-29 | 2027-06-22 | 25 | 0%
9.2 | Legal entity, invoicing & contract naming review | Legal | 2027-05-29 | 2027-07-07 | 40 | 0%
9.3 | Third-party listings & marketplace profiles prepared | Digital | 2027-06-18 | 2027-07-22 | 35 | 0%
9.4 | Redirects, SEO mapping & analytics continuity | Digital | 2027-06-28 | 2027-07-27 | 30 | 0%
9.5 | Switchover rehearsal in staging | Programme lead | 2027-07-18 | 2027-07-29 | 12 | 0%
10 | Switchover rehearsed and go decision made |  | 2027-08-07 | 2027-08-07 | — | —
11 | Reveal day & the long tail |  | 2027-08-07 | 2027-12-04 | 120 | 0%
11.1 | Reveal day — simultaneous switch of owned surfaces | Programme lead | 2027-08-07 | 2027-08-08 | 2 | 0%
11.2 | Press, customer and partner announcement | Communications | 2027-08-07 | 2027-08-09 | 3 | 0%
11.3 | Social handle migration & profile updates | Social | 2027-08-07 | 2027-08-09 | 3 | 0%
11.4 | Signage installation programme across sites | Facilities | 2027-08-10 | 2027-10-08 | 60 | 0%
11.5 | Packaging changeover as old stock depletes | Supply chain | 2027-08-10 | 2027-11-07 | 90 | 0%
11.6 | Third-party and partner surface chase list | Marketing ops | 2027-08-12 | 2027-10-20 | 70 | 0%
11.7 | Old brand asset | Brand lead | 2027-09-26 | 2027-11-09 | 45 | 0%

## Slide 5
 | retirement & takedown audit |  |  |  |  | 
12 | Long tail closed and old brand retired |  | 2027-12-05 | 2027-12-05 | — | —