## Slide 1
Bridge Construction Schedule
Free Gantt chart template · gantts.app

## Slide 2
Bridge Construction Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Survey & ground investigation
Topographic & hydrographic survey
Utility searches & trial holes
Boreholes & geotechnical testing
Environmental baseline survey
◆ GI report issued
Design & approvals
Preliminary design
Detailed design
Temporary works design
Environmental consent & river licence
Technical approval submission
◆ Technical approval granted
Enabling works & possessions
◆ Possession application submitted
◆ Possession window confirmed
Site set-up & compound
Haul road & site access
Utility diversions
Cofferdam & river works
Piling & foundations
Abutment piling
Pier piling
Pile integrity & load testing
Pile caps & foundation concrete
Substructure
Abutments & wing walls
Piers & pier caps
Bearing plinths & bearings
◆ Substructure complete
Superstructure & deck
Beam fabrication
Beam delivery to site
Possession & beam erection
Deck formwork & reinforcement
Deck concrete pour
Deck cure & strike
Surfacing, testing & opening
Waterproofing
Surfacing
Parapets & safety barriers
Drainage & road markings
Load testing & certification
Snagging & handover
◆ Open to traffic
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Survey & ground investigation |  | 2026-08-02 | 2026-10-30 | 90 | 100%
1.1 | Topographic & hydrographic survey | Surveyor | 2026-08-02 | 2026-08-31 | 30 | 100%
1.2 | Utility searches & trial holes | Civil | 2026-08-22 | 2026-09-20 | 30 | 100%
1.3 | Boreholes & geotechnical testing | GI contractor | 2026-09-01 | 2026-10-10 | 40 | 100%
1.4 | Environmental baseline survey | Ecologist | 2026-09-06 | 2026-10-15 | 40 | 100%
2 | GI report issued |  | 2026-10-31 | 2026-10-31 | — | —
3 | Design & approvals |  | 2026-10-16 | 2027-03-29 | 165 | 80%
3.1 | Preliminary design | Design engineer | 2026-10-16 | 2026-11-29 | 45 | 100%
3.2 | Detailed design | Design engineer | 2026-11-25 | 2027-02-17 | 85 | 90%
3.3 | Temporary works design | TW engineer | 2026-12-30 | 2027-02-27 | 60 | 60%
3.4 | Environmental consent & river licence | Consents lead | 2026-11-20 | 2027-02-17 | 90 | 70%
3.5 | Technical approval submission | Design engineer | 2027-02-18 | 2027-03-29 | 40 | 40%
4 | Technical approval granted |  | 2027-03-30 | 2027-03-30 | — | —
5 | Enabling works & possessions |  | 2027-01-29 | 2027-06-07 | 130 | 30%
6 | Possession application submitted |  | 2027-01-29 | 2027-01-29 | — | —
7 | Possession window confirmed |  | 2027-04-19 | 2027-04-19 | — | —
7.1 | Site set-up & compound | Main contractor | 2027-03-30 | 2027-04-23 | 25 | 20%
7.2 | Haul road & site access | Civil | 2027-04-14 | 2027-05-13 | 30 | 0%
7.3 | Utility diversions | Utilities | 2027-03-30 | 2027-05-23 | 55 | 10%
7.4 | Cofferdam & river works | Marine | 2027-05-09 | 2027-06-07 | 30 | 0%
8 | Piling & foundations |  | 2027-05-29 | 2027-09-20 | 115 | 0%

## Slide 4
8.1 | Abutment piling | Piling contractor | 2027-05-29 | 2027-07-07 | 40 | 0%
8.2 | Pier piling | Piling contractor | 2027-06-18 | 2027-08-01 | 45 | 0%
8.3 | Pile integrity & load testing | Testing | 2027-07-28 | 2027-08-16 | 20 | 0%
8.4 | Pile caps & foundation concrete | Civil | 2027-08-12 | 2027-09-20 | 40 | 0%
9 | Substructure |  | 2027-09-21 | 2028-01-18 | 120 | 0%
9.1 | Abutments & wing walls | Civil | 2027-09-21 | 2027-11-19 | 60 | 0%
9.2 | Piers & pier caps | Civil | 2027-10-16 | 2027-12-19 | 65 | 0%
9.3 | Bearing plinths & bearings | Civil | 2027-12-20 | 2028-01-18 | 30 | 0%
10 | Substructure complete |  | 2028-01-19 | 2028-01-19 | — | —
11 | Superstructure & deck |  | 2027-09-26 | 2028-03-18 | 175 | 0%
11.1 | Beam fabrication | Fabricator | 2027-09-26 | 2028-01-03 | 100 | 0%
11.2 | Beam delivery to site | Logistics | 2028-01-09 | 2028-01-23 | 15 | 0%
11.3 | Possession & beam erection | Erection team | 2028-01-24 | 2028-01-28 | 5 | 0%
11.4 | Deck formwork & reinforcement | Civil | 2028-01-30 | 2028-02-28 | 30 | 0%
11.5 | Deck concrete pour | Civil | 2028-03-01 | 2028-03-08 | 8 | 0%
11.6 | Deck cure & strike | Civil | 2028-03-09 | 2028-03-18 | 10 | 0%
12 | Surfacing, testing & opening |  | 2028-03-19 | 2028-06-21 | 95 | 0%
12.1 | Waterproofing | Specialist | 2028-03-19 | 2028-04-02 | 15 | 0%
12.2 | Surfacing | Surfacing | 2028-04-05 | 2028-04-19 | 15 | 0%
12.3 | Parapets & safety barriers | Civil | 2028-04-03 | 2028-05-02 | 30 | 0%
12.4 | Drainage & road markings | Civil | 2028-05-03 | 2028-05-22 | 20 | 0%
12.5 | Load testing & certification | Testing | 2028-05-23 | 2028-06-11 | 20 | 0%
12.6 | Snagging & handover | Main contractor | 2028-06-12 | 2028-06-21 | 10 | 0%
13 | Open to traffic |  | 2028-06-22 | 2028-06-22 | — | —