## Gantt
Bridge Construction Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26
1 | Survey & ground investigation |  | 2026-08-02 | 2026-10-30 | 90
1.1 | Topographic & hydrographic survey | Surveyor | 2026-08-02 | 2026-08-31 | 30
1.2 | Utility searches & trial holes | Civil | 2026-08-22 | 2026-09-20 | 30
1.3 | Boreholes & geotechnical testing | GI contractor | 2026-09-01 | 2026-10-10 | 40
1.4 | Environmental baseline survey | Ecologist | 2026-09-06 | 2026-10-15 | 40
2 | ◆ GI report issued |  | 2026-10-31 | 2026-10-31 | [13 empty] | ◆
3 | Design & approvals |  | 2026-10-16 | 2027-03-29 | 165
3.1 | Preliminary design | Design engineer | 2026-10-16 | 2026-11-29 | 45
3.2 | Detailed design | Design engineer | 2026-11-25 | 2027-02-17 | 85
3.3 | Temporary works design | TW engineer | 2026-12-30 | 2027-02-27 | 60
3.4 | Environmental consent & river licence | Consents lead | 2026-11-20 | 2027-02-17 | 90
3.5 | Technical approval submission | Design engineer | 2027-02-18 | 2027-03-29 | 40
4 | ◆ Technical approval granted |  | 2027-03-30 | 2027-03-30 | [35 empty] | ◆
5 | Enabling works & possessions |  | 2027-01-29 | 2027-06-07 | 130
6 | ◆ Possession application submitted |  | 2027-01-29 | 2027-01-29 | [26 empty] | ◆
7 | ◆ Possession window confirmed |  | 2027-04-19 | 2027-04-19 | [38 empty] | ◆
7.1 | Site set-up & compound | Main contractor | 2027-03-30 | 2027-04-23 | 25
7.2 | Haul road & site access | Civil | 2027-04-14 | 2027-05-13 | 30
7.3 | Utility diversions | Utilities | 2027-03-30 | 2027-05-23 | 55
7.4 | Cofferdam & river works | Marine | 2027-05-09 | 2027-06-07 | 30
8 | Piling & foundations |  | 2027-05-29 | 2027-09-20 | 115
8.1 | Abutment piling | Piling contractor | 2027-05-29 | 2027-07-07 | 40
8.2 | Pier piling | Piling contractor | 2027-06-18 | 2027-08-01 | 45
8.3 | Pile integrity & load testing | Testing | 2027-07-28 | 2027-08-16 | 20
8.4 | Pile caps & foundation concrete | Civil | 2027-08-12 | 2027-09-20 | 40
9 | Substructure |  | 2027-09-21 | 2028-01-18 | 120
9.1 | Abutments & wing walls | Civil | 2027-09-21 | 2027-11-19 | 60
9.2 | Piers & pier caps | Civil | 2027-10-16 | 2027-12-19 | 65
9.3 | Bearing plinths & bearings | Civil | 2027-12-20 | 2028-01-18 | 30
10 | ◆ Substructure complete |  | 2028-01-19 | 2028-01-19 | [77 empty] | ◆
11 | Superstructure & deck |  | 2027-09-26 | 2028-03-18 | 175
11.1 | Beam fabrication | Fabricator | 2027-09-26 | 2028-01-03 | 100
11.2 | Beam delivery to site | Logistics | 2028-01-09 | 2028-01-23 | 15
11.3 | Possession & beam erection | Erection team | 2028-01-24 | 2028-01-28 | 5
11.4 | Deck formwork & reinforcement | Civil | 2028-01-30 | 2028-02-28 | 30
11.5 | Deck concrete pour | Civil | 2028-03-01 | 2028-03-08 | 8
11.6 | Deck cure & strike | Civil | 2028-03-09 | 2028-03-18 | 10
12 | Surfacing, testing & opening |  | 2028-03-19 | 2028-06-21 | 95
12.1 | Waterproofing | Specialist | 2028-03-19 | 2028-04-02 | 15
12.2 | Surfacing | Surfacing | 2028-04-05 | 2028-04-19 | 15
12.3 | Parapets & safety barriers | Civil | 2028-04-03 | 2028-05-02 | 30
12.4 | Drainage & road markings | Civil | 2028-05-03 | 2028-05-22 | 20
12.5 | Load testing & certification | Testing | 2028-05-23 | 2028-06-11 | 20
12.6 | Snagging & handover | Main contractor | 2028-06-12 | 2028-06-21 | 10
13 | ◆ Open to traffic |  | 2028-06-22 | 2028-06-22 | [99 empty] | ◆