## Slide 1
Call Center Setup Plan
Free Gantt chart template · gantts.app

## Slide 2
Call Center Setup Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Operating model & site
Channel mix & hours of operation
Site, remote or hybrid decision
Headcount & cost model
◆ Operating model approved
Technology & telephony
CCaaS selection & contract
Number provisioning & porting
IVR & routing design
CRM & ticketing integration
WFM & quality tooling
Equipment & connectivity
◆ Telephony ready for test
Workforce planning
Volume forecast by interval
AHT & shrinkage assumptions
Erlang staffing model
Shift patterns & schedules
Recruitment waves
Job design & pay banding
Wave 1 sourcing & assessment
◆ Wave 1 offers accepted
Wave 2 sourcing & assessment
Wave 3 sourcing & assessment
Training & knowledge
Curriculum & assessment design
Knowledge base & macros build
Cohort 1 classroom training
Cohort 1 nesting
◆ Cohort 1 certified
Cohort 2 training & nesting
Cohort 3 training & nesting
Pilot, go-live & ramp
Pilot calls on limited queue
Quality calibration & QA scoring
◆ Go-live
Ramp step 1 (cohort 1 live)
Ramp step 2 (cohort 2 live)
Ramp step 3 (cohort 3 live)
Service level review & tuning
◆ Steady state
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Operating model & site |  | 2026-08-02 | 2026-09-20 | 50 | 100%
1.1 | Channel mix & hours of operation | Ops director | 2026-08-02 | 2026-08-21 | 20 | 100%
1.2 | Site, remote or hybrid decision | Ops director | 2026-08-17 | 2026-09-05 | 20 | 100%
1.3 | Headcount & cost model | Finance | 2026-09-01 | 2026-09-20 | 20 | 100%
2 | Operating model approved |  | 2026-09-21 | 2026-09-21 | — | —
3 | Technology & telephony |  | 2026-09-21 | 2027-01-08 | 110 | 55%
3.1 | CCaaS selection & contract | IT | 2026-09-21 | 2026-10-30 | 40 | 100%
3.2 | Number provisioning & porting | Carrier | 2026-10-16 | 2026-12-19 | 65 | 50%
3.3 | IVR & routing design | Ops & IT | 2026-10-31 | 2026-12-04 | 35 | 60%
3.4 | CRM & ticketing integration | IT | 2026-11-05 | 2026-12-19 | 45 | 40%
3.5 | WFM & quality tooling | IT | 2026-11-20 | 2026-12-19 | 30 | 20%
3.6 | Equipment & connectivity | IT | 2026-12-05 | 2027-01-08 | 35 | 10%
4 | Telephony ready for test |  | 2027-01-09 | 2027-01-09 | — | —
5 | Workforce planning |  | 2026-09-11 | 2026-11-09 | 60 | 90%
5.1 | Volume forecast by interval | WFM | 2026-09-11 | 2026-10-05 | 25 | 100%
5.2 | AHT & shrinkage assumptions | WFM | 2026-09-26 | 2026-10-15 | 20 | 100%
5.3 | Erlang staffing model | WFM | 2026-10-11 | 2026-10-30 | 20 | 90%
5.4 | Shift patterns & schedules | WFM | 2026-10-23 | 2026-11-09 | 18 | 70%
6 | Recruitment waves |  | 2026-10-01 | 2027-03-14 | 165 | 40%
6.1 | Job design & pay banding | HR | 2026-10-01 | 2026-10-20 | 20 | 100%
6.2 | Wave 1 sourcing & assessment | HR | 2026-10-21 | 2026-11-24 | 35 | 80%

## Slide 4
7 | Wave 1 offers accepted |  | 2026-11-28 | 2026-11-28 | — | —
7.1 | Wave 2 sourcing & assessment | HR | 2026-12-05 | 2027-01-08 | 35 | 0%
7.2 | Wave 3 sourcing & assessment | HR | 2027-02-03 | 2027-03-14 | 40 | 0%
8 | Training & knowledge |  | 2026-10-11 | 2027-04-18 | 190 | 30%
8.1 | Curriculum & assessment design | Training lead | 2026-10-11 | 2026-11-19 | 40 | 70%
8.2 | Knowledge base & macros build | Content & ops | 2026-10-26 | 2026-12-24 | 60 | 50%
8.3 | Cohort 1 classroom training | Training lead | 2026-12-05 | 2026-12-24 | 20 | 0%
8.4 | Cohort 1 nesting | Team leaders | 2026-12-28 | 2027-01-11 | 15 | 0%
9 | Cohort 1 certified |  | 2027-01-12 | 2027-01-12 | — | —
9.1 | Cohort 2 training & nesting | Training lead | 2027-01-19 | 2027-02-22 | 35 | 0%
9.2 | Cohort 3 training & nesting | Training lead | 2027-03-15 | 2027-04-18 | 35 | 0%
10 | Pilot, go-live & ramp |  | 2027-01-12 | 2027-05-21 | 130 | 0%
10.1 | Pilot calls on limited queue | Cohort 1 | 2027-01-14 | 2027-01-28 | 15 | 0%
10.2 | Quality calibration & QA scoring | QA | 2027-01-21 | 2027-02-09 | 20 | 0%
11 | Go-live |  | 2027-02-13 | 2027-02-13 | — | —
11.1 | Ramp step 1 (cohort 1 live) | Ops | 2027-02-13 | 2027-03-14 | 30 | 0%
11.2 | Ramp step 2 (cohort 2 live) | Ops | 2027-02-26 | 2027-04-11 | 45 | 0%
11.3 | Ramp step 3 (cohort 3 live) | Ops | 2027-04-21 | 2027-05-20 | 30 | 0%
11.4 | Service level review & tuning | WFM & ops | 2027-04-09 | 2027-05-18 | 40 | 0%
12 | Steady state |  | 2027-05-22 | 2027-05-22 | — | —