## Gantt
Call Center Setup Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24
1 | Operating model & site |  | 2026-08-02 | 2026-09-20 | 50
1.1 | Channel mix & hours of operation | Ops director | 2026-08-02 | 2026-08-21 | 20
1.2 | Site, remote or hybrid decision | Ops director | 2026-08-17 | 2026-09-05 | 20
1.3 | Headcount & cost model | Finance | 2026-09-01 | 2026-09-20 | 20
2 | ◆ Operating model approved |  | 2026-09-21 | 2026-09-21 | [8 empty] | ◆
3 | Technology & telephony |  | 2026-09-21 | 2027-01-08 | 110
3.1 | CCaaS selection & contract | IT | 2026-09-21 | 2026-10-30 | 40
3.2 | Number provisioning & porting | Carrier | 2026-10-16 | 2026-12-19 | 65
3.3 | IVR & routing design | Ops & IT | 2026-10-31 | 2026-12-04 | 35
3.4 | CRM & ticketing integration | IT | 2026-11-05 | 2026-12-19 | 45
3.5 | WFM & quality tooling | IT | 2026-11-20 | 2026-12-19 | 30
3.6 | Equipment & connectivity | IT | 2026-12-05 | 2027-01-08 | 35
4 | ◆ Telephony ready for test |  | 2027-01-09 | 2027-01-09 | [23 empty] | ◆
5 | Workforce planning |  | 2026-09-11 | 2026-11-09 | 60
5.1 | Volume forecast by interval | WFM | 2026-09-11 | 2026-10-05 | 25
5.2 | AHT & shrinkage assumptions | WFM | 2026-09-26 | 2026-10-15 | 20
5.3 | Erlang staffing model | WFM | 2026-10-11 | 2026-10-30 | 20
5.4 | Shift patterns & schedules | WFM | 2026-10-23 | 2026-11-09 | 18
6 | Recruitment waves |  | 2026-10-01 | 2027-03-14 | 165
6.1 | Job design & pay banding | HR | 2026-10-01 | 2026-10-20 | 20
6.2 | Wave 1 sourcing & assessment | HR | 2026-10-21 | 2026-11-24 | 35
7 | ◆ Wave 1 offers accepted |  | 2026-11-28 | 2026-11-28 | [17 empty] | ◆
7.1 | Wave 2 sourcing & assessment | HR | 2026-12-05 | 2027-01-08 | 35
7.2 | Wave 3 sourcing & assessment | HR | 2027-02-03 | 2027-03-14 | 40
8 | Training & knowledge |  | 2026-10-11 | 2027-04-18 | 190
8.1 | Curriculum & assessment design | Training lead | 2026-10-11 | 2026-11-19 | 40
8.2 | Knowledge base & macros build | Content & ops | 2026-10-26 | 2026-12-24 | 60
8.3 | Cohort 1 classroom training | Training lead | 2026-12-05 | 2026-12-24 | 20
8.4 | Cohort 1 nesting | Team leaders | 2026-12-28 | 2027-01-11 | 15
9 | ◆ Cohort 1 certified |  | 2027-01-12 | 2027-01-12 | [24 empty] | ◆
9.1 | Cohort 2 training & nesting | Training lead | 2027-01-19 | 2027-02-22 | 35
9.2 | Cohort 3 training & nesting | Training lead | 2027-03-15 | 2027-04-18 | 35
10 | Pilot, go-live & ramp |  | 2027-01-12 | 2027-05-21 | 130
10.1 | Pilot calls on limited queue | Cohort 1 | 2027-01-14 | 2027-01-28 | 15
10.2 | Quality calibration & QA scoring | QA | 2027-01-21 | 2027-02-09 | 20
11 | ◆ Go-live |  | 2027-02-13 | 2027-02-13 | [28 empty] | ◆
11.1 | Ramp step 1 (cohort 1 live) | Ops | 2027-02-13 | 2027-03-14 | 30
11.2 | Ramp step 2 (cohort 2 live) | Ops | 2027-02-26 | 2027-04-11 | 45
11.3 | Ramp step 3 (cohort 3 live) | Ops | 2027-04-21 | 2027-05-20 | 30
11.4 | Service level review & tuning | WFM & ops | 2027-04-09 | 2027-05-18 | 40
12 | ◆ Steady state |  | 2027-05-22 | 2027-05-22 | [42 empty] | ◆