## Slide 1
Change Management Plan
Free Gantt chart template · gantts.app

## Slide 2
Change Management Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Change strategy & impact assessment
Stakeholder mapping & analysis
Change impact assessment by group
Readiness baseline survey
Change strategy & approach
◆ Change strategy approved
Sponsorship & governance
Sponsor coalition identified
Sponsor briefing & commitment session
Change network & champion recruitment
Champion onboarding & cadence
Sponsor roadshow round 1
Resistance log & mitigation plan
◆ Change network live
Communications
Communications plan by audience
Case for change narrative & FAQ
Awareness campaign launch
Manager briefing packs
What-changes-for-me guides per role
Go-live communications sequence
Training
Training needs analysis by role
Curriculum & materials build
Train-the-trainer sessions
Cohort 1 training (pilot group)
Cohort 2 and 3 training
Final cohort training near go-live
◆ Training complete
Go-live readiness & support
Readiness assessment by business unit
Sponsor roadshow round 2
Floor-walker & superuser rota
Go-live readiness sign-off
◆ Go-live
Hypercare floor support
Reinforcement & sustainment
Adoption metrics dashboard
Pulse survey wave 1 (week 2)
Targeted refresher training
Recognition & reinforcement activities
Manager coaching & performance conversations
Pulse survey wave 2 (month 3)
Benefits realisation review
◆ Handover to business as usual
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Change strategy & impact assessment |  | 2026-08-02 | 2026-10-05 | 65 | 100%
1.1 | Stakeholder mapping & analysis | Change lead | 2026-08-02 | 2026-08-21 | 20 | 100%
1.2 | Change impact assessment by group | Change lead | 2026-08-17 | 2026-09-15 | 30 | 100%
1.3 | Readiness baseline survey | Change lead | 2026-09-01 | 2026-09-15 | 15 | 100%
1.4 | Change strategy & approach | Change lead | 2026-09-16 | 2026-10-05 | 20 | 90%
2 | Change strategy approved |  | 2026-10-06 | 2026-10-06 | — | —
3 | Sponsorship & governance |  | 2026-08-22 | 2027-01-08 | 140 | 50%
3.1 | Sponsor coalition identified | Change lead | 2026-08-22 | 2026-09-05 | 15 | 100%
3.2 | Sponsor briefing & commitment session | Sponsor | 2026-09-11 | 2026-09-20 | 10 | 100%
3.3 | Change network & champion recruitment | Change lead | 2026-10-06 | 2026-11-04 | 30 | 60%
3.4 | Champion onboarding & cadence | Change lead | 2026-11-05 | 2026-11-24 | 20 | 30%
3.5 | Sponsor roadshow round 1 | Sponsor | 2026-11-25 | 2026-12-19 | 25 | 0%
3.6 | Resistance log & mitigation plan | Change lead | 2026-12-10 | 2027-01-08 | 30 | 0%
4 | Change network live |  | 2026-12-20 | 2026-12-20 | — | —
5 | Communications |  | 2026-10-06 | 2027-04-03 | 180 | 30%
5.1 | Communications plan by audience | Comms | 2026-10-06 | 2026-10-30 | 25 | 70%
5.2 | Case for change narrative & FAQ | Comms | 2026-10-31 | 2026-11-19 | 20 | 40%
5.3 | Awareness campaign launch | Comms | 2026-11-20 | 2026-12-19 | 30 | 10%
5.4 | Manager briefing packs | Comms | 2026-12-20 | 2027-01-13 | 25 | 0%
5.5 | What-changes-for-me guides per role | Change lead | 2027-01-19 | 2027-02-17 | 30 | 0%
5.6 | Go-live communications sequence | Comms | 2027-03-05 | 2027-04-03 | 30 | 0%

## Slide 4
6 | Training |  | 2026-12-30 | 2027-05-25 | 147 | 0%
6.1 | Training needs analysis by role | Training lead | 2026-12-30 | 2027-01-23 | 25 | 0%
6.2 | Curriculum & materials build | Training lead | 2027-01-24 | 2027-03-09 | 45 | 0%
6.3 | Train-the-trainer sessions | Training lead | 2027-03-15 | 2027-03-29 | 15 | 0%
6.4 | Cohort 1 training (pilot group) | Trainers | 2027-04-09 | 2027-04-23 | 15 | 0%
6.5 | Cohort 2 and 3 training | Trainers | 2027-04-24 | 2027-05-13 | 20 | 0%
6.6 | Final cohort training near go-live | Trainers | 2027-05-14 | 2027-05-25 | 12 | 0%
7 | Training complete |  | 2027-05-26 | 2027-05-26 | — | —
8 | Go-live readiness & support |  | 2027-04-09 | 2027-06-27 | 80 | 0%
8.1 | Readiness assessment by business unit | Change lead | 2027-04-09 | 2027-04-28 | 20 | 0%
8.2 | Sponsor roadshow round 2 | Sponsor | 2027-04-24 | 2027-05-13 | 20 | 0%
8.3 | Floor-walker & superuser rota | Change lead | 2027-05-26 | 2027-06-02 | 8 | 0%
8.4 | Go-live readiness sign-off | Exec | 2027-05-29 | 2027-06-02 | 5 | 0%
9 | Go-live |  | 2027-06-03 | 2027-06-03 | — | —
9.1 | Hypercare floor support | Champions | 2027-06-03 | 2027-06-27 | 25 | 0%
10 | Reinforcement & sustainment |  | 2027-06-03 | 2027-11-09 | 160 | 0%
10.1 | Adoption metrics dashboard | Change lead | 2027-06-03 | 2027-06-22 | 20 | 0%
10.2 | Pulse survey wave 1 (week 2) | Change lead | 2027-06-18 | 2027-06-27 | 10 | 0%
10.3 | Targeted refresher training | Trainers | 2027-07-03 | 2027-07-27 | 25 | 0%
10.4 | Recognition & reinforcement activities | Sponsor | 2027-07-08 | 2027-09-05 | 60 | 0%
10.5 | Manager coaching & performance conversations | Managers | 2027-07-28 | 2027-09-10 | 45 | 0%
10.6 | Pulse survey wave 2 (month 3) | Change lead | 2027-09-01 | 2027-09-10 | 10 | 0%
10.7 | Benefits realisation review | Exec | 2027-09-26 | 2027-10-15 | 20 | 0%
11 | Handover to business as |  | 2027-10-21 | 2027-10-21 | — | —

## Slide 5
 | usual |  |  |  |  |