## Slide 1
Cloud Migration Project Plan
Free Gantt chart template · gantts.app

## Slide 2
Cloud Migration Project Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Discovery & assessment
Application inventory
Dependency mapping
Business criticality & RTO/RPO
7Rs disposition per workload
◆ Application dispositions agreed
Landing zone & foundation
Account & subscription structure
Network & hybrid connectivity
Identity & access model
Security guardrails & policy
Logging, monitoring & FinOps setup
◆ Landing zone live
Wave planning & pilot
Wave grouping by dependency
Migration runbook drafted
Pilot wave migration
Runbook revised from pilot
◆ Pilot wave complete
Migration waves
Wave 1 — build & data sync
Wave 1 — test & validate
Wave 2 — build & data sync
Wave 2 — test & validate
Wave 3 — build & data sync
Wave 3 — test & validate
Cutover & hypercare
Wave 1 cutover weekend
Wave 2 cutover weekend
Wave 3 cutover weekend
◆ Production cutover complete
Hypercare support
Decommission & optimize
Source environment shutdown
Right-sizing & reserved capacity
Data centre contract exit
◆ Source estate decommissioned
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Discovery & assessment |  | 2026-08-02 | 2026-10-30 | 90 | 100%
1.1 | Application inventory | Architecture | 2026-08-02 | 2026-09-05 | 35 | 100%
1.2 | Dependency mapping | Architecture | 2026-08-27 | 2026-10-10 | 45 | 100%
1.3 | Business criticality & RTO/RPO | Business owners | 2026-09-11 | 2026-10-10 | 30 | 100%
1.4 | 7Rs disposition per workload | Architecture | 2026-10-06 | 2026-10-30 | 25 | 100%
2 | Application dispositions agreed |  | 2026-10-31 | 2026-10-31 | — | —
3 | Landing zone & foundation |  | 2026-10-01 | 2027-01-18 | 110 | 80%
3.1 | Account & subscription structure | Cloud platform | 2026-10-01 | 2026-10-30 | 30 | 100%
3.2 | Network & hybrid connectivity | Network | 2026-10-16 | 2026-12-09 | 55 | 90%
3.3 | Identity & access model | Security | 2026-10-31 | 2026-12-09 | 40 | 90%
3.4 | Security guardrails & policy | Security | 2026-11-20 | 2027-01-03 | 45 | 70%
3.5 | Logging, monitoring & FinOps setup | Cloud platform | 2026-12-10 | 2027-01-18 | 40 | 50%
4 | Landing zone live |  | 2027-01-19 | 2027-01-19 | — | —
5 | Wave planning & pilot |  | 2026-11-10 | 2027-03-09 | 120 | 40%
5.1 | Wave grouping by dependency | Migration lead | 2026-11-10 | 2026-12-14 | 35 | 100%
5.2 | Migration runbook drafted | Migration lead | 2026-12-15 | 2027-01-13 | 30 | 60%
5.3 | Pilot wave migration | Migration team | 2027-01-19 | 2027-02-22 | 35 | 0%
5.4 | Runbook revised from pilot | Migration lead | 2027-02-23 | 2027-03-09 | 15 | 0%
6 | Pilot wave complete |  | 2027-03-10 | 2027-03-10 | — | —
7 | Migration waves |  | 2027-03-10 | 2027-09-05 | 180 | 0%
7.1 | Wave 1 — build & data sync | Migration team | 2027-03-10 | 2027-04-18 | 40 | 0%

## Slide 4
7.2 | Wave 1 — test & validate | QA | 2027-04-11 | 2027-05-05 | 25 | 0%
7.3 | Wave 2 — build & data sync | Migration team | 2027-05-04 | 2027-06-17 | 45 | 0%
7.4 | Wave 2 — test & validate | QA | 2027-06-10 | 2027-07-07 | 28 | 0%
7.5 | Wave 3 — build & data sync | Migration team | 2027-07-03 | 2027-08-16 | 45 | 0%
7.6 | Wave 3 — test & validate | QA | 2027-08-12 | 2027-09-05 | 25 | 0%
8 | Cutover & hypercare |  | 2027-05-04 | 2027-10-05 | 155 | 0%
8.1 | Wave 1 cutover weekend | All | 2027-05-06 | 2027-05-08 | 3 | 0%
8.2 | Wave 2 cutover weekend | All | 2027-07-08 | 2027-07-10 | 3 | 0%
8.3 | Wave 3 cutover weekend | All | 2027-09-06 | 2027-09-08 | 3 | 0%
9 | Production cutover complete |  | 2027-09-09 | 2027-09-09 | — | —
9.1 | Hypercare support | Support | 2027-09-09 | 2027-10-08 | 30 | 0%
10 | Decommission & optimize |  | 2027-09-09 | 2027-12-07 | 90 | 0%
10.1 | Source environment shutdown | Infrastructure | 2027-09-21 | 2027-10-30 | 40 | 0%
10.2 | Right-sizing & reserved capacity | FinOps | 2027-10-09 | 2027-11-22 | 45 | 0%
10.3 | Data centre contract exit | Procurement | 2027-10-31 | 2027-12-07 | 38 | 0%
11 | Source estate decommissioned |  | 2027-12-08 | 2027-12-08 | — | —