## Gantt
Cloud Migration Project Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13
1 | Discovery & assessment |  | 2026-08-02 | 2026-10-30 | 90
1.1 | Application inventory | Architecture | 2026-08-02 | 2026-09-05 | 35
1.2 | Dependency mapping | Architecture | 2026-08-27 | 2026-10-10 | 45
1.3 | Business criticality & RTO/RPO | Business owners | 2026-09-11 | 2026-10-10 | 30
1.4 | 7Rs disposition per workload | Architecture | 2026-10-06 | 2026-10-30 | 25
2 | ◆ Application dispositions agreed |  | 2026-10-31 | 2026-10-31 | [13 empty] | ◆
3 | Landing zone & foundation |  | 2026-10-01 | 2027-01-18 | 110
3.1 | Account & subscription structure | Cloud platform | 2026-10-01 | 2026-10-30 | 30
3.2 | Network & hybrid connectivity | Network | 2026-10-16 | 2026-12-09 | 55
3.3 | Identity & access model | Security | 2026-10-31 | 2026-12-09 | 40
3.4 | Security guardrails & policy | Security | 2026-11-20 | 2027-01-03 | 45
3.5 | Logging, monitoring & FinOps setup | Cloud platform | 2026-12-10 | 2027-01-18 | 40
4 | ◆ Landing zone live |  | 2027-01-19 | 2027-01-19 | [25 empty] | ◆
5 | Wave planning & pilot |  | 2026-11-10 | 2027-03-09 | 120
5.1 | Wave grouping by dependency | Migration lead | 2026-11-10 | 2026-12-14 | 35
5.2 | Migration runbook drafted | Migration lead | 2026-12-15 | 2027-01-13 | 30
5.3 | Pilot wave migration | Migration team | 2027-01-19 | 2027-02-22 | 35
5.4 | Runbook revised from pilot | Migration lead | 2027-02-23 | 2027-03-09 | 15
6 | ◆ Pilot wave complete |  | 2027-03-10 | 2027-03-10 | [32 empty] | ◆
7 | Migration waves |  | 2027-03-10 | 2027-09-05 | 180
7.1 | Wave 1 — build & data sync | Migration team | 2027-03-10 | 2027-04-18 | 40
7.2 | Wave 1 — test & validate | QA | 2027-04-11 | 2027-05-05 | 25
7.3 | Wave 2 — build & data sync | Migration team | 2027-05-04 | 2027-06-17 | 45
7.4 | Wave 2 — test & validate | QA | 2027-06-10 | 2027-07-07 | 28
7.5 | Wave 3 — build & data sync | Migration team | 2027-07-03 | 2027-08-16 | 45
7.6 | Wave 3 — test & validate | QA | 2027-08-12 | 2027-09-05 | 25
8 | Cutover & hypercare |  | 2027-05-04 | 2027-10-05 | 155
8.1 | Wave 1 cutover weekend | All | 2027-05-06 | 2027-05-08 | 3
8.2 | Wave 2 cutover weekend | All | 2027-07-08 | 2027-07-10 | 3
8.3 | Wave 3 cutover weekend | All | 2027-09-06 | 2027-09-08 | 3
9 | ◆ Production cutover complete |  | 2027-09-09 | 2027-09-09 | [58 empty] | ◆
9.1 | Hypercare support | Support | 2027-09-09 | 2027-10-08 | 30
10 | Decommission & optimize |  | 2027-09-09 | 2027-12-07 | 90
10.1 | Source environment shutdown | Infrastructure | 2027-09-21 | 2027-10-30 | 40
10.2 | Right-sizing & reserved capacity | FinOps | 2027-10-09 | 2027-11-22 | 45
10.3 | Data centre contract exit | Procurement | 2027-10-31 | 2027-12-07 | 38
11 | ◆ Source estate decommissioned |  | 2027-12-08 | 2027-12-08 | [71 empty] | ◆