## Slide 1
Conference Production Schedule
Free Gantt chart template · gantts.app

## Slide 2
Conference Production Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Venue & dates
Date selection & sector calendar check
Venue search & site visits
Venue contract & deposit
◆ Venue contracted
Hotel room block
Call for papers & programme
Themes & track structure
◆ Call for papers open
Submission period
◆ Submission deadline
Review & scoring
Selection & notifications
Agenda build & session timing
◆ Agenda published
Speakers
Keynote invitations
◆ Keynotes confirmed
Speaker agreements
Speaker travel & accommodation
Speaker briefings
◆ Slide deadline
Speaker rehearsals
Sponsorship & exhibition
Prospectus & tier pricing
Sponsor outreach & renewals
Sponsor contracting
◆ Sponsorship target hit
Exhibitor floor plan
Sponsor deliverable collection
Registration & marketing
Ticketing platform build
Early-bird tier open
Launch campaign
◆ Early-bird closes
Standard tier & email waves
Late tier & final push
Delegate joining instructions
Production & run of show
AV & staging brief
Room specs per track
Signage, print & badges
Crew & volunteer briefings
Run of show finalised
Build & venue set-up
◆ Doors open
Conference days
Derig & venue handback
Delegate survey & sponsor reports
Debrief & next-year dates
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Venue & dates |  | 2026-08-02 | 2026-10-15 | 75 | 100%
1.1 | Date selection & sector calendar check | Chair | 2026-08-02 | 2026-08-21 | 20 | 100%
1.2 | Venue search & site visits | Producer | 2026-08-17 | 2026-09-20 | 35 | 100%
1.3 | Venue contract & deposit | Producer | 2026-09-19 | 2026-10-13 | 25 | 100%
2 | Venue contracted |  | 2026-10-14 | 2026-10-14 | — | —
2.1 | Hotel room block | Producer | 2026-10-16 | 2026-11-04 | 20 | 100%
3 | Call for papers & programme |  | 2026-10-01 | 2027-03-24 | 175 | 60%
3.1 | Themes & track structure | Programme committee | 2026-10-01 | 2026-10-25 | 25 | 100%
4 | Call for papers open |  | 2026-10-31 | 2026-10-31 | — | —
4.1 | Submission period | Programme committee | 2026-10-31 | 2027-01-13 | 75 | 100%
5 | Submission deadline |  | 2027-01-14 | 2027-01-14 | — | —
5.1 | Review & scoring | Reviewers | 2027-01-14 | 2027-02-17 | 35 | 40%
5.2 | Selection & notifications | Programme committee | 2027-02-16 | 2027-03-07 | 20 | 0%
5.3 | Agenda build & session timing | Producer | 2027-03-05 | 2027-03-24 | 20 | 0%
6 | Agenda published |  | 2027-03-25 | 2027-03-25 | — | —
7 | Speakers |  | 2026-09-11 | 2027-06-22 | 285 | 30%
7.1 | Keynote invitations | Chair | 2026-09-11 | 2026-10-25 | 45 | 100%
8 | Keynotes confirmed |  | 2026-10-29 | 2026-10-29 | — | —
8.1 | Speaker agreements | Producer | 2027-03-08 | 2027-04-11 | 35 | 0%
8.2 | Speaker travel & accommodation | Producer | 2027-03-30 | 2027-05-18 | 50 | 0%
8.3 | Speaker briefings | Producer | 2027-05-04 | 2027-06-02 | 30 | 0%

## Slide 4
9 | Slide deadline |  | 2027-06-08 | 2027-06-08 | — | —
9.1 | Speaker rehearsals | AV & producer | 2027-06-10 | 2027-06-22 | 13 | 0%
10 | Sponsorship & exhibition |  | 2026-09-16 | 2027-05-23 | 250 | 45%
10.1 | Prospectus & tier pricing | Commercial | 2026-09-16 | 2026-10-15 | 30 | 100%
10.2 | Sponsor outreach & renewals | Commercial | 2026-10-16 | 2027-03-04 | 140 | 55%
10.3 | Sponsor contracting | Commercial | 2026-11-20 | 2027-03-19 | 120 | 40%
11 | Sponsorship target hit |  | 2027-03-25 | 2027-03-25 | — | —
11.1 | Exhibitor floor plan | Producer | 2027-03-25 | 2027-04-23 | 30 | 0%
11.2 | Sponsor deliverable collection | Commercial | 2027-04-14 | 2027-05-23 | 40 | 0%
12 | Registration & marketing |  | 2026-11-10 | 2027-06-22 | 225 | 35%
12.1 | Ticketing platform build | Marketing | 2026-11-10 | 2026-12-09 | 30 | 100%
12.2 | Early-bird tier open | Marketing | 2026-12-12 | 2027-02-09 | 60 | 60%
12.3 | Launch campaign | Marketing | 2026-12-12 | 2027-01-25 | 45 | 70%
13 | Early-bird closes |  | 2027-03-30 | 2027-03-30 | — | —
13.1 | Standard tier & email waves | Marketing | 2027-03-30 | 2027-05-28 | 60 | 0%
13.2 | Late tier & final push | Marketing | 2027-05-29 | 2027-06-19 | 22 | 0%
13.3 | Delegate joining instructions | Marketing | 2027-06-08 | 2027-06-19 | 12 | 0%
14 | Production & run of show |  | 2027-03-20 | 2027-07-27 | 130 | 10%
14.1 | AV & staging brief | Producer | 2027-03-20 | 2027-04-23 | 35 | 30%
14.2 | Room specs per track | AV | 2027-04-21 | 2027-05-15 | 25 | 0%
14.3 | Signage, print & badges | Producer | 2027-05-09 | 2027-06-12 | 35 | 0%
14.4 | Crew & volunteer briefings | Producer | 2027-06-03 | 2027-06-22 | 20 | 0%
14.5 | Run of show finalised | Producer | 2027-06-18 | 2027-06-22 | 5 | 0%
14.6 | Build & venue set-up | AV & crew | 2027-06-23 | 2027-06-24 | 2 | 0%

## Slide 5
15 | Doors open |  | 2027-06-25 | 2027-06-25 | — | —
15.1 | Conference days | All | 2027-06-25 | 2027-06-27 | 3 | 0%
15.2 | Derig & venue handback | AV & crew | 2027-06-28 | 2027-06-29 | 2 | 0%
15.3 | Delegate survey & sponsor reports | Marketing | 2027-06-29 | 2027-07-18 | 20 | 0%
15.4 | Debrief & next-year dates | Chair | 2027-07-13 | 2027-07-22 | 10 | 0%