## Gantt
CRM Implementation Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5
1 | Discovery & process design |  | 2026-08-02 | 2026-09-27 | 57
1.1 | Sales process & stage definitions | Sales ops | 2026-08-02 | 2026-08-26 | 25
1.2 | Pipeline & forecast definitions | Sales ops | 2026-08-17 | 2026-09-05 | 20
1.3 | Field & object design | CRM admin | 2026-09-01 | 2026-09-25 | 25
1.4 | Reporting & KPI requirements | Sales ops | 2026-09-11 | 2026-09-25 | 15
2 | ◆ Design signed off |  | 2026-09-28 | 2026-09-28 | [9 empty] | ◆
3 | Data audit, cleanse & dedupe |  | 2026-08-22 | 2027-01-08 | 140
3.1 | Source system inventory & extract | Data lead | 2026-08-22 | 2026-09-10 | 20
3.2 | Data quality profiling | Data lead | 2026-09-06 | 2026-10-05 | 30
3.3 | Deduplication rules & match keys | Data lead | 2026-10-01 | 2026-10-25 | 25
3.4 | Automated dedupe pass | Data lead | 2026-10-26 | 2026-11-14 | 20
3.5 | Sales-owned record remediation | Sales reps | 2026-11-10 | 2027-01-03 | 55
3.6 | Account hierarchy & territory clean-up | Sales ops | 2026-11-30 | 2027-01-03 | 35
4 | ◆ Data ready for migration rehearsal |  | 2027-01-09 | 2027-01-09 | [23 empty] | ◆
5 | Configuration & integration |  | 2026-09-28 | 2027-01-26 | 121
5.1 | Core object & workflow configuration | CRM admin | 2026-09-28 | 2026-11-11 | 45
5.2 | Permissions, roles & territory model | CRM admin | 2026-11-05 | 2026-11-29 | 25
5.3 | Email, calendar & telephony integration | IT | 2026-11-10 | 2026-12-14 | 35
5.4 | Marketing automation sync | Marketing ops | 2026-11-25 | 2026-12-24 | 30
5.5 | Quoting & ERP integration | IT | 2026-12-05 | 2027-01-13 | 40
5.6 | Reports & forecast dashboards | Sales ops | 2026-12-30 | 2027-01-26 | 28
6 | ◆ Configuration complete |  | 2027-01-27 | 2027-01-27 | [26 empty] | ◆
7 | Migration rehearsals |  | 2027-01-09 | 2027-03-29 | 80
7.1 | Migration rehearsal 1 (mapping test) | Data lead | 2027-01-09 | 2027-01-12 | 4
7.2 | Reconcile & fix rehearsal 1 defects | Data lead | 2027-01-13 | 2027-02-01 | 20
7.3 | Migration rehearsal 2 (deduped data) | Data lead | 2027-02-08 | 2027-02-11 | 4
7.4 | Sales validation of sample accounts | Sales reps | 2027-02-13 | 2027-03-04 | 20
7.5 | Timed rehearsal at full volume | Data lead | 2027-03-10 | 2027-03-13 | 4
8 | ◆ Migration rehearsal signed off |  | 2027-03-30 | 2027-03-30 | [35 empty] | ◆
9 | Training & adoption |  | 2027-01-27 | 2027-04-26 | 90
9.1 | Role-based training content | Enablement | 2027-01-27 | 2027-02-25 | 30
9.2 | Manager forecasting workshops | Enablement | 2027-03-05 | 2027-03-19 | 15
9.3 | Rep training cohorts | Enablement | 2027-03-20 | 2027-04-13 | 25
9.4 | Champion network & floor support plan | Sales ops | 2027-03-30 | 2027-04-18 | 20
10 | ◆ Training complete |  | 2027-04-27 | 2027-04-27 | [39 empty] | ◆
11 | Cutover & first forecast cycle |  | 2027-03-30 | 2027-07-02 | 95
11.1 | Quarter-boundary cutover window agreed | Sales leadership | 2027-03-30 | 2027-04-08 | 10
11.2 | Legacy CRM freeze | Data lead | 2027-04-27 | 2027-04-28 | 2
11.3 | Production data load | Data lead | 2027-04-29 | 2027-05-01 | 3
11.4 | Pipeline reconciliation vs legacy | Sales ops | 2027-05-02 | 2027-05-08 | 7
12 | ◆ Go-live |  | 2027-05-11 | 2027-05-11 | [41 empty] | ◆
12.1 | Hypercare & floor support | Sales ops | 2027-05-11 | 2027-06-04 | 25
12.2 | First full forecast cycle in new CRM | Sales leadership | 2027-05-19 | 2027-06-17 | 30
12.3 | Adoption metrics review & backlog | Sales ops | 2027-06-18 | 2027-07-02 | 15