## Slide 1
Crop Planting & Harvest
Free Gantt chart template · gantts.app

## Slide 2
Crop Planting & Harvest
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Winter planning, agronomy & inputs
Field-by-field cropping plan & rotation
Soil sampling, nutrient & pH results
Machinery service, calibration & spare parts
Seed, fertiliser & chemical ordering
Labour and contractor bookings for the season
◆ Inputs delivered and stored on farm
Seedbed preparation & planting window
Soil temperature & moisture monitoring
Primary cultivation & seedbed preparation
◆ Planting window opens
Pre-emergence herbicide & starter fertiliser
Drilling — early fields
Drilling — main block
Drilling — late and wet fields
◆ Drilling complete
Emergence & crop growth stages
Emergence counts & establishment assessment
Tillering and early vegetative growth
Stem extension & canopy closure
Flowering and grain fill
Weekly crop walking & pest scouting
Irrigation scheduling from soil moisture probes
Spray & nutrition programme
Post-emergence herbicide at early tillering
First nitrogen split
T1 fungicide at stem extension
Second nitrogen split & trace elements
T2 flag leaf fungicide
T3 ear spray at flowering
◆ Spray programme complete
Harvest & field logistics
Combine, trailer & cart fleet readiness
Grain moisture testing & harvest readiness
◆ Harvest window opens at target moisture
Harvest — early fields
Grain carting & weighbridge logistics
Harvest — main block
Harvest — late fields
◆ Harvest complete
Drying, storage & post-harvest
Continuous drier throughput & moisture control
Store filling, aeration & temperature monitoring
Grain sampling, grading & assurance records
Contract deliveries & haulage out
Post-harvest cultivation & cover crop drilling
Season review & next rotation plan
◆ Crop year closed out
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Winter planning, agronomy & inputs |  | 2026-08-02 | 2026-11-09 | 100 | 100%
1.1 | Field-by-field cropping plan & rotation | Farm manager | 2026-08-02 | 2026-08-31 | 30 | 100%
1.2 | Soil sampling, nutrient & pH results | Agronomist | 2026-08-12 | 2026-09-15 | 35 | 100%
1.3 | Machinery service, calibration & spare parts | Workshop | 2026-09-01 | 2026-10-20 | 50 | 100%
1.4 | Seed, fertiliser & chemical ordering | Farm manager | 2026-09-11 | 2026-10-20 | 40 | 100%
1.5 | Labour and contractor bookings for the season | Farm manager | 2026-09-26 | 2026-10-30 | 35 | 90%
2 | Inputs delivered and stored on farm |  | 2026-11-05 | 2026-11-05 | — | —
3 | Seedbed preparation & planting window |  | 2026-11-05 | 2027-01-18 | 75 | 40%
3.1 | Soil temperature & moisture monitoring | Agronomist | 2026-11-05 | 2026-12-09 | 35 | 100%
3.2 | Primary cultivation & seedbed preparation | Machinery | 2026-11-15 | 2026-12-14 | 30 | 80%
4 | Planting window opens |  | 2026-12-10 | 2026-12-10 | — | —
4.1 | Pre-emergence herbicide & starter fertiliser | Sprayer | 2026-12-08 | 2026-12-19 | 12 | 30%
4.2 | Drilling — early fields | Machinery | 2026-12-10 | 2026-12-23 | 14 | 20%
4.3 | Drilling — main block | Machinery | 2026-12-22 | 2027-01-08 | 18 | 0%
4.4 | Drilling — late and wet fields | Machinery | 2027-01-07 | 2027-01-18 | 12 | 0%
5 | Drilling complete |  | 2027-01-19 | 2027-01-19 | — | —
6 | Emergence & crop growth stages |  | 2027-01-19 | 2027-06-27 | 160 | 0%
6.1 | Emergence counts & establishment assessment | Agronomist | 2027-01-19 | 2027-02-07 | 20 | 0%
6.2 | Tillering and early vegetative growth | Crop | 2027-02-08 | 2027-03-24 | 45 | 0%
6.3 | Stem extension & canopy closure | Crop | 2027-03-25 | 2027-05-03 | 40 | 0%
6.4 | Flowering and grain fill | Crop | 2027-05-04 | 2027-06-27 | 55 | 0%

## Slide 4
6.5 | Weekly crop walking & pest scouting | Agronomist | 2027-01-24 | 2027-06-27 | 155 | 0%
6.6 | Irrigation scheduling from soil moisture probes | Irrigation | 2027-02-18 | 2027-06-17 | 120 | 0%
7 | Spray & nutrition programme |  | 2027-02-08 | 2027-07-07 | 150 | 0%
7.1 | Post-emergence herbicide at early tillering | Sprayer | 2027-02-18 | 2027-02-27 | 10 | 0%
7.2 | First nitrogen split | Machinery | 2027-02-28 | 2027-03-07 | 8 | 0%
7.3 | T1 fungicide at stem extension | Sprayer | 2027-03-30 | 2027-04-06 | 8 | 0%
7.4 | Second nitrogen split & trace elements | Machinery | 2027-04-09 | 2027-04-16 | 8 | 0%
7.5 | T2 flag leaf fungicide | Sprayer | 2027-04-27 | 2027-05-04 | 8 | 0%
7.6 | T3 ear spray at flowering | Sprayer | 2027-05-14 | 2027-05-21 | 8 | 0%
8 | Spray programme complete |  | 2027-06-28 | 2027-06-28 | — | —
9 | Harvest & field logistics |  | 2027-06-18 | 2027-09-05 | 80 | 0%
9.1 | Combine, trailer & cart fleet readiness | Workshop | 2027-06-18 | 2027-07-02 | 15 | 0%
9.2 | Grain moisture testing & harvest readiness | Agronomist | 2027-06-28 | 2027-07-12 | 15 | 0%
10 | Harvest window opens at target moisture |  | 2027-07-13 | 2027-07-13 | — | —
10.1 | Harvest — early fields | Harvest crew | 2027-07-13 | 2027-07-24 | 12 | 0%
10.2 | Grain carting & weighbridge logistics | Logistics | 2027-07-13 | 2027-08-26 | 45 | 0%
10.3 | Harvest — main block | Harvest crew | 2027-07-23 | 2027-08-11 | 20 | 0%
10.4 | Harvest — late fields | Harvest crew | 2027-08-10 | 2027-08-24 | 15 | 0%
11 | Harvest complete |  | 2027-08-27 | 2027-08-27 | — | —
12 | Drying, storage & post-harvest |  | 2027-07-13 | 2027-10-30 | 110 | 0%
12.1 | Continuous drier throughput & moisture control | Store | 2027-07-13 | 2027-08-31 | 50 | 0%
12.2 | Store filling, aeration & temperature monitoring | Store | 2027-07-23 | 2027-09-20 | 60 | 0%

## Slide 5
12.3 | Grain sampling, grading & assurance records | Store | 2027-08-17 | 2027-09-15 | 30 | 0%
12.4 | Contract deliveries & haulage out | Logistics | 2027-09-01 | 2027-10-15 | 45 | 0%
12.5 | Post-harvest cultivation & cover crop drilling | Machinery | 2027-09-01 | 2027-10-05 | 35 | 0%
12.6 | Season review & next rotation plan | Farm manager | 2027-10-06 | 2027-10-30 | 25 | 0%
13 | Crop year closed out |  | 2027-10-31 | 2027-10-31 | — | —