## Gantt
Crop Planting & Harvest
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1
1 | Winter planning, agronomy & inputs |  | 2026-08-02 | 2026-11-09 | 100
1.1 | Field-by-field cropping plan & rotation | Farm manager | 2026-08-02 | 2026-08-31 | 30
1.2 | Soil sampling, nutrient & pH results | Agronomist | 2026-08-12 | 2026-09-15 | 35
1.3 | Machinery service, calibration & spare parts | Workshop | 2026-09-01 | 2026-10-20 | 50
1.4 | Seed, fertiliser & chemical ordering | Farm manager | 2026-09-11 | 2026-10-20 | 40
1.5 | Labour and contractor bookings for the season | Farm manager | 2026-09-26 | 2026-10-30 | 35
2 | ◆ Inputs delivered and stored on farm |  | 2026-11-05 | 2026-11-05 | [14 empty] | ◆
3 | Seedbed preparation & planting window |  | 2026-11-05 | 2027-01-18 | 75
3.1 | Soil temperature & moisture monitoring | Agronomist | 2026-11-05 | 2026-12-09 | 35
3.2 | Primary cultivation & seedbed preparation | Machinery | 2026-11-15 | 2026-12-14 | 30
4 | ◆ Planting window opens |  | 2026-12-10 | 2026-12-10 | [19 empty] | ◆
4.1 | Pre-emergence herbicide & starter fertiliser | Sprayer | 2026-12-08 | 2026-12-19 | 12
4.2 | Drilling — early fields | Machinery | 2026-12-10 | 2026-12-23 | 14
4.3 | Drilling — main block | Machinery | 2026-12-22 | 2027-01-08 | 18
4.4 | Drilling — late and wet fields | Machinery | 2027-01-07 | 2027-01-18 | 12
5 | ◆ Drilling complete |  | 2027-01-19 | 2027-01-19 | [25 empty] | ◆
6 | Emergence & crop growth stages |  | 2027-01-19 | 2027-06-27 | 160
6.1 | Emergence counts & establishment assessment | Agronomist | 2027-01-19 | 2027-02-07 | 20
6.2 | Tillering and early vegetative growth | Crop | 2027-02-08 | 2027-03-24 | 45
6.3 | Stem extension & canopy closure | Crop | 2027-03-25 | 2027-05-03 | 40
6.4 | Flowering and grain fill | Crop | 2027-05-04 | 2027-06-27 | 55
6.5 | Weekly crop walking & pest scouting | Agronomist | 2027-01-24 | 2027-06-27 | 155
6.6 | Irrigation scheduling from soil moisture probes | Irrigation | 2027-02-18 | 2027-06-17 | 120
7 | Spray & nutrition programme |  | 2027-02-08 | 2027-07-07 | 150
7.1 | Post-emergence herbicide at early tillering | Sprayer | 2027-02-18 | 2027-02-27 | 10
7.2 | First nitrogen split | Machinery | 2027-02-28 | 2027-03-07 | 8
7.3 | T1 fungicide at stem extension | Sprayer | 2027-03-30 | 2027-04-06 | 8
7.4 | Second nitrogen split & trace elements | Machinery | 2027-04-09 | 2027-04-16 | 8
7.5 | T2 flag leaf fungicide | Sprayer | 2027-04-27 | 2027-05-04 | 8
7.6 | T3 ear spray at flowering | Sprayer | 2027-05-14 | 2027-05-21 | 8
8 | ◆ Spray programme complete |  | 2027-06-28 | 2027-06-28 | [48 empty] | ◆
9 | Harvest & field logistics |  | 2027-06-18 | 2027-09-05 | 80
9.1 | Combine, trailer & cart fleet readiness | Workshop | 2027-06-18 | 2027-07-02 | 15
9.2 | Grain moisture testing & harvest readiness | Agronomist | 2027-06-28 | 2027-07-12 | 15
10 | ◆ Harvest window opens at target moisture |  | 2027-07-13 | 2027-07-13 | [50 empty] | ◆
10.1 | Harvest — early fields | Harvest crew | 2027-07-13 | 2027-07-24 | 12
10.2 | Grain carting & weighbridge logistics | Logistics | 2027-07-13 | 2027-08-26 | 45
10.3 | Harvest — main block | Harvest crew | 2027-07-23 | 2027-08-11 | 20
10.4 | Harvest — late fields | Harvest crew | 2027-08-10 | 2027-08-24 | 15
11 | ◆ Harvest complete |  | 2027-08-27 | 2027-08-27 | [56 empty] | ◆
12 | Drying, storage & post-harvest |  | 2027-07-13 | 2027-10-30 | 110
12.1 | Continuous drier throughput & moisture control | Store | 2027-07-13 | 2027-08-31 | 50
12.2 | Store filling, aeration & temperature monitoring | Store | 2027-07-23 | 2027-09-20 | 60
12.3 | Grain sampling, grading & assurance records | Store | 2027-08-17 | 2027-09-15 | 30
12.4 | Contract deliveries & haulage out | Logistics | 2027-09-01 | 2027-10-15 | 45
12.5 | Post-harvest cultivation & cover crop drilling | Machinery | 2027-09-01 | 2027-10-05 | 35
12.6 | Season review & next rotation plan | Farm manager | 2027-10-06 | 2027-10-30 | 25
13 | ◆ Crop year closed out |  | 2027-10-31 | 2027-10-31 | [66 empty] | ◆