## Slide 1
Crowdfunding Campaign
Free Gantt chart template · gantts.app

## Slide 2
Crowdfunding Campaign
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Concept & validation
Define idea & value proposition
Research market & competitors
Set funding goal & budget
Design reward tiers & pricing
Choose platform (Kickstarter/Indiegogo)
◆ Concept validated
Build campaign assets
Build prototype & samples
Script & film the pitch video
Write the campaign page
Design graphics & images
◆ Assets ready
Pre-launch audience
Build a landing page
Grow the email list
Community & social media
Line up press & influencers
Secure early-bird commitments (20% of goal)
◆ Pre-launch list ready
Launch prep
Final page review & test
Set launch date & warm up the list
Prepare launch-day emails & posts
◆ Ready to launch
Campaign live
Launch day
Daily updates & backer engagement
Mid-campaign press push
Announce stretch goals
Final 48-hour push
◆ Campaign funded
Close & fulfilment
Thank backers & close campaign
Send pledge-manager surveys
Finalize production
Fulfil & ship rewards
◆ Rewards delivered
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Concept & validation |  | 2026-08-02 | 2026-08-22 | 21 | 100%
1.1 | Define idea & value proposition | Creator | 2026-08-02 | 2026-08-06 | 5 | 100%
1.2 | Research market & competitors | Creator | 2026-08-05 | 2026-08-11 | 7 | 90%
1.3 | Set funding goal & budget | Creator | 2026-08-09 | 2026-08-13 | 5 | 70%
1.4 | Design reward tiers & pricing | Creator | 2026-08-12 | 2026-08-18 | 7 | 50%
1.5 | Choose platform (Kickstarter/Indiegogo) | Creator | 2026-08-14 | 2026-08-17 | 4 | 40%
2 | Concept validated |  | 2026-08-23 | 2026-08-23 | , | ,
3 | Build campaign assets |  | 2026-08-20 | 2026-09-23 | 35 | 0%
3.1 | Build prototype & samples | Creator | 2026-08-20 | 2026-09-13 | 25 | 20%
3.2 | Script & film the pitch video | Creator | 2026-08-23 | 2026-09-11 | 20 | 0%
3.3 | Write the campaign page | Creator | 2026-08-30 | 2026-09-12 | 14 | 0%
3.4 | Design graphics & images | Creator | 2026-09-01 | 2026-09-12 | 12 | 0%
4 | Assets ready |  | 2026-09-24 | 2026-09-24 | , | ,
5 | Pre-launch audience |  | 2026-08-30 | 2026-10-10 | 42 | 0%
5.1 | Build a landing page | Creator | 2026-08-30 | 2026-09-03 | 5 | 0%
5.2 | Grow the email list | Creator | 2026-09-04 | 2026-10-08 | 35 | 0%
5.3 | Community & social media | Creator | 2026-09-04 | 2026-10-08 | 35 | 0%
5.4 | Line up press & influencers | PR | 2026-09-16 | 2026-09-30 | 15 | 0%
5.5 | Secure early-bird commitments (20% of goal) | Creator | 2026-09-21 | 2026-10-08 | 18 | 0%
6 | Pre-launch list ready |  | 2026-10-11 | 2026-10-11 | , | ,
7 | Launch prep |  | 2026-10-01 | 2026-10-10 | 10 | 0%

## Slide 4
7.1 | Final page review & test | Creator | 2026-10-01 | 2026-10-04 | 4 | 0%
7.2 | Set launch date & warm up the list | Creator | 2026-10-03 | 2026-10-07 | 5 | 0%
7.3 | Prepare launch-day emails & posts | Creator | 2026-10-05 | 2026-10-08 | 4 | 0%
8 | Ready to launch |  | 2026-10-11 | 2026-10-11 | , | ,
9 | Campaign live |  | 2026-10-11 | 2026-11-09 | 30 | 0%
9.1 | Launch day | Creator | 2026-10-11 | 2026-10-11 | 1 | 0%
9.2 | Daily updates & backer engagement | Creator | 2026-10-11 | 2026-11-09 | 30 | 0%
9.3 | Mid-campaign press push | PR | 2026-10-21 | 2026-10-27 | 7 | 0%
9.4 | Announce stretch goals | Creator | 2026-10-26 | 2026-11-04 | 10 | 0%
9.5 | Final 48-hour push | Creator | 2026-11-08 | 2026-11-09 | 2 | 0%
10 | Campaign funded |  | 2026-11-10 | 2026-11-10 | , | ,
11 | Close & fulfilment |  | 2026-11-10 | 2026-12-07 | 28 | 0%
11.1 | Thank backers & close campaign | Creator | 2026-11-10 | 2026-11-12 | 3 | 0%
11.2 | Send pledge-manager surveys | Ops | 2026-11-12 | 2026-11-18 | 7 | 0%
11.3 | Finalize production | Ops | 2026-11-15 | 2026-12-02 | 18 | 0%
11.4 | Fulfil & ship rewards | Ops | 2026-11-28 | 2026-12-07 | 10 | 0%
12 | Rewards delivered |  | 2026-12-08 | 2026-12-08 | , | ,