## Gantt
Crowdfunding Campaign
Made free at gantts.app, edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14
1 | Concept & validation |  | 2026-08-02 | 2026-08-22 | 21
1.1 | Define idea & value proposition | Creator | 2026-08-02 | 2026-08-06 | 5
1.2 | Research market & competitors | Creator | 2026-08-05 | 2026-08-11 | 7
1.3 | Set funding goal & budget | Creator | 2026-08-09 | 2026-08-13 | 5
1.4 | Design reward tiers & pricing | Creator | 2026-08-12 | 2026-08-18 | 7
1.5 | Choose platform (Kickstarter/Indiegogo) | Creator | 2026-08-14 | 2026-08-17 | 4
2 | ◆ Concept validated |  | 2026-08-23 | 2026-08-23 |  |  |  |  | ◆
3 | Build campaign assets |  | 2026-08-20 | 2026-09-23 | 35
3.1 | Build prototype & samples | Creator | 2026-08-20 | 2026-09-13 | 25
3.2 | Script & film the pitch video | Creator | 2026-08-23 | 2026-09-11 | 20
3.3 | Write the campaign page | Creator | 2026-08-30 | 2026-09-12 | 14
3.4 | Design graphics & images | Creator | 2026-09-01 | 2026-09-12 | 12
4 | ◆ Assets ready |  | 2026-09-24 | 2026-09-24 | [8 empty] | ◆
5 | Pre-launch audience |  | 2026-08-30 | 2026-10-10 | 42
5.1 | Build a landing page | Creator | 2026-08-30 | 2026-09-03 | 5
5.2 | Grow the email list | Creator | 2026-09-04 | 2026-10-08 | 35
5.3 | Community & social media | Creator | 2026-09-04 | 2026-10-08 | 35
5.4 | Line up press & influencers | PR | 2026-09-16 | 2026-09-30 | 15
5.5 | Secure early-bird commitments (20% of goal) | Creator | 2026-09-21 | 2026-10-08 | 18
6 | ◆ Pre-launch list ready |  | 2026-10-11 | 2026-10-11 | [11 empty] | ◆
7 | Launch prep |  | 2026-10-01 | 2026-10-10 | 10
7.1 | Final page review & test | Creator | 2026-10-01 | 2026-10-04 | 4
7.2 | Set launch date & warm up the list | Creator | 2026-10-03 | 2026-10-07 | 5
7.3 | Prepare launch-day emails & posts | Creator | 2026-10-05 | 2026-10-08 | 4
8 | ◆ Ready to launch |  | 2026-10-11 | 2026-10-11 | [11 empty] | ◆
9 | Campaign live |  | 2026-10-11 | 2026-11-09 | 30
9.1 | Launch day | Creator | 2026-10-11 | 2026-10-11 | 1
9.2 | Daily updates & backer engagement | Creator | 2026-10-11 | 2026-11-09 | 30
9.3 | Mid-campaign press push | PR | 2026-10-21 | 2026-10-27 | 7
9.4 | Announce stretch goals | Creator | 2026-10-26 | 2026-11-04 | 10
9.5 | Final 48-hour push | Creator | 2026-11-08 | 2026-11-09 | 2
10 | ◆ Campaign funded |  | 2026-11-10 | 2026-11-10 | [15 empty] | ◆
11 | Close & fulfilment |  | 2026-11-10 | 2026-12-07 | 28
11.1 | Thank backers & close campaign | Creator | 2026-11-10 | 2026-11-12 | 3
11.2 | Send pledge-manager surveys | Ops | 2026-11-12 | 2026-11-18 | 7
11.3 | Finalize production | Ops | 2026-11-15 | 2026-12-02 | 18
11.4 | Fulfil & ship rewards | Ops | 2026-11-28 | 2026-12-07 | 10
12 | ◆ Rewards delivered |  | 2026-12-08 | 2026-12-08 | [19 empty] | ◆