## Slide 1
Data Center Build Schedule
Free Gantt chart template · gantts.app

## Slide 2
Data Center Build Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Site selection & power
Site search & shortlist
Utility capacity confirmation
Fibre route survey
Land acquisition
◆ Power secured
Design & permitting
Concept design & topology
Detailed design
Planning & building permits
◆ Permit granted
Long-lead procurement
Generators & UPS order
Switchgear & transformers order
Chillers & cooling plant order
Shell & core
Earthworks & foundations
Structure & envelope
Roof & weathertight
MEP fit-out
Electrical distribution
Generators & UPS install
Cooling plant install
Fire suppression & security
Raised floor & containment
Commissioning & handover
Levels 1-3 commissioning
Level 4 functional testing
Level 5 integrated systems test
IT deployment
◆ Service ready
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Site selection & power |  | 2026-08-02 | 2026-12-29 | 150 | 100%
1.1 | Site search & shortlist | Development | 2026-08-02 | 2026-09-20 | 50 | 100%
1.2 | Utility capacity confirmation | Development | 2026-09-11 | 2026-11-19 | 70 | 100%
1.3 | Fibre route survey | Network | 2026-10-01 | 2026-11-09 | 40 | 100%
1.4 | Land acquisition | Legal | 2026-11-10 | 2026-12-29 | 50 | 100%
2 | Power secured |  | 2026-12-30 | 2026-12-30 | — | —
3 | Design & permitting |  | 2026-11-20 | 2027-04-08 | 140 | 80%
3.1 | Concept design & topology | Engineering | 2026-11-20 | 2027-01-03 | 45 | 100%
3.2 | Detailed design | Engineering | 2026-12-30 | 2027-03-29 | 90 | 80%
3.3 | Planning & building permits | Consultant | 2027-01-19 | 2027-04-08 | 80 | 60%
4 | Permit granted |  | 2027-04-09 | 2027-04-09 | — | —
5 | Long-lead procurement |  | 2027-02-18 | 2027-11-04 | 260 | 40%
5.1 | Generators & UPS order | Procurement | 2027-02-18 | 2027-10-15 | 240 | 40%
5.2 | Switchgear & transformers order | Procurement | 2027-02-28 | 2027-11-04 | 250 | 35%
5.3 | Chillers & cooling plant order | Procurement | 2027-03-20 | 2027-10-05 | 200 | 30%
6 | Shell & core |  | 2027-04-09 | 2027-10-05 | 180 | 10%
6.1 | Earthworks & foundations | Civil | 2027-04-09 | 2027-06-07 | 60 | 20%
6.2 | Structure & envelope | Structural | 2027-05-29 | 2027-08-26 | 90 | 5%
6.3 | Roof & weathertight | Structural | 2027-08-17 | 2027-09-25 | 40 | 0%
7 | MEP fit-out |  | 2027-09-06 | 2028-02-22 | 170 | 0%
7.1 | Electrical distribution | Electrical | 2027-09-06 | 2027-12-24 | 110 | 0%

## Slide 4
7.2 | Generators & UPS install | Electrical | 2027-11-05 | 2028-01-23 | 80 | 0%
7.3 | Cooling plant install | Mechanical | 2027-10-16 | 2028-01-23 | 100 | 0%
7.4 | Fire suppression & security | Specialist | 2027-12-05 | 2028-02-02 | 60 | 0%
7.5 | Raised floor & containment | Fit-out | 2027-11-15 | 2028-01-03 | 50 | 0%
8 | Commissioning & handover |  | 2028-01-24 | 2028-06-01 | 130 | 0%
8.1 | Levels 1-3 commissioning | CxA | 2028-01-24 | 2028-03-08 | 45 | 0%
8.2 | Level 4 functional testing | CxA | 2028-03-04 | 2028-04-07 | 35 | 0%
8.3 | Level 5 integrated systems test | CxA | 2028-04-05 | 2028-05-04 | 30 | 0%
8.4 | IT deployment | IT | 2028-04-13 | 2028-05-27 | 45 | 0%
9 | Service ready |  | 2028-06-02 | 2028-06-02 | — | —