## Gantt
Data Center Build Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5
1 | Site selection & power |  | 2026-08-02 | 2026-12-29 | 150
1.1 | Site search & shortlist | Development | 2026-08-02 | 2026-09-20 | 50
1.2 | Utility capacity confirmation | Development | 2026-09-11 | 2026-11-19 | 70
1.3 | Fibre route survey | Network | 2026-10-01 | 2026-11-09 | 40
1.4 | Land acquisition | Legal | 2026-11-10 | 2026-12-29 | 50
2 | ◆ Power secured |  | 2026-12-30 | 2026-12-30 | [22 empty] | ◆
3 | Design & permitting |  | 2026-11-20 | 2027-04-08 | 140
3.1 | Concept design & topology | Engineering | 2026-11-20 | 2027-01-03 | 45
3.2 | Detailed design | Engineering | 2026-12-30 | 2027-03-29 | 90
3.3 | Planning & building permits | Consultant | 2027-01-19 | 2027-04-08 | 80
4 | ◆ Permit granted |  | 2027-04-09 | 2027-04-09 | [36 empty] | ◆
5 | Long-lead procurement |  | 2027-02-18 | 2027-11-04 | 260
5.1 | Generators & UPS order | Procurement | 2027-02-18 | 2027-10-15 | 240
5.2 | Switchgear & transformers order | Procurement | 2027-02-28 | 2027-11-04 | 250
5.3 | Chillers & cooling plant order | Procurement | 2027-03-20 | 2027-10-05 | 200
6 | Shell & core |  | 2027-04-09 | 2027-10-05 | 180
6.1 | Earthworks & foundations | Civil | 2027-04-09 | 2027-06-07 | 60
6.2 | Structure & envelope | Structural | 2027-05-29 | 2027-08-26 | 90
6.3 | Roof & weathertight | Structural | 2027-08-17 | 2027-09-25 | 40
7 | MEP fit-out |  | 2027-09-06 | 2028-02-22 | 170
7.1 | Electrical distribution | Electrical | 2027-09-06 | 2027-12-24 | 110
7.2 | Generators & UPS install | Electrical | 2027-11-05 | 2028-01-23 | 80
7.3 | Cooling plant install | Mechanical | 2027-10-16 | 2028-01-23 | 100
7.4 | Fire suppression & security | Specialist | 2027-12-05 | 2028-02-02 | 60
7.5 | Raised floor & containment | Fit-out | 2027-11-15 | 2028-01-03 | 50
8 | Commissioning & handover |  | 2028-01-24 | 2028-06-01 | 130
8.1 | Levels 1-3 commissioning | CxA | 2028-01-24 | 2028-03-08 | 45
8.2 | Level 4 functional testing | CxA | 2028-03-04 | 2028-04-07 | 35
8.3 | Level 5 integrated systems test | CxA | 2028-04-05 | 2028-05-04 | 30
8.4 | IT deployment | IT | 2028-04-13 | 2028-05-27 | 45
9 | ◆ Service ready |  | 2028-06-02 | 2028-06-02 | [96 empty] | ◆