## Slide 1
Data Migration Project Plan
Free Gantt chart template · gantts.app

## Slide 2
Data Migration Project Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Discovery & profiling
Source system inventory
Data profiling & quality report
Migrate / archive scope decision
◆ Scope & sources agreed
Mapping & rules
Field-level mapping per object
Transformation & default rules
Reference data alignment
Reconciliation rules defined
◆ Mapping signed off
Cleansing
Cleansing rules & automated fixes
Business remediation of exceptions
Deduplication pass
Build & unit test
Extract & load build per object
Error handling & restart logic
Reconciliation reports built
Mock loads & reconciliation
Mock load 1 (mapping test)
Reconcile & fix defects 1
Mock load 2 (cleansed data)
Reconcile & fix defects 2
Mock load 3 (timed dress rehearsal)
Business data validation
◆ Dress rehearsal passed
Cutover & verification
◆ Go / no-go on data readiness
Source freeze
Delta extract
Production cutover load
Reconciliation sign-off
Business verification
◆ Data accepted
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Discovery & profiling |  | 2026-08-02 | 2026-09-15 | 45 | 100%
1.1 | Source system inventory | Data lead | 2026-08-02 | 2026-08-16 | 15 | 100%
1.2 | Data profiling & quality report | Data team | 2026-08-14 | 2026-09-12 | 30 | 100%
1.3 | Migrate / archive scope decision | Business owners | 2026-09-06 | 2026-09-17 | 12 | 100%
2 | Scope & sources agreed |  | 2026-09-18 | 2026-09-18 | — | —
3 | Mapping & rules |  | 2026-09-18 | 2026-11-11 | 55 | 90%
3.1 | Field-level mapping per object | Data team | 2026-09-18 | 2026-10-22 | 35 | 100%
3.2 | Transformation & default rules | Data team | 2026-10-11 | 2026-11-09 | 30 | 90%
3.3 | Reference data alignment | Business owners | 2026-10-16 | 2026-11-09 | 25 | 80%
3.4 | Reconciliation rules defined | Finance & data | 2026-10-21 | 2026-11-11 | 22 | 70%
4 | Mapping signed off |  | 2026-11-12 | 2026-11-12 | — | —
5 | Cleansing |  | 2026-09-21 | 2027-01-08 | 110 | 55%
5.1 | Cleansing rules & automated fixes | Data team | 2026-09-21 | 2026-10-30 | 40 | 90%
5.2 | Business remediation of exceptions | Business owners | 2026-10-26 | 2027-01-03 | 70 | 40%
5.3 | Deduplication pass | Data team | 2026-12-10 | 2027-01-08 | 30 | 20%
6 | Build & unit test |  | 2026-11-12 | 2027-01-25 | 75 | 30%
6.1 | Extract & load build per object | Developers | 2026-11-12 | 2026-12-31 | 50 | 40%
6.2 | Error handling & restart logic | Developers | 2026-12-15 | 2027-01-08 | 25 | 20%
6.3 | Reconciliation reports built | Developers | 2026-12-20 | 2027-01-25 | 37 | 10%
7 | Mock loads & reconciliation |  | 2027-01-26 | 2027-04-30 | 95 | 0%
7.1 | Mock load 1 (mapping test) | Data team | 2027-01-26 | 2027-01-29 | 4 | 0%

## Slide 4
7.2 | Reconcile & fix defects 1 | Data team | 2027-01-30 | 2027-02-18 | 20 | 0%
7.3 | Mock load 2 (cleansed data) | Data team | 2027-02-23 | 2027-02-26 | 4 | 0%
7.4 | Reconcile & fix defects 2 | Data team | 2027-02-27 | 2027-03-18 | 20 | 0%
7.5 | Mock load 3 (timed dress rehearsal) | All | 2027-03-25 | 2027-03-28 | 4 | 0%
7.6 | Business data validation | Business owners | 2027-03-29 | 2027-04-22 | 25 | 0%
8 | Dress rehearsal passed |  | 2027-05-01 | 2027-05-01 | — | —
9 | Cutover & verification |  | 2027-05-01 | 2027-05-30 | 30 | 0%
10 | Go / no-go on data readiness |  | 2027-05-04 | 2027-05-04 | — | —
10.1 | Source freeze | Business owners | 2027-05-07 | 2027-05-07 | 1 | 0%
10.2 | Delta extract | Data team | 2027-05-08 | 2027-05-08 | 1 | 0%
10.3 | Production cutover load | Data team | 2027-05-09 | 2027-05-10 | 2 | 0%
10.4 | Reconciliation sign-off | Finance | 2027-05-11 | 2027-05-13 | 3 | 0%
10.5 | Business verification | Business owners | 2027-05-14 | 2027-05-23 | 10 | 0%
11 | Data accepted |  | 2027-05-25 | 2027-05-25 | — | —