## Gantt
Data Migration Project Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31
1 | Discovery & profiling |  | 2026-08-02 | 2026-09-15 | 45
1.1 | Source system inventory | Data lead | 2026-08-02 | 2026-08-16 | 15
1.2 | Data profiling & quality report | Data team | 2026-08-14 | 2026-09-12 | 30
1.3 | Migrate / archive scope decision | Business owners | 2026-09-06 | 2026-09-17 | 12
2 | ◆ Scope & sources agreed |  | 2026-09-18 | 2026-09-18 | [7 empty] | ◆
3 | Mapping & rules |  | 2026-09-18 | 2026-11-11 | 55
3.1 | Field-level mapping per object | Data team | 2026-09-18 | 2026-10-22 | 35
3.2 | Transformation & default rules | Data team | 2026-10-11 | 2026-11-09 | 30
3.3 | Reference data alignment | Business owners | 2026-10-16 | 2026-11-09 | 25
3.4 | Reconciliation rules defined | Finance & data | 2026-10-21 | 2026-11-11 | 22
4 | ◆ Mapping signed off |  | 2026-11-12 | 2026-11-12 | [15 empty] | ◆
5 | Cleansing |  | 2026-09-21 | 2027-01-08 | 110
5.1 | Cleansing rules & automated fixes | Data team | 2026-09-21 | 2026-10-30 | 40
5.2 | Business remediation of exceptions | Business owners | 2026-10-26 | 2027-01-03 | 70
5.3 | Deduplication pass | Data team | 2026-12-10 | 2027-01-08 | 30
6 | Build & unit test |  | 2026-11-12 | 2027-01-25 | 75
6.1 | Extract & load build per object | Developers | 2026-11-12 | 2026-12-31 | 50
6.2 | Error handling & restart logic | Developers | 2026-12-15 | 2027-01-08 | 25
6.3 | Reconciliation reports built | Developers | 2026-12-20 | 2027-01-25 | 37
7 | Mock loads & reconciliation |  | 2027-01-26 | 2027-04-30 | 95
7.1 | Mock load 1 (mapping test) | Data team | 2027-01-26 | 2027-01-29 | 4
7.2 | Reconcile & fix defects 1 | Data team | 2027-01-30 | 2027-02-18 | 20
7.3 | Mock load 2 (cleansed data) | Data team | 2027-02-23 | 2027-02-26 | 4
7.4 | Reconcile & fix defects 2 | Data team | 2027-02-27 | 2027-03-18 | 20
7.5 | Mock load 3 (timed dress rehearsal) | All | 2027-03-25 | 2027-03-28 | 4
7.6 | Business data validation | Business owners | 2027-03-29 | 2027-04-22 | 25
8 | ◆ Dress rehearsal passed |  | 2027-05-01 | 2027-05-01 | [39 empty] | ◆
9 | Cutover & verification |  | 2027-05-01 | 2027-05-30 | 30
10 | ◆ Go / no-go on data readiness |  | 2027-05-04 | 2027-05-04 | [40 empty] | ◆
10.1 | Source freeze | Business owners | 2027-05-07 | 2027-05-07 | 1
10.2 | Delta extract | Data team | 2027-05-08 | 2027-05-08 | 1
10.3 | Production cutover load | Data team | 2027-05-09 | 2027-05-10 | 2
10.4 | Reconciliation sign-off | Finance | 2027-05-11 | 2027-05-13 | 3
10.5 | Business verification | Business owners | 2027-05-14 | 2027-05-23 | 10
11 | ◆ Data accepted |  | 2027-05-25 | 2027-05-25 | [43 empty] | ◆