## Slide 1
Digital Transformation Roadmap
Free Gantt chart template · gantts.app

## Slide 2
Digital Transformation Roadmap
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Aug 28
Sep 11
Sep 25
Oct 9
Oct 23
Nov 6
Nov 20
Dec 4
Dec 18
Jan 1
Jan 15
Jan 29
Feb 12
Feb 26
Mar 12
Mar 26
Apr 9
Apr 23
May 7
May 21
Jun 4
Strategy, baseline & governance
Current state & digital maturity assessment
Application & data landscape inventory
Target operating model definition
Value case & benefit baselines set
Wave sequencing & dependency mapping
Governance rhythm & portfolio board stood up
◆ Roadmap and governance approved
Wave 1 — foundations
Identity & access management platform
Cloud landing zone & security baseline
Integration layer & API standards
Data platform build
Data governance & ownership model
Master data quality remediation
◆ Foundations live
Wave 2 — core process digitisation
Process discovery & prioritisation
Finance process automation
Procurement & supplier workflow
HR & workforce systems migration
Document & workflow management rollout
Manual & spreadsheet process retirement
◆ Core processes migrated
Wave 3 — customer-facing capability
Customer journey research & redesign
Unified customer data view
Customer portal build
Self-service & case management
Mobile experience release
◆ Customer capability launched
Wave 4 — analytics & intelligent automation
Self-service analytics rollout
Predictive model development
Model governance & responsible use policy
Automate high-volume decisions
◆ Analytics capability adopted
Benefit realisation & sustainment
Wave 1 benefit review
Wave 2 benefit review
Wave 3 benefit review
Wave 4 benefit review
Adoption measurement & change tracking
Governance reset at leadership change
Annual roadmap refresh
Legacy system decommissioning
Capability transfer to line teams
◆ Programme transitioned to run
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Strategy, baseline & governance |  | 2026-08-02 | 2026-11-19 | 110 | 100%
1.1 | Current state & digital maturity assessment | Strategy | 2026-08-02 | 2026-09-10 | 40 | 100%
1.2 | Application & data landscape inventory | Architecture | 2026-08-17 | 2026-09-25 | 40 | 100%
1.3 | Target operating model definition | Strategy | 2026-09-11 | 2026-10-15 | 35 | 100%
1.4 | Value case & benefit baselines set | Finance | 2026-09-26 | 2026-10-25 | 30 | 100%
1.5 | Wave sequencing & dependency mapping | Portfolio office | 2026-10-01 | 2026-10-30 | 30 | 100%
1.6 | Governance rhythm & portfolio board stood up | Portfolio office | 2026-10-21 | 2026-11-19 | 30 | 100%
2 | Roadmap and governance approved |  | 2026-11-20 | 2026-11-20 | — | —
3 | Wave 1 — foundations |  | 2026-11-20 | 2027-06-17 | 210 | 60%
3.1 | Identity & access management platform | Security | 2026-11-20 | 2027-02-17 | 90 | 90%
3.2 | Cloud landing zone & security baseline | Infrastructure | 2026-11-20 | 2027-02-27 | 100 | 80%
3.3 | Integration layer & API standards | Architecture | 2026-12-30 | 2027-04-18 | 110 | 60%
3.4 | Data platform build | Data engineering | 2027-01-09 | 2027-05-08 | 120 | 50%
3.5 | Data governance & ownership model | Data office | 2027-01-29 | 2027-04-28 | 90 | 30%
3.6 | Master data quality remediation | Data office | 2027-02-28 | 2027-06-07 | 100 | 20%
4 | Foundations live |  | 2027-06-18 | 2027-06-18 | — | —
5 | Wave 2 — core process digitisation |  | 2027-05-29 | 2028-01-03 | 220 | 0%
5.1 | Process discovery & prioritisation | Process office | 2027-05-29 | 2027-07-12 | 45 | 0%
5.2 | Finance process automation | Finance | 2027-07-13 | 2027-10-30 | 110 | 0%
5.3 | Procurement & supplier workflow | Procurement | 2027-07-28 | 2027-11-04 | 100 | 0%
5.4 | HR & workforce systems migration | HR | 2027-08-17 | 2027-12-04 | 110 | 0%

## Slide 4
5.5 | Document & workflow management rollout | IT | 2027-09-06 | 2027-12-04 | 90 | 0%
5.6 | Manual & spreadsheet process retirement | Process office | 2027-10-26 | 2028-01-03 | 70 | 0%
6 | Core processes migrated |  | 2028-01-04 | 2028-01-04 | — | —
7 | Wave 3 — customer-facing capability |  | 2027-12-15 | 2028-07-31 | 230 | 0%
7.1 | Customer journey research & redesign | Design | 2027-12-15 | 2028-02-12 | 60 | 0%
7.2 | Unified customer data view | Data engineering | 2028-01-04 | 2028-04-02 | 90 | 0%
7.3 | Customer portal build | Product | 2028-02-13 | 2028-06-11 | 120 | 0%
7.4 | Self-service & case management | Product | 2028-03-24 | 2028-07-01 | 100 | 0%
7.5 | Mobile experience release | Product | 2028-05-03 | 2028-07-31 | 90 | 0%
8 | Customer capability launched |  | 2028-08-01 | 2028-08-01 | — | —
9 | Wave 4 — analytics & intelligent automation |  | 2028-07-02 | 2029-03-18 | 260 | 0%
9.1 | Self-service analytics rollout | Data office | 2028-07-02 | 2028-10-09 | 100 | 0%
9.2 | Predictive model development | Data science | 2028-08-31 | 2028-12-28 | 120 | 0%
9.3 | Model governance & responsible use policy | Risk | 2028-09-20 | 2028-12-08 | 80 | 0%
9.4 | Automate high-volume decisions | Operations | 2028-11-29 | 2029-02-26 | 90 | 0%
10 | Analytics capability adopted |  | 2029-03-19 | 2029-03-19 | — | —
11 | Benefit realisation & sustainment |  | 2027-06-18 | 2029-06-06 | 720 | 0%
11.1 | Wave 1 benefit review | Finance | 2027-06-18 | 2027-07-17 | 30 | 0%
11.2 | Wave 2 benefit review | Finance | 2028-01-04 | 2028-02-02 | 30 | 0%
11.3 | Wave 3 benefit review | Finance | 2028-08-01 | 2028-08-30 | 30 | 0%
11.4 | Wave 4 benefit review | Finance | 2029-03-19 | 2029-04-17 | 30 | 0%
11.5 | Adoption measurement & change tracking | Change lead | 2027-06-28 | 2029-04-17 | 660 | 0%
11.6 | Governance reset at leadership change | Portfolio office | 2027-11-25 | 2027-12-19 | 25 | 0%
11.7 | Annual roadmap refresh | Portfolio office | 2028-07-02 | 2028-08-05 | 35 | 0%

## Slide 5
11.8 | Legacy system decommissioning | IT | 2028-09-20 | 2029-04-07 | 200 | 0%
11.9 | Capability transfer to line teams | Portfolio office | 2029-03-09 | 2029-05-17 | 70 | 0%
12 | Programme transitioned to run |  | 2029-05-28 | 2029-05-28 | — | —