## Gantt
Digital Transformation Roadmap
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26 | Jul 3 | Jul 10 | Jul 17 | Jul 24 | Jul 31 | Aug 7 | Aug 14 | Aug 21 | Aug 28 | Sep 4 | Sep 11 | Sep 18 | Sep 25 | Oct 2 | Oct 9 | Oct 16 | Oct 23 | Oct 30 | Nov 6 | Nov 13 | Nov 20 | Nov 27 | Dec 4 | Dec 11 | Dec 18 | Dec 25 | Jan 1 | Jan 8 | Jan 15 | Jan 22 | Jan 29 | Feb 5 | Feb 12 | Feb 19 | Feb 26 | Mar 5 | Mar 12 | Mar 19 | Mar 26 | Apr 2 | Apr 9 | Apr 16 | Apr 23 | Apr 30 | May 7 | May 14 | May 21 | May 28 | Jun 4 | Jun 11
1 | Strategy, baseline & governance |  | 2026-08-02 | 2026-11-19 | 110
1.1 | Current state & digital maturity assessment | Strategy | 2026-08-02 | 2026-09-10 | 40
1.2 | Application & data landscape inventory | Architecture | 2026-08-17 | 2026-09-25 | 40
1.3 | Target operating model definition | Strategy | 2026-09-11 | 2026-10-15 | 35
1.4 | Value case & benefit baselines set | Finance | 2026-09-26 | 2026-10-25 | 30
1.5 | Wave sequencing & dependency mapping | Portfolio office | 2026-10-01 | 2026-10-30 | 30
1.6 | Governance rhythm & portfolio board stood up | Portfolio office | 2026-10-21 | 2026-11-19 | 30
2 | ◆ Roadmap and governance approved |  | 2026-11-20 | 2026-11-20 | [16 empty] | ◆
3 | Wave 1 — foundations |  | 2026-11-20 | 2027-06-17 | 210
3.1 | Identity & access management platform | Security | 2026-11-20 | 2027-02-17 | 90
3.2 | Cloud landing zone & security baseline | Infrastructure | 2026-11-20 | 2027-02-27 | 100
3.3 | Integration layer & API standards | Architecture | 2026-12-30 | 2027-04-18 | 110
3.4 | Data platform build | Data engineering | 2027-01-09 | 2027-05-08 | 120
3.5 | Data governance & ownership model | Data office | 2027-01-29 | 2027-04-28 | 90
3.6 | Master data quality remediation | Data office | 2027-02-28 | 2027-06-07 | 100
4 | ◆ Foundations live |  | 2027-06-18 | 2027-06-18 | [46 empty] | ◆
5 | Wave 2 — core process digitisation |  | 2027-05-29 | 2028-01-03 | 220
5.1 | Process discovery & prioritisation | Process office | 2027-05-29 | 2027-07-12 | 45
5.2 | Finance process automation | Finance | 2027-07-13 | 2027-10-30 | 110
5.3 | Procurement & supplier workflow | Procurement | 2027-07-28 | 2027-11-04 | 100
5.4 | HR & workforce systems migration | HR | 2027-08-17 | 2027-12-04 | 110
5.5 | Document & workflow management rollout | IT | 2027-09-06 | 2027-12-04 | 90
5.6 | Manual & spreadsheet process retirement | Process office | 2027-10-26 | 2028-01-03 | 70
6 | ◆ Core processes migrated |  | 2028-01-04 | 2028-01-04 | [75 empty] | ◆
7 | Wave 3 — customer-facing capability |  | 2027-12-15 | 2028-07-31 | 230
7.1 | Customer journey research & redesign | Design | 2027-12-15 | 2028-02-12 | 60
7.2 | Unified customer data view | Data engineering | 2028-01-04 | 2028-04-02 | 90
7.3 | Customer portal build | Product | 2028-02-13 | 2028-06-11 | 120
7.4 | Self-service & case management | Product | 2028-03-24 | 2028-07-01 | 100
7.5 | Mobile experience release | Product | 2028-05-03 | 2028-07-31 | 90
8 | ◆ Customer capability launched |  | 2028-08-01 | 2028-08-01 | [105 empty] | ◆
9 | Wave 4 — analytics & intelligent automation |  | 2028-07-02 | 2029-03-18 | 260
9.1 | Self-service analytics rollout | Data office | 2028-07-02 | 2028-10-09 | 100
9.2 | Predictive model development | Data science | 2028-08-31 | 2028-12-28 | 120
9.3 | Model governance & responsible use policy | Risk | 2028-09-20 | 2028-12-08 | 80
9.4 | Automate high-volume decisions | Operations | 2028-11-29 | 2029-02-26 | 90
10 | ◆ Analytics capability adopted |  | 2029-03-19 | 2029-03-19 | [138 empty] | ◆
11 | Benefit realisation & sustainment |  | 2027-06-18 | 2029-06-06 | 720
11.1 | Wave 1 benefit review | Finance | 2027-06-18 | 2027-07-17 | 30
11.2 | Wave 2 benefit review | Finance | 2028-01-04 | 2028-02-02 | 30
11.3 | Wave 3 benefit review | Finance | 2028-08-01 | 2028-08-30 | 30
11.4 | Wave 4 benefit review | Finance | 2029-03-19 | 2029-04-17 | 30
11.5 | Adoption measurement & change tracking | Change lead | 2027-06-28 | 2029-04-17 | 660
11.6 | Governance reset at leadership change | Portfolio office | 2027-11-25 | 2027-12-19 | 25
11.7 | Annual roadmap refresh | Portfolio office | 2028-07-02 | 2028-08-05 | 35
11.8 | Legacy system decommissioning | IT | 2028-09-20 | 2029-04-07 | 200
11.9 | Capability transfer to line teams | Portfolio office | 2029-03-09 | 2029-05-17 | 70
12 | ◆ Programme transitioned to run |  | 2029-05-28 | 2029-05-28 | [148 empty] | ◆