## Slide 1
Disaster Recovery Plan
Free Gantt chart template · gantts.app

## Slide 2
Disaster Recovery Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Business impact analysis
Application & service inventory
Dependency mapping
Business impact analysis workshops
RTO and RPO targets agreed
◆ RTO/RPO baseline approved
DR strategy & architecture
Recovery tier assignment per application
DR site or region selection
Replication & backup architecture
Network, DNS & failover design
Cost & gap review against targets
◆ Architecture approved
Build & replication
DR infrastructure provisioning
Storage & database replication setup
Backup policy & retention changes
Identity & security controls at DR site
Monitoring & replication lag alerting
◆ Replication steady state verified
Runbooks & documentation
Failover runbook per recovery tier
Rollback & failback procedures
Crisis communication & call tree
Declaration criteria & authority matrix
◆ Runbooks published
Test sequence
Tabletop exercise
Tabletop findings & runbook fixes
Change window booked for partial failover
Partial failover test (tier 1 applications)
Rollback from partial failover
Partial test findings & remediation
Change window booked for full failover
Full failover test with business validation
Failback to primary
◆ Full failover test passed
Approval & maintenance
Test report & residual risk register
Executive approval of DR plan
◆ Plan approved
Responder training & on-call briefing
Annual test calendar & review cycle
Change control hook for new applications
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Business impact analysis |  | 2026-08-02 | 2026-09-25 | 55 | 100%
1.1 | Application & service inventory | IT | 2026-08-02 | 2026-08-21 | 20 | 100%
1.2 | Dependency mapping | Architecture | 2026-08-14 | 2026-09-07 | 25 | 100%
1.3 | Business impact analysis workshops | Business owners | 2026-08-22 | 2026-09-15 | 25 | 100%
1.4 | RTO and RPO targets agreed | Exec | 2026-09-11 | 2026-09-25 | 15 | 100%
2 | RTO/RPO baseline approved |  | 2026-09-26 | 2026-09-26 | — | —
3 | DR strategy & architecture |  | 2026-09-26 | 2026-12-04 | 70 | 80%
3.1 | Recovery tier assignment per application | Architecture | 2026-09-26 | 2026-10-15 | 20 | 100%
3.2 | DR site or region selection | Infrastructure | 2026-10-01 | 2026-10-25 | 25 | 100%
3.3 | Replication & backup architecture | Architecture | 2026-10-16 | 2026-11-14 | 30 | 80%
3.4 | Network, DNS & failover design | Network | 2026-10-31 | 2026-11-29 | 30 | 60%
3.5 | Cost & gap review against targets | Finance & IT | 2026-11-15 | 2026-12-04 | 20 | 40%
4 | Architecture approved |  | 2026-12-05 | 2026-12-05 | — | —
5 | Build & replication |  | 2026-12-05 | 2027-03-14 | 100 | 30%
5.1 | DR infrastructure provisioning | Infrastructure | 2026-12-05 | 2027-01-13 | 40 | 50%
5.2 | Storage & database replication setup | Infrastructure | 2026-12-25 | 2027-02-07 | 45 | 30%
5.3 | Backup policy & retention changes | Infrastructure | 2026-12-30 | 2027-01-28 | 30 | 20%
5.4 | Identity & security controls at DR site | Security | 2027-01-14 | 2027-02-17 | 35 | 10%
5.5 | Monitoring & replication lag alerting | Operations | 2027-02-08 | 2027-03-09 | 30 | 0%
6 | Replication steady state verified |  | 2027-03-15 | 2027-03-15 | — | —
7 | Runbooks & documentation |  | 2027-01-29 | 2027-04-18 | 80 | 0%

## Slide 4
7.1 | Failover runbook per recovery tier | Operations | 2027-01-29 | 2027-03-14 | 45 | 0%
7.2 | Rollback & failback procedures | Operations | 2027-02-28 | 2027-03-29 | 30 | 0%
7.3 | Crisis communication & call tree | Comms | 2027-03-10 | 2027-03-29 | 20 | 0%
7.4 | Declaration criteria & authority matrix | Exec | 2027-03-30 | 2027-04-13 | 15 | 0%
8 | Runbooks published |  | 2027-04-19 | 2027-04-19 | — | —
9 | Test sequence |  | 2027-04-19 | 2027-08-06 | 110 | 0%
9.1 | Tabletop exercise | All responders | 2027-04-19 | 2027-04-21 | 3 | 0%
9.2 | Tabletop findings & runbook fixes | Operations | 2027-04-22 | 2027-05-11 | 20 | 0%
9.3 | Change window booked for partial failover | Change board | 2027-05-14 | 2027-05-23 | 10 | 0%
9.4 | Partial failover test (tier 1 applications) | Infrastructure | 2027-05-29 | 2027-05-31 | 3 | 0%
9.5 | Rollback from partial failover | Infrastructure | 2027-06-01 | 2027-06-02 | 2 | 0%
9.6 | Partial test findings & remediation | Operations | 2027-06-04 | 2027-07-03 | 30 | 0%
9.7 | Change window booked for full failover | Change board | 2027-07-08 | 2027-07-22 | 15 | 0%
9.8 | Full failover test with business validation | All | 2027-07-28 | 2027-07-31 | 4 | 0%
9.9 | Failback to primary | Infrastructure | 2027-08-01 | 2027-08-03 | 3 | 0%
10 | Full failover test passed |  | 2027-08-07 | 2027-08-07 | — | —
11 | Approval & maintenance |  | 2027-08-07 | 2027-10-25 | 80 | 0%
11.1 | Test report & residual risk register | Operations | 2027-08-07 | 2027-08-26 | 20 | 0%
11.2 | Executive approval of DR plan | Exec | 2027-08-27 | 2027-09-10 | 15 | 0%
12 | Plan approved |  | 2027-09-11 | 2027-09-11 | — | —
12.1 | Responder training & on-call briefing | Operations | 2027-09-11 | 2027-09-30 | 20 | 0%
12.2 | Annual test calendar & review cycle | Operations | 2027-09-26 | 2027-10-10 | 15 | 0%
12.3 | Change control hook for new applications | Change board | 2027-10-06 | 2027-10-25 | 20 | 0%