## Gantt
Disaster Recovery Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1
1 | Business impact analysis |  | 2026-08-02 | 2026-09-25 | 55
1.1 | Application & service inventory | IT | 2026-08-02 | 2026-08-21 | 20
1.2 | Dependency mapping | Architecture | 2026-08-14 | 2026-09-07 | 25
1.3 | Business impact analysis workshops | Business owners | 2026-08-22 | 2026-09-15 | 25
1.4 | RTO and RPO targets agreed | Exec | 2026-09-11 | 2026-09-25 | 15
2 | ◆ RTO/RPO baseline approved |  | 2026-09-26 | 2026-09-26 | [8 empty] | ◆
3 | DR strategy & architecture |  | 2026-09-26 | 2026-12-04 | 70
3.1 | Recovery tier assignment per application | Architecture | 2026-09-26 | 2026-10-15 | 20
3.2 | DR site or region selection | Infrastructure | 2026-10-01 | 2026-10-25 | 25
3.3 | Replication & backup architecture | Architecture | 2026-10-16 | 2026-11-14 | 30
3.4 | Network, DNS & failover design | Network | 2026-10-31 | 2026-11-29 | 30
3.5 | Cost & gap review against targets | Finance & IT | 2026-11-15 | 2026-12-04 | 20
4 | ◆ Architecture approved |  | 2026-12-05 | 2026-12-05 | [18 empty] | ◆
5 | Build & replication |  | 2026-12-05 | 2027-03-14 | 100
5.1 | DR infrastructure provisioning | Infrastructure | 2026-12-05 | 2027-01-13 | 40
5.2 | Storage & database replication setup | Infrastructure | 2026-12-25 | 2027-02-07 | 45
5.3 | Backup policy & retention changes | Infrastructure | 2026-12-30 | 2027-01-28 | 30
5.4 | Identity & security controls at DR site | Security | 2027-01-14 | 2027-02-17 | 35
5.5 | Monitoring & replication lag alerting | Operations | 2027-02-08 | 2027-03-09 | 30
6 | ◆ Replication steady state verified |  | 2027-03-15 | 2027-03-15 | [33 empty] | ◆
7 | Runbooks & documentation |  | 2027-01-29 | 2027-04-18 | 80
7.1 | Failover runbook per recovery tier | Operations | 2027-01-29 | 2027-03-14 | 45
7.2 | Rollback & failback procedures | Operations | 2027-02-28 | 2027-03-29 | 30
7.3 | Crisis communication & call tree | Comms | 2027-03-10 | 2027-03-29 | 20
7.4 | Declaration criteria & authority matrix | Exec | 2027-03-30 | 2027-04-13 | 15
8 | ◆ Runbooks published |  | 2027-04-19 | 2027-04-19 | [38 empty] | ◆
9 | Test sequence |  | 2027-04-19 | 2027-08-06 | 110
9.1 | Tabletop exercise | All responders | 2027-04-19 | 2027-04-21 | 3
9.2 | Tabletop findings & runbook fixes | Operations | 2027-04-22 | 2027-05-11 | 20
9.3 | Change window booked for partial failover | Change board | 2027-05-14 | 2027-05-23 | 10
9.4 | Partial failover test (tier 1 applications) | Infrastructure | 2027-05-29 | 2027-05-31 | 3
9.5 | Rollback from partial failover | Infrastructure | 2027-06-01 | 2027-06-02 | 2
9.6 | Partial test findings & remediation | Operations | 2027-06-04 | 2027-07-03 | 30
9.7 | Change window booked for full failover | Change board | 2027-07-08 | 2027-07-22 | 15
9.8 | Full failover test with business validation | All | 2027-07-28 | 2027-07-31 | 4
9.9 | Failback to primary | Infrastructure | 2027-08-01 | 2027-08-03 | 3
10 | ◆ Full failover test passed |  | 2027-08-07 | 2027-08-07 | [53 empty] | ◆
11 | Approval & maintenance |  | 2027-08-07 | 2027-10-25 | 80
11.1 | Test report & residual risk register | Operations | 2027-08-07 | 2027-08-26 | 20
11.2 | Executive approval of DR plan | Exec | 2027-08-27 | 2027-09-10 | 15
12 | ◆ Plan approved |  | 2027-09-11 | 2027-09-11 | [58 empty] | ◆
12.1 | Responder training & on-call briefing | Operations | 2027-09-11 | 2027-09-30 | 20
12.2 | Annual test calendar & review cycle | Operations | 2027-09-26 | 2027-10-10 | 15
12.3 | Change control hook for new applications | Change board | 2027-10-06 | 2027-10-25 | 20