## Slide 1
Dissertation Timeline
Free Gantt chart template · gantts.app

## Slide 2
Dissertation Timeline
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Topic & proposal
Topic selection & reading
Research questions & design
Proposal written & submitted
◆ Proposal approved
Literature review
Systematic search & reading
Synthesis & review chapter
Methodology & ethics
Method & instrument design
Ethics submission & review
◆ Ethics approval
Data collection
Recruitment
Fieldwork / data gathering
Analysis
Data cleaning & coding
Analysis & results write-up
Drafting & submission
Full draft to supervisor
Supervisor feedback
Revisions & formatting
◆ Submitted
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Topic & proposal |  | 2026-08-02 | 2026-09-20 | 50 | 100%
1.1 | Topic selection & reading | Student | 2026-08-02 | 2026-08-26 | 25 | 100%
1.2 | Research questions & design | Student | 2026-08-22 | 2026-09-10 | 20 | 100%
1.3 | Proposal written & submitted | Student | 2026-09-09 | 2026-09-20 | 12 | 100%
2 | Proposal approved |  | 2026-09-21 | 2026-09-21 | — | —
3 | Literature review |  | 2026-08-27 | 2026-11-24 | 90 | 60%
3.1 | Systematic search & reading | Student | 2026-08-27 | 2026-10-15 | 50 | 80%
3.2 | Synthesis & review chapter | Student | 2026-10-11 | 2026-11-24 | 45 | 40%
4 | Methodology & ethics |  | 2026-09-21 | 2026-11-14 | 55 | 50%
4.1 | Method & instrument design | Student | 2026-09-21 | 2026-10-20 | 30 | 70%
4.2 | Ethics submission & review | Committee | 2026-10-16 | 2026-11-14 | 30 | 30%
5 | Ethics approval |  | 2026-11-15 | 2026-11-15 | — | —
6 | Data collection |  | 2026-11-15 | 2027-02-12 | 90 | 0%
6.1 | Recruitment | Student | 2026-11-15 | 2026-12-14 | 30 | 0%
6.2 | Fieldwork / data gathering | Student | 2026-12-05 | 2027-02-12 | 70 | 0%
7 | Analysis |  | 2027-02-08 | 2027-04-08 | 60 | 0%
7.1 | Data cleaning & coding | Student | 2027-02-08 | 2027-03-04 | 25 | 0%
7.2 | Analysis & results write-up | Student | 2027-03-02 | 2027-04-08 | 38 | 0%
8 | Drafting & submission |  | 2027-03-30 | 2027-07-12 | 105 | 0%
8.1 | Full draft to supervisor | Student | 2027-03-30 | 2027-05-08 | 40 | 0%
8.2 | Supervisor feedback | Supervisor | 2027-05-09 | 2027-05-28 | 20 | 0%

## Slide 4
8.3 | Revisions & formatting | Student | 2027-05-29 | 2027-07-02 | 35 | 0%
9 | Submitted |  | 2027-07-13 | 2027-07-13 | — | —