## Slide 1
ERP Implementation Schedule
Free Gantt chart template · gantts.app

## Slide 2
ERP Implementation Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Discovery & fit-gap
Current-state process mapping
Requirements & fit-gap analysis
◆ Scope agreed
Solution design
To-be process design
Configuration workbooks
Integration & reporting specs
◆ Design sign-off
Build & configuration
System configuration
Extensions & integrations
Reports & dashboards
Security & role model
Data migration
Data profiling & cleansing
Mapping & transformation rules
Mock load 1
Mock load 2
Mock load 3 (dress rehearsal)
Testing
System integration testing
User acceptance testing
Defect resolution
◆ UAT signed off
Training, cutover & hypercare
End-user training
Cutover rehearsal
◆ Go / no-go decision
Cutover weekend
◆ Go-live
Hypercare
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Discovery & fit-gap |  | 2026-08-02 | 2026-09-30 | 60 | 100%
1.1 | Current-state process mapping | Business analyst | 2026-08-02 | 2026-08-31 | 30 | 100%
1.2 | Requirements & fit-gap analysis | Business analyst | 2026-08-27 | 2026-09-30 | 35 | 100%
2 | Scope agreed |  | 2026-10-01 | 2026-10-01 | — | —
3 | Solution design |  | 2026-10-01 | 2026-12-09 | 70 | 100%
3.1 | To-be process design | Solution architect | 2026-10-01 | 2026-11-14 | 45 | 100%
3.2 | Configuration workbooks | Consultants | 2026-10-26 | 2026-11-29 | 35 | 100%
3.3 | Integration & reporting specs | Solution architect | 2026-10-31 | 2026-12-09 | 40 | 90%
4 | Design sign-off |  | 2026-12-10 | 2026-12-10 | — | —
5 | Build & configuration |  | 2026-12-10 | 2027-04-08 | 120 | 60%
5.1 | System configuration | Consultants | 2026-12-10 | 2027-02-27 | 80 | 80%
5.2 | Extensions & integrations | Developers | 2026-12-30 | 2027-04-08 | 100 | 50%
5.3 | Reports & dashboards | Developers | 2027-02-08 | 2027-04-08 | 60 | 30%
5.4 | Security & role model | Security | 2027-02-18 | 2027-04-03 | 45 | 20%
6 | Data migration |  | 2026-10-11 | 2027-04-28 | 200 | 45%
6.1 | Data profiling & cleansing | Data team | 2026-10-11 | 2027-01-28 | 110 | 70%
6.2 | Mapping & transformation rules | Data team | 2026-12-20 | 2027-02-17 | 60 | 50%
6.3 | Mock load 1 | Data team | 2027-02-18 | 2027-03-04 | 15 | 0%
6.4 | Mock load 2 | Data team | 2027-03-20 | 2027-04-03 | 15 | 0%
6.5 | Mock load 3 (dress rehearsal) | Data team | 2027-04-14 | 2027-04-28 | 15 | 0%
7 | Testing |  | 2027-04-09 | 2027-07-07 | 90 | 0%

## Slide 4
7.1 | System integration testing | QA | 2027-04-09 | 2027-05-18 | 40 | 0%
7.2 | User acceptance testing | Business users | 2027-05-14 | 2027-06-27 | 45 | 0%
7.3 | Defect resolution | Developers | 2027-04-24 | 2027-07-02 | 70 | 0%
8 | UAT signed off |  | 2027-07-08 | 2027-07-08 | — | —
9 | Training, cutover & hypercare |  | 2027-05-29 | 2027-08-26 | 90 | 0%
9.1 | End-user training | Training lead | 2027-05-29 | 2027-07-07 | 40 | 0%
9.2 | Cutover rehearsal | Programme | 2027-07-03 | 2027-07-12 | 10 | 0%
10 | Go / no-go decision |  | 2027-07-18 | 2027-07-18 | — | —
10.1 | Cutover weekend | All | 2027-07-23 | 2027-07-26 | 4 | 0%
11 | Go-live |  | 2027-07-27 | 2027-07-27 | — | —
11.1 | Hypercare | Support | 2027-07-27 | 2027-08-25 | 30 | 0%