## Slide 1
Event Planning Timeline
Free Gantt chart template · gantts.app

## Slide 2
Event Planning Timeline
Aug 3
Aug 17
Aug 31
Sep 14
Planning
Set budget & goals
Book venue
Confirm speakers
Promotion
Website & tickets
Email + social push
Logistics
Catering & AV
Run of show
◆ Event day
Wrap-up & thank you
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Planning |  | 2026-08-02 | 2026-08-15 | 14 | 60%
1.1 | Set budget & goals | Lead | 2026-08-02 | 2026-08-04 | 3 | 100%
1.2 | Book venue | Coord | 2026-08-05 | 2026-08-09 | 5 | 80%
1.3 | Confirm speakers | Coord | 2026-08-07 | 2026-08-15 | 9 | 40%
2 | Promotion |  | 2026-08-16 | 2026-09-05 | 21 | 10%
2.1 | Website & tickets | Web | 2026-08-16 | 2026-08-22 | 7 | 20%
2.2 | Email + social push | Social | 2026-08-20 | 2026-09-05 | 17 | 5%
3 | Logistics |  | 2026-09-01 | 2026-09-10 | 10 | 0%
3.1 | Catering & AV | Ops | 2026-09-01 | 2026-09-06 | 6 | 0%
3.2 | Run of show | Ops | 2026-09-06 | 2026-09-10 | 5 | 0%
4 | Event day |  | 2026-09-11 | 2026-09-11 | — | —
5 | Wrap-up & thank you |  | 2026-09-12 | 2026-09-15 | 4 | 0%