## Slide 1
Fiber Broadband Rollout
Free Gantt chart template · gantts.app

## Slide 2
Fiber Broadband Rollout
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Programme setup & high-level design
Demand assessment & area prioritisation
High-level network design & PoP siting
Vendor & contractor framework award
Build standards & as-built data model
Core & backhaul procurement
◆ Rollout plan baselined
Permits, wayleaves & survey
Street works permit applications
Wayleave negotiation - private land
MDU landlord agreements
Duct & pole availability survey
PIA order placement & duct remediation
◆ Wayleaves cleared for wave 1
Area A - wave 1 build
Area A detailed design & splice plan
Area A duct clearance & civils
Area A cable blowing & pole overlash
Area A splicing & cabinet build
Area A OTDR test & as-built handover
◆ Area A RFS
Area B - wave 2 build
Area B detailed design & splice plan
Area B duct clearance & civils
Area B cable blowing & pole overlash
Area B splicing & cabinet build
Area B OTDR test & as-built handover
◆ Area B RFS
Area C - wave 3 build
Area C wayleaves & permits
Area C detailed design & splice plan
Area C duct clearance & civils
Area C cable blowing & splicing
Area C OTDR test & as-built handover
◆ Area C RFS
Activation, sales & connections
PoP & core network commissioning
OSS/BSS & provisioning integration
Field install crew scaling & training
Pre-marketing & registration of interest
Area A connections & installs
Area B connections & installs
Area C connections & installs
◆ Take-up review & wave 4 go/no-go
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Programme setup & high-level design |  | 2026-08-02 | 2026-10-30 | 90 | 100%
1.1 | Demand assessment & area prioritisation | Strategy | 2026-08-02 | 2026-08-31 | 30 | 100%
1.2 | High-level network design & PoP siting | Network design | 2026-08-22 | 2026-09-30 | 40 | 100%
1.3 | Vendor & contractor framework award | Procurement | 2026-09-11 | 2026-10-25 | 45 | 100%
1.4 | Build standards & as-built data model | Network design | 2026-10-01 | 2026-10-30 | 30 | 100%
1.5 | Core & backhaul procurement | Procurement | 2026-10-01 | 2026-11-29 | 60 | 90%
2 | Rollout plan baselined |  | 2026-10-31 | 2026-10-31 | — | —
3 | Permits, wayleaves & survey |  | 2026-10-01 | 2027-02-17 | 140 | 70%
3.1 | Street works permit applications | Consents | 2026-10-01 | 2026-11-29 | 60 | 90%
3.2 | Wayleave negotiation - private land | Consents | 2026-10-01 | 2027-01-18 | 110 | 60%
3.3 | MDU landlord agreements | Consents | 2026-10-21 | 2027-01-18 | 90 | 40%
3.4 | Duct & pole availability survey | Survey | 2026-10-11 | 2026-11-29 | 50 | 100%
3.5 | PIA order placement & duct remediation | Civils | 2026-11-30 | 2027-01-28 | 60 | 30%
4 | Wayleaves cleared for wave 1 |  | 2027-01-19 | 2027-01-19 | — | —
5 | Area A - wave 1 build |  | 2026-11-30 | 2027-05-23 | 175 | 20%
5.1 | Area A detailed design & splice plan | Network design | 2026-11-30 | 2026-12-29 | 30 | 100%
5.2 | Area A duct clearance & civils | Civils | 2027-01-19 | 2027-03-04 | 45 | 60%
5.3 | Area A cable blowing & pole overlash | Cabling | 2027-03-05 | 2027-04-08 | 35 | 10%
5.4 | Area A splicing & cabinet build | Splicing | 2027-04-09 | 2027-05-08 | 30 | 0%
5.5 | Area A OTDR test & as-built handover | Test | 2027-05-09 | 2027-05-28 | 20 | 0%
6 | Area A RFS |  | 2027-05-31 | 2027-05-31 | — | —

## Slide 4
7 | Area B - wave 2 build |  | 2027-02-18 | 2027-08-31 | 195 | 0%
7.1 | Area B detailed design & splice plan | Network design | 2027-02-18 | 2027-03-19 | 30 | 20%
7.2 | Area B duct clearance & civils | Civils | 2027-03-30 | 2027-05-18 | 50 | 0%
7.3 | Area B cable blowing & pole overlash | Cabling | 2027-05-19 | 2027-06-22 | 35 | 0%
7.4 | Area B splicing & cabinet build | Splicing | 2027-06-23 | 2027-07-22 | 30 | 0%
7.5 | Area B OTDR test & as-built handover | Test | 2027-07-23 | 2027-08-11 | 20 | 0%
8 | Area B RFS |  | 2027-08-14 | 2027-08-14 | — | —
9 | Area C - wave 3 build |  | 2027-05-09 | 2027-11-24 | 200 | 0%
9.1 | Area C wayleaves & permits | Consents | 2027-05-09 | 2027-07-02 | 55 | 0%
9.2 | Area C detailed design & splice plan | Network design | 2027-07-03 | 2027-08-01 | 30 | 0%
9.3 | Area C duct clearance & civils | Civils | 2027-08-02 | 2027-09-20 | 50 | 0%
9.4 | Area C cable blowing & splicing | Cabling | 2027-09-21 | 2027-11-04 | 45 | 0%
9.5 | Area C OTDR test & as-built handover | Test | 2027-11-05 | 2027-11-24 | 20 | 0%
10 | Area C RFS |  | 2027-11-27 | 2027-11-27 | — | —
11 | Activation, sales & connections |  | 2027-03-30 | 2028-01-23 | 300 | 0%
11.1 | PoP & core network commissioning | Network ops | 2027-03-30 | 2027-05-08 | 40 | 0%
11.2 | OSS/BSS & provisioning integration | IT | 2027-04-09 | 2027-06-07 | 60 | 0%
11.3 | Field install crew scaling & training | Ops | 2027-05-09 | 2027-07-07 | 60 | 0%
11.4 | Pre-marketing & registration of interest | Marketing | 2027-05-09 | 2027-06-17 | 40 | 0%
11.5 | Area A connections & installs | Install | 2027-05-31 | 2027-08-28 | 90 | 0%
11.6 | Area B connections & installs | Install | 2027-08-14 | 2027-11-01 | 80 | 0%
11.7 | Area C connections & installs | Install | 2027-11-27 | 2028-01-25 | 60 | 0%
12 | Take-up review & wave 4 go/no-go |  | 2028-01-29 | 2028-01-29 | — | —