## Gantt
Fiber Broadband Rollout
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31
1 | Programme setup & high-level design |  | 2026-08-02 | 2026-10-30 | 90
1.1 | Demand assessment & area prioritisation | Strategy | 2026-08-02 | 2026-08-31 | 30
1.2 | High-level network design & PoP siting | Network design | 2026-08-22 | 2026-09-30 | 40
1.3 | Vendor & contractor framework award | Procurement | 2026-09-11 | 2026-10-25 | 45
1.4 | Build standards & as-built data model | Network design | 2026-10-01 | 2026-10-30 | 30
1.5 | Core & backhaul procurement | Procurement | 2026-10-01 | 2026-11-29 | 60
2 | ◆ Rollout plan baselined |  | 2026-10-31 | 2026-10-31 | [13 empty] | ◆
3 | Permits, wayleaves & survey |  | 2026-10-01 | 2027-02-17 | 140
3.1 | Street works permit applications | Consents | 2026-10-01 | 2026-11-29 | 60
3.2 | Wayleave negotiation - private land | Consents | 2026-10-01 | 2027-01-18 | 110
3.3 | MDU landlord agreements | Consents | 2026-10-21 | 2027-01-18 | 90
3.4 | Duct & pole availability survey | Survey | 2026-10-11 | 2026-11-29 | 50
3.5 | PIA order placement & duct remediation | Civils | 2026-11-30 | 2027-01-28 | 60
4 | ◆ Wayleaves cleared for wave 1 |  | 2027-01-19 | 2027-01-19 | [25 empty] | ◆
5 | Area A - wave 1 build |  | 2026-11-30 | 2027-05-23 | 175
5.1 | Area A detailed design & splice plan | Network design | 2026-11-30 | 2026-12-29 | 30
5.2 | Area A duct clearance & civils | Civils | 2027-01-19 | 2027-03-04 | 45
5.3 | Area A cable blowing & pole overlash | Cabling | 2027-03-05 | 2027-04-08 | 35
5.4 | Area A splicing & cabinet build | Splicing | 2027-04-09 | 2027-05-08 | 30
5.5 | Area A OTDR test & as-built handover | Test | 2027-05-09 | 2027-05-28 | 20
6 | ◆ Area A RFS |  | 2027-05-31 | 2027-05-31 | [44 empty] | ◆
7 | Area B - wave 2 build |  | 2027-02-18 | 2027-08-31 | 195
7.1 | Area B detailed design & splice plan | Network design | 2027-02-18 | 2027-03-19 | 30
7.2 | Area B duct clearance & civils | Civils | 2027-03-30 | 2027-05-18 | 50
7.3 | Area B cable blowing & pole overlash | Cabling | 2027-05-19 | 2027-06-22 | 35
7.4 | Area B splicing & cabinet build | Splicing | 2027-06-23 | 2027-07-22 | 30
7.5 | Area B OTDR test & as-built handover | Test | 2027-07-23 | 2027-08-11 | 20
8 | ◆ Area B RFS |  | 2027-08-14 | 2027-08-14 | [54 empty] | ◆
9 | Area C - wave 3 build |  | 2027-05-09 | 2027-11-24 | 200
9.1 | Area C wayleaves & permits | Consents | 2027-05-09 | 2027-07-02 | 55
9.2 | Area C detailed design & splice plan | Network design | 2027-07-03 | 2027-08-01 | 30
9.3 | Area C duct clearance & civils | Civils | 2027-08-02 | 2027-09-20 | 50
9.4 | Area C cable blowing & splicing | Cabling | 2027-09-21 | 2027-11-04 | 45
9.5 | Area C OTDR test & as-built handover | Test | 2027-11-05 | 2027-11-24 | 20
10 | ◆ Area C RFS |  | 2027-11-27 | 2027-11-27 | [69 empty] | ◆
11 | Activation, sales & connections |  | 2027-03-30 | 2028-01-23 | 300
11.1 | PoP & core network commissioning | Network ops | 2027-03-30 | 2027-05-08 | 40
11.2 | OSS/BSS & provisioning integration | IT | 2027-04-09 | 2027-06-07 | 60
11.3 | Field install crew scaling & training | Ops | 2027-05-09 | 2027-07-07 | 60
11.4 | Pre-marketing & registration of interest | Marketing | 2027-05-09 | 2027-06-17 | 40
11.5 | Area A connections & installs | Install | 2027-05-31 | 2027-08-28 | 90
11.6 | Area B connections & installs | Install | 2027-08-14 | 2027-11-01 | 80
11.7 | Area C connections & installs | Install | 2027-11-27 | 2028-01-25 | 60
12 | ◆ Take-up review & wave 4 go/no-go |  | 2028-01-29 | 2028-01-29 | [78 empty] | ◆