## Slide 1
Film Production Schedule
Free Gantt chart template · gantts.app

## Slide 2
Film Production Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Development
Script drafts & rewrites
Rights & option agreements
Budget & schedule breakdown
Financing & attachments
◆ Greenlight
Pre-production
Casting — leads
Department heads hired
Location scout & permits
Production design & build
Wardrobe & make-up prep
Shooting schedule locked
Camera & equipment tests
Principal photography
Block 1 — studio stage
Block 2 — location exteriors
Block 3 — pick-ups & inserts
Contingency days
◆ Picture wrap
Post-production — picture
Dailies & assembly
Editor's cut
Director's cut
Notes & recut
◆ Picture lock
Sound & picture finishing
VFX shot delivery
ADR & foley
Sound design & score
Final mix
Colour grade & online conform
Delivery & distribution
DCP & master creation
QC & technical review
Captions & localisation
Marketing materials & trailer
Festival submissions
◆ Delivery accepted
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Development |  | 2026-08-02 | 2026-12-29 | 150 | 100%
1.1 | Script drafts & rewrites | Writer | 2026-08-02 | 2026-10-30 | 90 | 100%
1.2 | Rights & option agreements | Legal | 2026-08-22 | 2026-10-05 | 45 | 100%
1.3 | Budget & schedule breakdown | Line producer | 2026-10-16 | 2026-11-19 | 35 | 100%
1.4 | Financing & attachments | Producer | 2026-10-31 | 2026-12-29 | 60 | 100%
2 | Greenlight |  | 2026-12-30 | 2026-12-30 | — | —
3 | Pre-production |  | 2026-12-30 | 2027-03-14 | 75 | 70%
3.1 | Casting — leads | Casting | 2026-12-30 | 2027-02-02 | 35 | 100%
3.2 | Department heads hired | Producer | 2026-12-30 | 2027-01-23 | 25 | 100%
3.3 | Location scout & permits | Locations | 2027-01-07 | 2027-02-25 | 50 | 70%
3.4 | Production design & build | Production designer | 2027-01-21 | 2027-03-06 | 45 | 50%
3.5 | Wardrobe & make-up prep | Costume | 2027-01-29 | 2027-03-09 | 40 | 40%
3.6 | Shooting schedule locked | First AD | 2027-02-03 | 2027-02-22 | 20 | 30%
3.7 | Camera & equipment tests | Camera | 2027-02-28 | 2027-03-09 | 10 | 0%
4 | Principal photography |  | 2027-03-15 | 2027-04-23 | 40 | 0%
4.1 | Block 1 — studio stage | Crew | 2027-03-15 | 2027-03-28 | 14 | 0%
4.2 | Block 2 — location exteriors | Crew | 2027-03-30 | 2027-04-13 | 15 | 0%
4.3 | Block 3 — pick-ups & inserts | Crew | 2027-04-15 | 2027-04-20 | 6 | 0%
4.4 | Contingency days | Crew | 2027-04-21 | 2027-04-23 | 3 | 0%
5 | Picture wrap |  | 2027-04-24 | 2027-04-24 | — | —
6 | Post-production — picture |  | 2027-03-18 | 2027-08-09 | 145 | 0%

## Slide 4
6.1 | Dailies & assembly | Editor | 2027-03-18 | 2027-05-01 | 45 | 0%
6.2 | Editor's cut | Editor | 2027-04-24 | 2027-05-23 | 30 | 0%
6.3 | Director's cut | Director | 2027-05-24 | 2027-07-07 | 45 | 0%
6.4 | Notes & recut | Editor | 2027-07-08 | 2027-08-09 | 33 | 0%
7 | Picture lock |  | 2027-08-10 | 2027-08-10 | — | —
8 | Sound & picture finishing |  | 2027-05-29 | 2027-10-25 | 150 | 0%
8.1 | VFX shot delivery | VFX vendor | 2027-05-29 | 2027-10-05 | 130 | 0%
8.2 | ADR & foley | Sound | 2027-08-10 | 2027-09-08 | 30 | 0%
8.3 | Sound design & score | Composer | 2027-08-10 | 2027-10-03 | 55 | 0%
8.4 | Final mix | Re-recording mixer | 2027-10-04 | 2027-10-18 | 15 | 0%
8.5 | Colour grade & online conform | Colourist | 2027-10-06 | 2027-10-25 | 20 | 0%
9 | Delivery & distribution |  | 2027-10-26 | 2028-01-03 | 70 | 0%
9.1 | DCP & master creation | Post supervisor | 2027-10-26 | 2027-11-14 | 20 | 0%
9.2 | QC & technical review | Post supervisor | 2027-11-13 | 2027-11-27 | 15 | 0%
9.3 | Captions & localisation | Post supervisor | 2027-11-15 | 2027-12-09 | 25 | 0%
9.4 | Marketing materials & trailer | Marketing | 2027-10-16 | 2027-12-04 | 50 | 0%
9.5 | Festival submissions | Producer | 2027-11-25 | 2027-12-24 | 30 | 0%
10 | Delivery accepted |  | 2028-01-04 | 2028-01-04 | — | —