## Gantt
Film Production Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10
1 | Development |  | 2026-08-02 | 2026-12-29 | 150
1.1 | Script drafts & rewrites | Writer | 2026-08-02 | 2026-10-30 | 90
1.2 | Rights & option agreements | Legal | 2026-08-22 | 2026-10-05 | 45
1.3 | Budget & schedule breakdown | Line producer | 2026-10-16 | 2026-11-19 | 35
1.4 | Financing & attachments | Producer | 2026-10-31 | 2026-12-29 | 60
2 | ◆ Greenlight |  | 2026-12-30 | 2026-12-30 | [22 empty] | ◆
3 | Pre-production |  | 2026-12-30 | 2027-03-14 | 75
3.1 | Casting — leads | Casting | 2026-12-30 | 2027-02-02 | 35
3.2 | Department heads hired | Producer | 2026-12-30 | 2027-01-23 | 25
3.3 | Location scout & permits | Locations | 2027-01-07 | 2027-02-25 | 50
3.4 | Production design & build | Production designer | 2027-01-21 | 2027-03-06 | 45
3.5 | Wardrobe & make-up prep | Costume | 2027-01-29 | 2027-03-09 | 40
3.6 | Shooting schedule locked | First AD | 2027-02-03 | 2027-02-22 | 20
3.7 | Camera & equipment tests | Camera | 2027-02-28 | 2027-03-09 | 10
4 | Principal photography |  | 2027-03-15 | 2027-04-23 | 40
4.1 | Block 1 — studio stage | Crew | 2027-03-15 | 2027-03-28 | 14
4.2 | Block 2 — location exteriors | Crew | 2027-03-30 | 2027-04-13 | 15
4.3 | Block 3 — pick-ups & inserts | Crew | 2027-04-15 | 2027-04-20 | 6
4.4 | Contingency days | Crew | 2027-04-21 | 2027-04-23 | 3
5 | ◆ Picture wrap |  | 2027-04-24 | 2027-04-24 | [38 empty] | ◆
6 | Post-production — picture |  | 2027-03-18 | 2027-08-09 | 145
6.1 | Dailies & assembly | Editor | 2027-03-18 | 2027-05-01 | 45
6.2 | Editor's cut | Editor | 2027-04-24 | 2027-05-23 | 30
6.3 | Director's cut | Director | 2027-05-24 | 2027-07-07 | 45
6.4 | Notes & recut | Editor | 2027-07-08 | 2027-08-09 | 33
7 | ◆ Picture lock |  | 2027-08-10 | 2027-08-10 | [54 empty] | ◆
8 | Sound & picture finishing |  | 2027-05-29 | 2027-10-25 | 150
8.1 | VFX shot delivery | VFX vendor | 2027-05-29 | 2027-10-05 | 130
8.2 | ADR & foley | Sound | 2027-08-10 | 2027-09-08 | 30
8.3 | Sound design & score | Composer | 2027-08-10 | 2027-10-03 | 55
8.4 | Final mix | Re-recording mixer | 2027-10-04 | 2027-10-18 | 15
8.5 | Colour grade & online conform | Colourist | 2027-10-06 | 2027-10-25 | 20
9 | Delivery & distribution |  | 2027-10-26 | 2028-01-03 | 70
9.1 | DCP & master creation | Post supervisor | 2027-10-26 | 2027-11-14 | 20
9.2 | QC & technical review | Post supervisor | 2027-11-13 | 2027-11-27 | 15
9.3 | Captions & localisation | Post supervisor | 2027-11-15 | 2027-12-09 | 25
9.4 | Marketing materials & trailer | Marketing | 2027-10-16 | 2027-12-04 | 50
9.5 | Festival submissions | Producer | 2027-11-25 | 2027-12-24 | 30
10 | ◆ Delivery accepted |  | 2028-01-04 | 2028-01-04 | [75 empty] | ◆