## Slide 1
Franchise Rollout Plan
Free Gantt chart template · gantts.app

## Slide 2
Franchise Rollout Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
System readiness
Unit economics model
Franchise legal & disclosure pack
Operations manual
Brand standards & fit-out kit
Supplier & logistics agreements
Field support model & hiring
◆ System ready to sell
Territory & pipeline
Territory mapping & market sizing
Franchisee marketing & lead gen
Applications & discovery days
Financial qualification & approval
◆ First agreements signed
Wave 1 units
W1 site selection & approval
W1 lease & landlord works
W1 design & permits
W1 fit-out & equipment
W1 franchisee & staff training
W1 launch marketing
W1 opening week support
◆ Wave 1 open
Wave 2 units
W2 franchisee approval
W2 site selection & lease
W2 design & permits
W2 fit-out & equipment
W2 training & launch marketing
◆ Wave 2 open
Wave 3 units
W3 franchisee approval
W3 site selection & lease
W3 design & permits
W3 fit-out & equipment
W3 training & launch marketing
◆ Wave 3 open
Support & system improvement
Post-opening field visits
Unit performance reviews
Manual & training updates
Rollout review & next-wave sizing
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | System readiness |  | 2026-08-02 | 2026-12-19 | 140 | 100%
1.1 | Unit economics model | Finance | 2026-08-02 | 2026-09-05 | 35 | 100%
1.2 | Franchise legal & disclosure pack | Legal | 2026-08-27 | 2026-11-04 | 70 | 100%
1.3 | Operations manual | Ops | 2026-08-22 | 2026-11-19 | 90 | 100%
1.4 | Brand standards & fit-out kit | Brand | 2026-09-26 | 2026-11-24 | 60 | 100%
1.5 | Supplier & logistics agreements | Procurement | 2026-10-21 | 2026-12-09 | 50 | 100%
1.6 | Field support model & hiring | Ops | 2026-11-05 | 2026-12-19 | 45 | 100%
2 | System ready to sell |  | 2026-12-20 | 2026-12-20 | — | —
3 | Territory & pipeline |  | 2026-11-10 | 2027-04-08 | 150 | 70%
3.1 | Territory mapping & market sizing | Development | 2026-11-10 | 2026-12-19 | 40 | 100%
3.2 | Franchisee marketing & lead gen | Development | 2026-12-20 | 2027-03-19 | 90 | 80%
3.3 | Applications & discovery days | Development | 2027-01-14 | 2027-03-14 | 60 | 60%
3.4 | Financial qualification & approval | Finance | 2027-02-13 | 2027-03-29 | 45 | 40%
4 | First agreements signed |  | 2027-04-04 | 2027-04-04 | — | —
5 | Wave 1 units |  | 2027-04-04 | 2027-10-15 | 195 | 10%
5.1 | W1 site selection & approval | Development | 2027-04-04 | 2027-05-18 | 45 | 20%
5.2 | W1 lease & landlord works | Legal | 2027-05-17 | 2027-06-25 | 40 | 0%
5.3 | W1 design & permits | Design | 2027-05-29 | 2027-07-17 | 50 | 0%
5.4 | W1 fit-out & equipment | Contractor | 2027-07-16 | 2027-09-13 | 60 | 0%
5.5 | W1 franchisee & staff training | Training | 2027-08-22 | 2027-09-20 | 30 | 0%
5.6 | W1 launch marketing | Marketing | 2027-09-01 | 2027-10-05 | 35 | 0%

## Slide 4
5.7 | W1 opening week support | Field manager | 2027-10-06 | 2027-10-15 | 10 | 0%
6 | Wave 1 open |  | 2027-10-16 | 2027-10-16 | — | —
7 | Wave 2 units |  | 2027-07-08 | 2028-01-23 | 200 | 0%
7.1 | W2 franchisee approval | Development | 2027-07-08 | 2027-08-21 | 45 | 0%
7.2 | W2 site selection & lease | Development | 2027-08-22 | 2027-10-20 | 60 | 0%
7.3 | W2 design & permits | Design | 2027-10-16 | 2027-12-04 | 50 | 0%
7.4 | W2 fit-out & equipment | Contractor | 2027-11-30 | 2028-01-23 | 55 | 0%
7.5 | W2 training & launch marketing | Training | 2027-12-20 | 2028-01-23 | 35 | 0%
8 | Wave 2 open |  | 2028-01-29 | 2028-01-29 | — | —
9 | Wave 3 units |  | 2027-11-15 | 2028-06-16 | 215 | 0%
9.1 | W3 franchisee approval | Development | 2027-11-15 | 2028-01-03 | 50 | 0%
9.2 | W3 site selection & lease | Development | 2028-01-04 | 2028-03-03 | 60 | 0%
9.3 | W3 design & permits | Design | 2028-03-02 | 2028-04-20 | 50 | 0%
9.4 | W3 fit-out & equipment | Contractor | 2028-04-18 | 2028-06-11 | 55 | 0%
9.5 | W3 training & launch marketing | Training | 2028-05-08 | 2028-06-11 | 35 | 0%
10 | Wave 3 open |  | 2028-06-17 | 2028-06-17 | — | —
11 | Support & system improvement |  | 2027-10-16 | 2028-07-01 | 260 | 0%
11.1 | Post-opening field visits | Field manager | 2027-10-16 | 2028-06-21 | 250 | 0%
11.2 | Unit performance reviews | Ops | 2027-12-15 | 2028-06-21 | 190 | 0%
11.3 | Manual & training updates | Ops | 2028-01-14 | 2028-03-13 | 60 | 0%
11.4 | Rollout review & next-wave sizing | Exec | 2028-06-22 | 2028-07-06 | 15 | 0%