## Gantt
Franchise Rollout Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26 | Jul 3 | Jul 10
1 | System readiness |  | 2026-08-02 | 2026-12-19 | 140
1.1 | Unit economics model | Finance | 2026-08-02 | 2026-09-05 | 35
1.2 | Franchise legal & disclosure pack | Legal | 2026-08-27 | 2026-11-04 | 70
1.3 | Operations manual | Ops | 2026-08-22 | 2026-11-19 | 90
1.4 | Brand standards & fit-out kit | Brand | 2026-09-26 | 2026-11-24 | 60
1.5 | Supplier & logistics agreements | Procurement | 2026-10-21 | 2026-12-09 | 50
1.6 | Field support model & hiring | Ops | 2026-11-05 | 2026-12-19 | 45
2 | ◆ System ready to sell |  | 2026-12-20 | 2026-12-20 | [21 empty] | ◆
3 | Territory & pipeline |  | 2026-11-10 | 2027-04-08 | 150
3.1 | Territory mapping & market sizing | Development | 2026-11-10 | 2026-12-19 | 40
3.2 | Franchisee marketing & lead gen | Development | 2026-12-20 | 2027-03-19 | 90
3.3 | Applications & discovery days | Development | 2027-01-14 | 2027-03-14 | 60
3.4 | Financial qualification & approval | Finance | 2027-02-13 | 2027-03-29 | 45
4 | ◆ First agreements signed |  | 2027-04-04 | 2027-04-04 | [36 empty] | ◆
5 | Wave 1 units |  | 2027-04-04 | 2027-10-15 | 195
5.1 | W1 site selection & approval | Development | 2027-04-04 | 2027-05-18 | 45
5.2 | W1 lease & landlord works | Legal | 2027-05-17 | 2027-06-25 | 40
5.3 | W1 design & permits | Design | 2027-05-29 | 2027-07-17 | 50
5.4 | W1 fit-out & equipment | Contractor | 2027-07-16 | 2027-09-13 | 60
5.5 | W1 franchisee & staff training | Training | 2027-08-22 | 2027-09-20 | 30
5.6 | W1 launch marketing | Marketing | 2027-09-01 | 2027-10-05 | 35
5.7 | W1 opening week support | Field manager | 2027-10-06 | 2027-10-15 | 10
6 | ◆ Wave 1 open |  | 2027-10-16 | 2027-10-16 | [63 empty] | ◆
7 | Wave 2 units |  | 2027-07-08 | 2028-01-23 | 200
7.1 | W2 franchisee approval | Development | 2027-07-08 | 2027-08-21 | 45
7.2 | W2 site selection & lease | Development | 2027-08-22 | 2027-10-20 | 60
7.3 | W2 design & permits | Design | 2027-10-16 | 2027-12-04 | 50
7.4 | W2 fit-out & equipment | Contractor | 2027-11-30 | 2028-01-23 | 55
7.5 | W2 training & launch marketing | Training | 2027-12-20 | 2028-01-23 | 35
8 | ◆ Wave 2 open |  | 2028-01-29 | 2028-01-29 | [78 empty] | ◆
9 | Wave 3 units |  | 2027-11-15 | 2028-06-16 | 215
9.1 | W3 franchisee approval | Development | 2027-11-15 | 2028-01-03 | 50
9.2 | W3 site selection & lease | Development | 2028-01-04 | 2028-03-03 | 60
9.3 | W3 design & permits | Design | 2028-03-02 | 2028-04-20 | 50
9.4 | W3 fit-out & equipment | Contractor | 2028-04-18 | 2028-06-11 | 55
9.5 | W3 training & launch marketing | Training | 2028-05-08 | 2028-06-11 | 35
10 | ◆ Wave 3 open |  | 2028-06-17 | 2028-06-17 | [98 empty] | ◆
11 | Support & system improvement |  | 2027-10-16 | 2028-07-01 | 260
11.1 | Post-opening field visits | Field manager | 2027-10-16 | 2028-06-21 | 250
11.2 | Unit performance reviews | Ops | 2027-12-15 | 2028-06-21 | 190
11.3 | Manual & training updates | Ops | 2028-01-14 | 2028-03-13 | 60
11.4 | Rollout review & next-wave sizing | Exec | 2028-06-22 | 2028-07-06 | 15