## Slide 1
GDPR Compliance Timeline
Free Gantt chart template · gantts.app

## Slide 2
GDPR Compliance Timeline
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Programme setup & scoping
Appoint DPO or accountable privacy lead
Determine controller and processor roles
Scope entities, systems & jurisdictions in play
Gap assessment against current practice
Governance forum & programme plan agreed
◆ Programme scope and roles agreed
Records of processing — the foundation
Data discovery workshops with each function
System and data store inventory
Map processing activities & data flows
Identify special category & children data
Draft records of processing activities
Sign off records with each data owner
◆ Records of processing baselined
Lawful basis, retention & transfers
Assign lawful basis per processing activity
Legitimate interests assessments where relied on
Consent capture & withdrawal mechanics rebuilt
Retention schedule & deletion rules per record type
International transfer mapping & mechanism selection
Privacy notices rewritten from the records
◆ Lawful basis and retention approved
Rights & DSAR response capability
Design data subject rights request procedure
Identity verification & intake channel build
Search and extraction tooling across systems
Train handling teams on the response period
Dry-run a full request end to end & time it
◆ DSAR process tested end to end
Security & breach notification readiness
Technical & organisational measures review
Breach detection & escalation path defined
Breach assessment & notification decision procedure
Breach register & documentation template
Tabletop breach exercise against the clock
◆ Breach response rehearsed
DPIAs, vendors & continuous operation
DPIA screening criteria & template
Run DPIAs on high-risk processing identified
Processor contract & Article 28 terms remediation
Privacy training & awareness rollout
Embed records review into the change process
Accountability evidence pack & annual review cycle
◆ Defensible position reached
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Programme setup & scoping |  | 2026-08-02 | 2026-09-20 | 50 | 100%
1.1 | Appoint DPO or accountable privacy lead | Exec | 2026-08-02 | 2026-08-16 | 15 | 100%
1.2 | Determine controller and processor roles | Legal | 2026-08-12 | 2026-08-29 | 18 | 100%
1.3 | Scope entities, systems & jurisdictions in play | Privacy lead | 2026-08-14 | 2026-09-07 | 25 | 100%
1.4 | Gap assessment against current practice | Consultant | 2026-08-27 | 2026-09-15 | 20 | 100%
1.5 | Governance forum & programme plan agreed | Exec | 2026-09-06 | 2026-09-20 | 15 | 100%
2 | Programme scope and roles agreed |  | 2026-09-21 | 2026-09-21 | — | —
3 | Records of processing — the foundation |  | 2026-09-21 | 2026-12-24 | 95 | 60%
3.1 | Data discovery workshops with each function | Privacy lead | 2026-09-21 | 2026-10-20 | 30 | 100%
3.2 | System and data store inventory | IT | 2026-09-26 | 2026-10-30 | 35 | 100%
3.3 | Map processing activities & data flows | Privacy lead | 2026-10-21 | 2026-11-24 | 35 | 70%
3.4 | Identify special category & children data | Privacy lead | 2026-11-05 | 2026-11-29 | 25 | 50%
3.5 | Draft records of processing activities | Privacy lead | 2026-11-15 | 2026-12-14 | 30 | 30%
3.6 | Sign off records with each data owner | Data owners | 2026-12-10 | 2026-12-24 | 15 | 0%
4 | Records of processing baselined |  | 2026-12-25 | 2026-12-25 | — | —
5 | Lawful basis, retention & transfers |  | 2026-12-25 | 2027-03-14 | 80 | 0%
5.1 | Assign lawful basis per processing activity | Legal | 2026-12-25 | 2027-01-23 | 30 | 0%
5.2 | Legitimate interests assessments where relied on | Legal | 2027-01-09 | 2027-02-07 | 30 | 0%
5.3 | Consent capture & withdrawal mechanics rebuilt | Engineering | 2027-01-14 | 2027-02-17 | 35 | 0%

## Slide 4
5.4 | Retention schedule & deletion rules per record type | Records manager | 2027-01-19 | 2027-02-27 | 40 | 0%
5.5 | International transfer mapping & mechanism selection | Legal | 2027-01-24 | 2027-03-09 | 45 | 0%
5.6 | Privacy notices rewritten from the records | Communications | 2027-02-03 | 2027-03-04 | 30 | 0%
6 | Lawful basis and retention approved |  | 2027-03-15 | 2027-03-15 | — | —
7 | Rights & DSAR response capability |  | 2027-02-18 | 2027-06-07 | 110 | 0%
7.1 | Design data subject rights request procedure | Privacy lead | 2027-02-18 | 2027-03-14 | 25 | 0%
7.2 | Identity verification & intake channel build | Support | 2027-03-05 | 2027-04-03 | 30 | 0%
7.3 | Search and extraction tooling across systems | IT | 2027-03-15 | 2027-04-28 | 45 | 0%
7.4 | Train handling teams on the response period | Privacy lead | 2027-04-24 | 2027-05-13 | 20 | 0%
7.5 | Dry-run a full request end to end & time it | Privacy lead | 2027-05-14 | 2027-06-02 | 20 | 0%
8 | DSAR process tested end to end |  | 2027-06-08 | 2027-06-08 | — | —
9 | Security & breach notification readiness |  | 2027-03-30 | 2027-07-27 | 120 | 0%
9.1 | Technical & organisational measures review | Security | 2027-03-30 | 2027-05-08 | 40 | 0%
9.2 | Breach detection & escalation path defined | Security | 2027-05-09 | 2027-06-02 | 25 | 0%
9.3 | Breach assessment & notification decision procedure | Legal | 2027-05-24 | 2027-06-17 | 25 | 0%
9.4 | Breach register & documentation template | Privacy lead | 2027-06-03 | 2027-06-17 | 15 | 0%
9.5 | Tabletop breach exercise against the clock | Incident team | 2027-06-18 | 2027-07-02 | 15 | 0%
10 | Breach response rehearsed |  | 2027-07-28 | 2027-07-28 | — | —
11 | DPIAs, vendors & continuous operation |  | 2027-05-29 | 2027-10-25 | 150 | 0%
11.1 | DPIA screening criteria & template | Privacy lead | 2027-05-29 | 2027-06-22 | 25 | 0%

## Slide 5
11.2 | Run DPIAs on high-risk processing identified | Privacy lead | 2027-06-23 | 2027-08-11 | 50 | 0%
11.3 | Processor contract & Article 28 terms remediation | Procurement | 2027-06-08 | 2027-08-06 | 60 | 0%
11.4 | Privacy training & awareness rollout | HR | 2027-07-28 | 2027-09-05 | 40 | 0%
11.5 | Embed records review into the change process | Privacy lead | 2027-08-27 | 2027-09-30 | 35 | 0%
11.6 | Accountability evidence pack & annual review cycle | Privacy lead | 2027-09-16 | 2027-10-25 | 40 | 0%
12 | Defensible position reached |  | 2027-10-26 | 2027-10-26 | — | —