## Slide 1
Go-to-Market Plan
Free Gantt chart template · gantts.app

## Slide 2
Go-to-Market Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Market & customer research
Define ICP & buyer personas
Competitive & market analysis
Validate problem & willingness to pay
◆ Research complete
Positioning & messaging
Positioning & value proposition
Messaging framework & pillars
◆ Messaging approved
Pricing & packaging
Pricing model & tiers
Business case & targets
◆ Pricing signed off
Enablement & assets
Sales enablement & training
Website & landing pages
Demo, collateral & docs
◆ Assets ready
Launch
Internal launch & readiness
◆ External launch, go live
Launch campaigns & PR
Sales outreach & pipeline
Post-launch & iterate
Measure funnel & KPIs
Gather feedback & win/loss
Optimize funnel & iterate
◆ 30-day review
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Market & customer research |  | 2026-08-02 | 2026-08-22 | 21 | 100%
1.1 | Define ICP & buyer personas | Product Marketing | 2026-08-02 | 2026-08-08 | 7 | 100%
1.2 | Competitive & market analysis | Product Marketing | 2026-08-09 | 2026-08-18 | 10 | 100%
1.3 | Validate problem & willingness to pay | Product | 2026-08-16 | 2026-08-22 | 7 | 80%
2 | Research complete |  | 2026-08-23 | 2026-08-23 | , | ,
3 | Positioning & messaging |  | 2026-08-23 | 2026-09-09 | 18 | 40%
3.1 | Positioning & value proposition | Product Marketing | 2026-08-23 | 2026-09-01 | 10 | 60%
3.2 | Messaging framework & pillars | Product Marketing | 2026-09-02 | 2026-09-09 | 8 | 20%
4 | Messaging approved |  | 2026-09-10 | 2026-09-10 | , | ,
5 | Pricing & packaging |  | 2026-09-03 | 2026-09-22 | 20 | 20%
5.1 | Pricing model & tiers | Product | 2026-09-03 | 2026-09-14 | 12 | 30%
5.2 | Business case & targets | Finance | 2026-09-15 | 2026-09-22 | 8 | 0%
6 | Pricing signed off |  | 2026-09-23 | 2026-09-23 | , | ,
7 | Enablement & assets |  | 2026-09-16 | 2026-10-15 | 30 | 0%
7.1 | Sales enablement & training | Sales Enablement | 2026-09-16 | 2026-09-29 | 14 | 0%
7.2 | Website & landing pages | Marketing | 2026-09-16 | 2026-10-03 | 18 | 0%
7.3 | Demo, collateral & docs | Product Marketing | 2026-09-23 | 2026-10-08 | 16 | 0%
8 | Assets ready |  | 2026-10-16 | 2026-10-16 | , | ,
9 | Launch |  | 2026-10-11 | 2026-10-30 | 20 | 0%
9.1 | Internal launch & readiness | Product Marketing | 2026-10-11 | 2026-10-15 | 5 | 0%
10 | External launch, go live |  | 2026-10-16 | 2026-10-16 | , | ,

## Slide 4
10.1 | Launch campaigns & PR | Marketing | 2026-10-16 | 2026-10-27 | 12 | 0%
10.2 | Sales outreach & pipeline | Sales | 2026-10-18 | 2026-10-30 | 13 | 0%
11 | Post-launch & iterate |  | 2026-10-31 | 2026-11-19 | 20 | 0%
11.1 | Measure funnel & KPIs | Product Marketing | 2026-10-31 | 2026-11-09 | 10 | 0%
11.2 | Gather feedback & win/loss | Sales | 2026-11-05 | 2026-11-12 | 8 | 0%
11.3 | Optimize funnel & iterate | Marketing | 2026-11-10 | 2026-11-19 | 10 | 0%
12 | 30-day review |  | 2026-11-20 | 2026-11-20 | , | ,