## Gantt
Go-to-Market Plan
Made free at gantts.app, edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23
1 | Market & customer research |  | 2026-08-02 | 2026-08-22 | 21
1.1 | Define ICP & buyer personas | Product Marketing | 2026-08-02 | 2026-08-08 | 7
1.2 | Competitive & market analysis | Product Marketing | 2026-08-09 | 2026-08-18 | 10
1.3 | Validate problem & willingness to pay | Product | 2026-08-16 | 2026-08-22 | 7
2 | ◆ Research complete |  | 2026-08-23 | 2026-08-23 |  |  |  |  | ◆
3 | Positioning & messaging |  | 2026-08-23 | 2026-09-09 | 18
3.1 | Positioning & value proposition | Product Marketing | 2026-08-23 | 2026-09-01 | 10
3.2 | Messaging framework & pillars | Product Marketing | 2026-09-02 | 2026-09-09 | 8
4 | ◆ Messaging approved |  | 2026-09-10 | 2026-09-10 | [6 empty] | ◆
5 | Pricing & packaging |  | 2026-09-03 | 2026-09-22 | 20
5.1 | Pricing model & tiers | Product | 2026-09-03 | 2026-09-14 | 12
5.2 | Business case & targets | Finance | 2026-09-15 | 2026-09-22 | 8
6 | ◆ Pricing signed off |  | 2026-09-23 | 2026-09-23 | [8 empty] | ◆
7 | Enablement & assets |  | 2026-09-16 | 2026-10-15 | 30
7.1 | Sales enablement & training | Sales Enablement | 2026-09-16 | 2026-09-29 | 14
7.2 | Website & landing pages | Marketing | 2026-09-16 | 2026-10-03 | 18
7.3 | Demo, collateral & docs | Product Marketing | 2026-09-23 | 2026-10-08 | 16
8 | ◆ Assets ready |  | 2026-10-16 | 2026-10-16 | [11 empty] | ◆
9 | Launch |  | 2026-10-11 | 2026-10-30 | 20
9.1 | Internal launch & readiness | Product Marketing | 2026-10-11 | 2026-10-15 | 5
10 | ◆ External launch, go live |  | 2026-10-16 | 2026-10-16 | [11 empty] | ◆
10.1 | Launch campaigns & PR | Marketing | 2026-10-16 | 2026-10-27 | 12
10.2 | Sales outreach & pipeline | Sales | 2026-10-18 | 2026-10-30 | 13
11 | Post-launch & iterate |  | 2026-10-31 | 2026-11-19 | 20
11.1 | Measure funnel & KPIs | Product Marketing | 2026-10-31 | 2026-11-09 | 10
11.2 | Gather feedback & win/loss | Sales | 2026-11-05 | 2026-11-12 | 8
11.3 | Optimize funnel & iterate | Marketing | 2026-11-10 | 2026-11-19 | 10
12 | ◆ 30-day review |  | 2026-11-20 | 2026-11-20 | [16 empty] | ◆