## Slide 1
Gym Opening
Free Gantt chart template · gantts.app

## Slide 2
Gym Opening
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Concept, site & lease
Concept, format & catchment analysis
Financial model & membership price ladder
Site search & unit shortlist
Funding, entity & insurance in place
Lease heads of terms & signature
◆ Lease signed
Design, permits & fit-out
Gym floor layout & zoning plan
Building permit & change of use application
Structural floor loading & acoustic isolation design
Strip-out, MEP rough-in & HVAC upgrade
Changing rooms, showers & drainage
Rubber flooring, mirrors & studio finishes
◆ Fit-out substantially complete
Equipment procurement & installation
Equipment specification & supplier quotes
Cardio & strength equipment order placed
Long-lead manufacture & shipping
Free weights, racks & functional rig delivery
Equipment install, assembly & anchoring
Equipment safety inspection & asset register
◆ Gym floor equipped and safe to use
Brand, marketing & founding-member pre-sale
Brand identity, name & signage design
Website, booking app & payment gateway live
Hoarding, local PR & waiting list build
◆ Founding-member pre-sale opens
Founding-member pre-sale campaign
Pre-sale open days in the unfinished space
◆ Founding-member target reached
Staffing, certification & programming
Manager and trainer recruitment
Trainer certification & insurance checks
Class timetable built & instructors assigned
Equipment familiarisation & induction training
First aid, CPR & emergency procedure drills
Class rehearsal & timetable dry run
◆ Team ready to operate
Inspections, soft launch & opening
Fire safety & occupancy inspection
Cleaning, stock, retail & vending set-up
Access control, lockers & member card issue
Founding-member soft launch week
Snagging and feedback fixes
◆ Public opening day
First month retention review
◆ Steady-state operation
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Concept, site & lease |  | 2026-08-02 | 2026-11-09 | 100 | 100%
1.1 | Concept, format & catchment analysis | Founder | 2026-08-02 | 2026-08-31 | 30 | 100%
1.2 | Financial model & membership price ladder | Founder | 2026-08-22 | 2026-09-20 | 30 | 100%
1.3 | Site search & unit shortlist | Property | 2026-08-27 | 2026-10-10 | 45 | 100%
1.4 | Funding, entity & insurance in place | Founder | 2026-09-21 | 2026-11-04 | 45 | 100%
1.5 | Lease heads of terms & signature | Property | 2026-10-06 | 2026-11-09 | 35 | 100%
2 | Lease signed |  | 2026-11-10 | 2026-11-10 | — | —
3 | Design, permits & fit-out |  | 2026-11-10 | 2027-04-23 | 165 | 30%
3.1 | Gym floor layout & zoning plan | Designer | 2026-11-10 | 2026-12-09 | 30 | 100%
3.2 | Building permit & change of use application | Regulatory | 2026-12-05 | 2027-02-02 | 60 | 60%
3.3 | Structural floor loading & acoustic isolation design | Engineer | 2026-12-10 | 2027-01-13 | 35 | 50%
3.4 | Strip-out, MEP rough-in & HVAC upgrade | Contractor | 2027-02-03 | 2027-03-29 | 55 | 0%
3.5 | Changing rooms, showers & drainage | Contractor | 2027-02-28 | 2027-04-13 | 45 | 0%
3.6 | Rubber flooring, mirrors & studio finishes | Contractor | 2027-03-25 | 2027-04-23 | 30 | 0%
4 | Fit-out substantially complete |  | 2027-04-24 | 2027-04-24 | — | —
5 | Equipment procurement & installation |  | 2026-11-20 | 2027-05-18 | 180 | 20%
5.1 | Equipment specification & supplier quotes | Founder | 2026-11-20 | 2026-12-24 | 35 | 100%
5.2 | Cardio & strength equipment order placed | Procurement | 2026-12-25 | 2027-01-08 | 15 | 100%
5.3 | Long-lead manufacture & shipping | Supplier | 2027-01-09 | 2027-04-13 | 95 | 30%

## Slide 4
5.4 | Free weights, racks & functional rig delivery | Supplier | 2027-04-09 | 2027-04-20 | 12 | 0%
5.5 | Equipment install, assembly & anchoring | Installer | 2027-04-21 | 2027-05-08 | 18 | 0%
5.6 | Equipment safety inspection & asset register | Operations | 2027-05-09 | 2027-05-16 | 8 | 0%
6 | Gym floor equipped and safe to use |  | 2027-05-19 | 2027-05-19 | — | —
7 | Brand, marketing & founding-member pre-sale |  | 2026-12-10 | 2027-05-18 | 160 | 40%
7.1 | Brand identity, name & signage design | Marketing | 2026-12-10 | 2027-01-13 | 35 | 100%
7.2 | Website, booking app & payment gateway live | Marketing | 2027-01-09 | 2027-02-22 | 45 | 80%
7.3 | Hoarding, local PR & waiting list build | Marketing | 2027-01-14 | 2027-03-14 | 60 | 70%
8 | Founding-member pre-sale opens |  | 2027-02-23 | 2027-02-23 | — | —
8.1 | Founding-member pre-sale campaign | Sales | 2027-02-23 | 2027-05-18 | 85 | 30%
8.2 | Pre-sale open days in the unfinished space | Sales | 2027-03-20 | 2027-04-18 | 30 | 0%
9 | Founding-member target reached |  | 2027-05-19 | 2027-05-19 | — | —
10 | Staffing, certification & programming |  | 2027-03-20 | 2027-06-17 | 90 | 0%
10.1 | Manager and trainer recruitment | HR | 2027-03-20 | 2027-04-28 | 40 | 0%
10.2 | Trainer certification & insurance checks | HR | 2027-04-24 | 2027-05-23 | 30 | 0%
10.3 | Class timetable built & instructors assigned | Operations | 2027-05-14 | 2027-06-02 | 20 | 0%
10.4 | Equipment familiarisation & induction training | Operations | 2027-05-19 | 2027-05-30 | 12 | 0%
10.5 | First aid, CPR & emergency procedure drills | Operations | 2027-05-24 | 2027-06-02 | 10 | 0%
10.6 | Class rehearsal & timetable dry run | Operations | 2027-06-03 | 2027-06-10 | 8 | 0%
11 | Team ready to operate |  | 2027-06-13 | 2027-06-13 | — | —
12 | Inspections, soft launch & opening |  | 2027-05-19 | 2027-08-01 | 75 | 0%
12.1 | Fire safety & occupancy inspection | Regulator | 2027-05-19 | 2027-05-30 | 12 | 0%

## Slide 5
12.2 | Cleaning, stock, retail & vending set-up | Operations | 2027-05-29 | 2027-06-09 | 12 | 0%
12.3 | Access control, lockers & member card issue | IT | 2027-05-31 | 2027-06-09 | 10 | 0%
12.4 | Founding-member soft launch week | Sales | 2027-06-13 | 2027-06-19 | 7 | 0%
12.5 | Snagging and feedback fixes | Operations | 2027-06-20 | 2027-06-27 | 8 | 0%
13 | Public opening day |  | 2027-07-03 | 2027-07-03 | — | —
13.1 | First month retention review | Founder | 2027-07-03 | 2027-08-01 | 30 | 0%
14 | Steady-state operation |  | 2027-08-02 | 2027-08-02 | — | —