## Gantt
Gym Opening
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9
1 | Concept, site & lease |  | 2026-08-02 | 2026-11-09 | 100
1.1 | Concept, format & catchment analysis | Founder | 2026-08-02 | 2026-08-31 | 30
1.2 | Financial model & membership price ladder | Founder | 2026-08-22 | 2026-09-20 | 30
1.3 | Site search & unit shortlist | Property | 2026-08-27 | 2026-10-10 | 45
1.4 | Funding, entity & insurance in place | Founder | 2026-09-21 | 2026-11-04 | 45
1.5 | Lease heads of terms & signature | Property | 2026-10-06 | 2026-11-09 | 35
2 | ◆ Lease signed |  | 2026-11-10 | 2026-11-10 | [15 empty] | ◆
3 | Design, permits & fit-out |  | 2026-11-10 | 2027-04-23 | 165
3.1 | Gym floor layout & zoning plan | Designer | 2026-11-10 | 2026-12-09 | 30
3.2 | Building permit & change of use application | Regulatory | 2026-12-05 | 2027-02-02 | 60
3.3 | Structural floor loading & acoustic isolation design | Engineer | 2026-12-10 | 2027-01-13 | 35
3.4 | Strip-out, MEP rough-in & HVAC upgrade | Contractor | 2027-02-03 | 2027-03-29 | 55
3.5 | Changing rooms, showers & drainage | Contractor | 2027-02-28 | 2027-04-13 | 45
3.6 | Rubber flooring, mirrors & studio finishes | Contractor | 2027-03-25 | 2027-04-23 | 30
4 | ◆ Fit-out substantially complete |  | 2027-04-24 | 2027-04-24 | [38 empty] | ◆
5 | Equipment procurement & installation |  | 2026-11-20 | 2027-05-18 | 180
5.1 | Equipment specification & supplier quotes | Founder | 2026-11-20 | 2026-12-24 | 35
5.2 | Cardio & strength equipment order placed | Procurement | 2026-12-25 | 2027-01-08 | 15
5.3 | Long-lead manufacture & shipping | Supplier | 2027-01-09 | 2027-04-13 | 95
5.4 | Free weights, racks & functional rig delivery | Supplier | 2027-04-09 | 2027-04-20 | 12
5.5 | Equipment install, assembly & anchoring | Installer | 2027-04-21 | 2027-05-08 | 18
5.6 | Equipment safety inspection & asset register | Operations | 2027-05-09 | 2027-05-16 | 8
6 | ◆ Gym floor equipped and safe to use |  | 2027-05-19 | 2027-05-19 | [42 empty] | ◆
7 | Brand, marketing & founding-member pre-sale |  | 2026-12-10 | 2027-05-18 | 160
7.1 | Brand identity, name & signage design | Marketing | 2026-12-10 | 2027-01-13 | 35
7.2 | Website, booking app & payment gateway live | Marketing | 2027-01-09 | 2027-02-22 | 45
7.3 | Hoarding, local PR & waiting list build | Marketing | 2027-01-14 | 2027-03-14 | 60
8 | ◆ Founding-member pre-sale opens |  | 2027-02-23 | 2027-02-23 | [30 empty] | ◆
8.1 | Founding-member pre-sale campaign | Sales | 2027-02-23 | 2027-05-18 | 85
8.2 | Pre-sale open days in the unfinished space | Sales | 2027-03-20 | 2027-04-18 | 30
9 | ◆ Founding-member target reached |  | 2027-05-19 | 2027-05-19 | [42 empty] | ◆
10 | Staffing, certification & programming |  | 2027-03-20 | 2027-06-17 | 90
10.1 | Manager and trainer recruitment | HR | 2027-03-20 | 2027-04-28 | 40
10.2 | Trainer certification & insurance checks | HR | 2027-04-24 | 2027-05-23 | 30
10.3 | Class timetable built & instructors assigned | Operations | 2027-05-14 | 2027-06-02 | 20
10.4 | Equipment familiarisation & induction training | Operations | 2027-05-19 | 2027-05-30 | 12
10.5 | First aid, CPR & emergency procedure drills | Operations | 2027-05-24 | 2027-06-02 | 10
10.6 | Class rehearsal & timetable dry run | Operations | 2027-06-03 | 2027-06-10 | 8
11 | ◆ Team ready to operate |  | 2027-06-13 | 2027-06-13 | [46 empty] | ◆
12 | Inspections, soft launch & opening |  | 2027-05-19 | 2027-08-01 | 75
12.1 | Fire safety & occupancy inspection | Regulator | 2027-05-19 | 2027-05-30 | 12
12.2 | Cleaning, stock, retail & vending set-up | Operations | 2027-05-29 | 2027-06-09 | 12
12.3 | Access control, lockers & member card issue | IT | 2027-05-31 | 2027-06-09 | 10
12.4 | Founding-member soft launch week | Sales | 2027-06-13 | 2027-06-19 | 7
12.5 | Snagging and feedback fixes | Operations | 2027-06-20 | 2027-06-27 | 8
13 | ◆ Public opening day |  | 2027-07-03 | 2027-07-03 | [48 empty] | ◆
13.1 | First month retention review | Founder | 2027-07-03 | 2027-08-01 | 30
14 | ◆ Steady-state operation |  | 2027-08-02 | 2027-08-02 | [53 empty] | ◆