## Slide 1
Home Renovation Schedule
Free Gantt chart template · gantts.app

## Slide 2
Home Renovation Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Planning
Design & budget
Permits & approvals
Demolition
Demo & prep
Structural & rough-in
Framing & structure
Electrical, plumbing & HVAC
Finishes
Drywall, paint & flooring
Final inspection & walkthrough
◆ Project complete
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Planning |  | 2026-08-02 | 2026-08-22 | 21 | 100%
1.1 | Design & budget | Owner | 2026-08-02 | 2026-08-15 | 14 | 100%
1.2 | Permits & approvals | Contractor | 2026-08-12 | 2026-08-25 | 14 | 60%
2 | Demolition |  | 2026-08-26 | 2026-08-30 | 5 | 0%
2.1 | Demo & prep | Crew | 2026-08-26 | 2026-08-30 | 5 | 0%
3 | Structural & rough-in |  | 2026-08-31 | 2026-09-19 | 20 | 0%
3.1 | Framing & structure | Crew | 2026-08-31 | 2026-09-07 | 8 | 0%
3.2 | Electrical, plumbing & HVAC | Trades | 2026-09-08 | 2026-09-19 | 12 | 0%
4 | Finishes |  | 2026-09-20 | 2026-10-09 | 20 | 0%
4.1 | Drywall, paint & flooring | Crew | 2026-09-20 | 2026-10-04 | 15 | 0%
4.2 | Final inspection & walkthrough | Owner | 2026-10-10 | 2026-10-12 | 3 | 0%
5 | Project complete |  | 2026-10-13 | 2026-10-13 | — | —