## Gantt
Hospital Department Opening
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3
1 | Business case & approval |  | 2026-08-02 | 2026-10-30 | 90
1.1 | Clinical need & service model | Clinical director | 2026-08-02 | 2026-09-05 | 35
1.2 | Activity & workforce modelling | Planning | 2026-08-27 | 2026-09-30 | 35
1.3 | Capital business case | Finance | 2026-09-21 | 2026-10-30 | 40
1.4 | Board & commissioner approval | Board | 2026-10-16 | 2026-10-30 | 15
2 | ◆ Business case approved |  | 2026-10-31 | 2026-10-31 | [13 empty] | ◆
3 | Design & derogations |  | 2026-10-31 | 2027-02-27 | 120
3.1 | Schedule of accommodation | Project team | 2026-10-31 | 2026-11-29 | 30
3.2 | Detailed design to HBN / HTM | Architect | 2026-11-25 | 2027-01-28 | 65
3.3 | Derogations agreed | Estates & IPC | 2027-01-09 | 2027-02-17 | 40
3.4 | Statutory approvals & permits | Consultant | 2027-01-19 | 2027-02-27 | 40
4 | ◆ Design frozen |  | 2027-02-28 | 2027-02-28 | [31 empty] | ◆
5 | Construction & fit-out |  | 2027-02-28 | 2027-08-26 | 180
5.1 | Enabling works & service decant | Contractor | 2027-02-28 | 2027-04-08 | 40
5.2 | Structure & MEP works | Contractor | 2027-04-04 | 2027-07-07 | 95
5.3 | Medical gas pipeline install | Specialist | 2027-05-29 | 2027-07-12 | 45
5.4 | Ventilation & isolation rooms | Specialist | 2027-06-13 | 2027-08-06 | 55
5.5 | Finishes & handover | Contractor | 2027-07-08 | 2027-08-26 | 50
6 | ◆ Construction complete |  | 2027-08-27 | 2027-08-27 | [56 empty] | ◆
7 | Medical equipment |  | 2026-12-30 | 2027-10-15 | 290
7.1 | Equipment schedule & budget | Clinical lead | 2026-12-30 | 2027-02-12 | 45
7.2 | Procurement & tender | Procurement | 2027-02-13 | 2027-04-23 | 70
7.3 | Long-lead imaging order | Procurement | 2027-04-24 | 2027-08-21 | 120
7.4 | Delivery & installation | Supplier | 2027-08-25 | 2027-09-23 | 30
7.5 | Acceptance testing & calibration | Medical physics | 2027-09-21 | 2027-10-15 | 25
8 | Infection prevention & validation |  | 2027-06-28 | 2027-10-25 | 120
8.1 | IPC design & build review | IPC team | 2027-06-28 | 2027-07-27 | 30
8.2 | Ventilation validation | Authorising engineer | 2027-08-27 | 2027-09-20 | 25
8.3 | Water safety & flushing regime | Estates | 2027-08-27 | 2027-10-10 | 45
8.4 | Environmental & micro sampling | Microbiology | 2027-10-01 | 2027-10-20 | 20
9 | ◆ IPC sign-off |  | 2027-10-26 | 2027-10-26 | [65 empty] | ◆
10 | Staffing & competency |  | 2027-03-30 | 2027-11-04 | 220
10.1 | Workforce plan & establishment | HR | 2027-03-30 | 2027-05-08 | 40
10.2 | Recruitment campaign | HR | 2027-05-09 | 2027-08-11 | 95
10.3 | Credentialing & practising privileges | Medical staffing | 2027-08-07 | 2027-09-25 | 50
10.4 | Induction & competency sign-off | Practice educator | 2027-09-26 | 2027-11-04 | 40
11 | Information governance |  | 2027-05-29 | 2027-11-04 | 160
11.1 | Clinical systems configuration | Digital | 2027-05-29 | 2027-07-27 | 60
11.2 | DPIA & records governance | IG lead | 2027-06-28 | 2027-08-16 | 50
11.3 | Interface & reporting testing | Digital | 2027-08-22 | 2027-10-05 | 45
11.4 | IG sign-off | IG lead | 2027-10-16 | 2027-11-04 | 20
12 | Commissioning & opening |  | 2027-10-16 | 2027-12-29 | 75
12.1 | Operational policies & SOPs | Matron | 2027-10-16 | 2027-11-14 | 30
12.2 | Regulator registration & inspection | Governance | 2027-10-28 | 2027-12-11 | 45
12.3 | Simulation & dry-run days | All | 2027-11-15 | 2027-11-29 | 15
13 | ◆ Go / no-go review |  | 2027-12-15 | 2027-12-15 | [72 empty] | ◆
14 | ◆ First patient |  | 2027-12-30 | 2027-12-30 | [74 empty] | ◆