## Slide 1
Hotel Refurbishment Schedule
Free Gantt chart template · gantts.app

## Slide 2
Hotel Refurbishment Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feasibility & revenue planning
Condition survey & scope
Room-night displacement model
Closure strategy & phasing
◆ Capital approved
Design & procurement
Concept design & standards
Detailed design & FF&E spec
Mock-up room build
◆ Mock-up room signed off
FF&E procurement & lead times
Back-of-house & lifts
Riser & service survey
Plant & chiller replacement
Lift car 1 modernisation
Lift car 2 modernisation
BOH corridors & staff areas
Guest floor closures
◆ Noisy works window agreed
Floor 1 strip-out & fit-out
Floor 1 snag & return to sale
Floors 2-3 strip-out & fit-out
Floors 2-3 snag & return to sale
Floors 4-5 strip-out & fit-out
Floors 4-5 snag & return to sale
Guest decant & rebooking
◆ Last guest floor handed back
Public areas & F&B
Temporary lobby & bar provision
Lobby & reception refit
Restaurant & bar refit
Meeting rooms & spa
Handover & re-marketing
Commissioning & fire strategy sign-off
Staff retraining on new product
Photography & rate repositioning
◆ Full inventory restored
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Feasibility & revenue planning |  | 2026-08-02 | 2026-10-15 | 75 | 100%
1.1 | Condition survey & scope | Asset manager | 2026-08-02 | 2026-08-31 | 30 | 100%
1.2 | Room-night displacement model | Revenue | 2026-08-22 | 2026-09-20 | 30 | 100%
1.3 | Closure strategy & phasing | Asset manager | 2026-09-16 | 2026-10-15 | 30 | 100%
2 | Capital approved |  | 2026-10-16 | 2026-10-16 | — | —
3 | Design & procurement |  | 2026-10-16 | 2027-04-28 | 195 | 70%
3.1 | Concept design & standards | Designer | 2026-10-16 | 2026-11-29 | 45 | 100%
3.2 | Detailed design & FF&E spec | Designer | 2026-11-25 | 2027-01-18 | 55 | 90%
3.3 | Mock-up room build | Contractor | 2027-01-19 | 2027-02-17 | 30 | 60%
4 | Mock-up room signed off |  | 2027-02-18 | 2027-02-18 | — | —
4.1 | FF&E procurement & lead times | Procurement | 2027-01-24 | 2027-04-28 | 95 | 40%
5 | Back-of-house & lifts |  | 2027-02-18 | 2027-08-11 | 175 | 20%
5.1 | Riser & service survey | M&E | 2027-02-18 | 2027-03-14 | 25 | 80%
5.2 | Plant & chiller replacement | M&E | 2027-03-10 | 2027-05-08 | 60 | 30%
5.3 | Lift car 1 modernisation | Lift contractor | 2027-03-25 | 2027-05-28 | 65 | 10%
5.4 | Lift car 2 modernisation | Lift contractor | 2027-05-29 | 2027-08-01 | 65 | 0%
5.5 | BOH corridors & staff areas | Contractor | 2027-04-09 | 2027-06-17 | 70 | 0%
6 | Guest floor closures |  | 2027-04-29 | 2028-01-13 | 260 | 0%
7 | Noisy works window agreed |  | 2027-04-29 | 2027-04-29 | — | —
7.1 | Floor 1 strip-out & fit-out | Contractor | 2027-04-29 | 2027-06-27 | 60 | 0%
7.2 | Floor 1 snag & return to sale | Ops | 2027-06-28 | 2027-07-09 | 12 | 0%

## Slide 4
7.3 | Floors 2-3 strip-out & fit-out | Contractor | 2027-07-10 | 2027-09-22 | 75 | 0%
7.4 | Floors 2-3 snag & return to sale | Ops | 2027-09-23 | 2027-10-04 | 12 | 0%
7.5 | Floors 4-5 strip-out & fit-out | Contractor | 2027-10-05 | 2027-12-18 | 75 | 0%
7.6 | Floors 4-5 snag & return to sale | Ops | 2027-12-19 | 2027-12-30 | 12 | 0%
7.7 | Guest decant & rebooking | Front office | 2027-04-29 | 2028-01-03 | 250 | 0%
8 | Last guest floor handed back |  | 2027-12-31 | 2027-12-31 | — | —
9 | Public areas & F&B |  | 2027-08-17 | 2028-01-23 | 160 | 0%
9.1 | Temporary lobby & bar provision | Ops | 2027-08-17 | 2027-09-05 | 20 | 0%
9.2 | Lobby & reception refit | Contractor | 2027-09-01 | 2027-11-04 | 65 | 0%
9.3 | Restaurant & bar refit | Contractor | 2027-10-06 | 2027-12-04 | 60 | 0%
9.4 | Meeting rooms & spa | Contractor | 2027-11-25 | 2028-01-23 | 60 | 0%
10 | Handover & re-marketing |  | 2027-12-20 | 2028-02-22 | 65 | 0%
10.1 | Commissioning & fire strategy sign-off | M&E | 2027-12-20 | 2028-01-13 | 25 | 0%
10.2 | Staff retraining on new product | GM | 2027-12-25 | 2028-01-13 | 20 | 0%
10.3 | Photography & rate repositioning | Revenue | 2028-01-04 | 2028-02-02 | 30 | 0%
11 | Full inventory restored |  | 2028-02-23 | 2028-02-23 | — | —