## Gantt
Hotel Refurbishment Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28
1 | Feasibility & revenue planning |  | 2026-08-02 | 2026-10-15 | 75
1.1 | Condition survey & scope | Asset manager | 2026-08-02 | 2026-08-31 | 30
1.2 | Room-night displacement model | Revenue | 2026-08-22 | 2026-09-20 | 30
1.3 | Closure strategy & phasing | Asset manager | 2026-09-16 | 2026-10-15 | 30
2 | ◆ Capital approved |  | 2026-10-16 | 2026-10-16 | [11 empty] | ◆
3 | Design & procurement |  | 2026-10-16 | 2027-04-28 | 195
3.1 | Concept design & standards | Designer | 2026-10-16 | 2026-11-29 | 45
3.2 | Detailed design & FF&E spec | Designer | 2026-11-25 | 2027-01-18 | 55
3.3 | Mock-up room build | Contractor | 2027-01-19 | 2027-02-17 | 30
4 | ◆ Mock-up room signed off |  | 2027-02-18 | 2027-02-18 | [29 empty] | ◆
4.1 | FF&E procurement & lead times | Procurement | 2027-01-24 | 2027-04-28 | 95
5 | Back-of-house & lifts |  | 2027-02-18 | 2027-08-11 | 175
5.1 | Riser & service survey | M&E | 2027-02-18 | 2027-03-14 | 25
5.2 | Plant & chiller replacement | M&E | 2027-03-10 | 2027-05-08 | 60
5.3 | Lift car 1 modernisation | Lift contractor | 2027-03-25 | 2027-05-28 | 65
5.4 | Lift car 2 modernisation | Lift contractor | 2027-05-29 | 2027-08-01 | 65
5.5 | BOH corridors & staff areas | Contractor | 2027-04-09 | 2027-06-17 | 70
6 | Guest floor closures |  | 2027-04-29 | 2028-01-13 | 260
7 | ◆ Noisy works window agreed |  | 2027-04-29 | 2027-04-29 | [39 empty] | ◆
7.1 | Floor 1 strip-out & fit-out | Contractor | 2027-04-29 | 2027-06-27 | 60
7.2 | Floor 1 snag & return to sale | Ops | 2027-06-28 | 2027-07-09 | 12
7.3 | Floors 2-3 strip-out & fit-out | Contractor | 2027-07-10 | 2027-09-22 | 75
7.4 | Floors 2-3 snag & return to sale | Ops | 2027-09-23 | 2027-10-04 | 12
7.5 | Floors 4-5 strip-out & fit-out | Contractor | 2027-10-05 | 2027-12-18 | 75
7.6 | Floors 4-5 snag & return to sale | Ops | 2027-12-19 | 2027-12-30 | 12
7.7 | Guest decant & rebooking | Front office | 2027-04-29 | 2028-01-03 | 250
8 | ◆ Last guest floor handed back |  | 2027-12-31 | 2027-12-31 | [74 empty] | ◆
9 | Public areas & F&B |  | 2027-08-17 | 2028-01-23 | 160
9.1 | Temporary lobby & bar provision | Ops | 2027-08-17 | 2027-09-05 | 20
9.2 | Lobby & reception refit | Contractor | 2027-09-01 | 2027-11-04 | 65
9.3 | Restaurant & bar refit | Contractor | 2027-10-06 | 2027-12-04 | 60
9.4 | Meeting rooms & spa | Contractor | 2027-11-25 | 2028-01-23 | 60
10 | Handover & re-marketing |  | 2027-12-20 | 2028-02-22 | 65
10.1 | Commissioning & fire strategy sign-off | M&E | 2027-12-20 | 2028-01-13 | 25
10.2 | Staff retraining on new product | GM | 2027-12-25 | 2028-01-13 | 20
10.3 | Photography & rate repositioning | Revenue | 2028-01-04 | 2028-02-02 | 30
11 | ◆ Full inventory restored |  | 2028-02-23 | 2028-02-23 | [82 empty] | ◆