## Slide 1
Internal Audit Plan
Free Gantt chart template · gantts.app

## Slide 2
Internal Audit Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Annual planning
Risk assessment
Audit universe refresh
Stakeholder interviews
Resource & budget plan
Draft annual plan
◆ Plan approved by committee
Engagement scoping
Engagement announcement
Background research & data request
Process walkthroughs
Risk & control matrix
◆ Terms of reference agreed
Fieldwork & testing
Control design assessment
Sample selection
Substantive testing
Working papers & evidence
◆ Fieldwork complete
Findings & validation
Draft observations
Factual accuracy check
Rating & prioritization
Closing meeting
◆ Closing meeting held
Management response
Agree actions & owners
Target dates confirmed
Escalate accepted risks
Reporting
Draft report
Quality review
◆ Final report issued
Audit committee presentation
Follow-up
Remediation tracking
Verification testing of closed actions
Overdue actions reported to committee
◆ Follow-up cycle closed
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Annual planning |  | 2026-08-02 | 2026-09-30 | 60 | 100%
1.1 | Risk assessment | Audit lead | 2026-08-02 | 2026-08-26 | 25 | 100%
1.2 | Audit universe refresh | Audit lead | 2026-08-12 | 2026-08-31 | 20 | 100%
1.3 | Stakeholder interviews | Audit lead | 2026-08-17 | 2026-09-05 | 20 | 100%
1.4 | Resource & budget plan | Audit lead | 2026-09-01 | 2026-09-15 | 15 | 100%
1.5 | Draft annual plan | Audit lead | 2026-09-11 | 2026-09-25 | 15 | 100%
2 | Plan approved by committee |  | 2026-10-01 | 2026-10-01 | — | —
3 | Engagement scoping |  | 2026-10-01 | 2026-11-04 | 35 | 90%
3.1 | Engagement announcement | Audit manager | 2026-10-01 | 2026-10-03 | 3 | 100%
3.2 | Background research & data request | Auditor | 2026-10-04 | 2026-10-18 | 15 | 100%
3.3 | Process walkthroughs | Auditor | 2026-10-13 | 2026-10-27 | 15 | 80%
3.4 | Risk & control matrix | Auditor | 2026-10-21 | 2026-11-01 | 12 | 70%
4 | Terms of reference agreed |  | 2026-11-05 | 2026-11-05 | — | —
5 | Fieldwork & testing |  | 2026-11-05 | 2026-12-19 | 45 | 30%
5.1 | Control design assessment | Auditor | 2026-11-05 | 2026-11-16 | 12 | 60%
5.2 | Sample selection | Auditor | 2026-11-13 | 2026-11-20 | 8 | 40%
5.3 | Substantive testing | Auditor | 2026-11-20 | 2026-12-14 | 25 | 10%
5.4 | Working papers & evidence | Auditor | 2026-11-15 | 2026-12-19 | 35 | 20%
6 | Fieldwork complete |  | 2026-12-20 | 2026-12-20 | — | —
7 | Findings & validation |  | 2026-12-15 | 2027-01-13 | 30 | 0%
7.1 | Draft observations | Auditor | 2026-12-15 | 2026-12-26 | 12 | 0%

## Slide 4
7.2 | Factual accuracy check | Process owner | 2026-12-27 | 2027-01-05 | 10 | 0%
7.3 | Rating & prioritization | Audit manager | 2027-01-04 | 2027-01-09 | 6 | 0%
7.4 | Closing meeting | Audit manager | 2027-01-12 | 2027-01-13 | 2 | 0%
8 | Closing meeting held |  | 2027-01-14 | 2027-01-14 | — | —
9 | Management response |  | 2027-01-14 | 2027-02-07 | 25 | 0%
9.1 | Agree actions & owners | Management | 2027-01-14 | 2027-01-28 | 15 | 0%
9.2 | Target dates confirmed | Management | 2027-01-24 | 2027-02-02 | 10 | 0%
9.3 | Escalate accepted risks | Audit lead | 2027-01-29 | 2027-02-07 | 10 | 0%
10 | Reporting |  | 2027-02-03 | 2027-03-09 | 35 | 0%
10.1 | Draft report | Audit manager | 2027-02-03 | 2027-02-14 | 12 | 0%
10.2 | Quality review | Audit lead | 2027-02-15 | 2027-02-22 | 8 | 0%
11 | Final report issued |  | 2027-02-26 | 2027-02-26 | — | —
11.1 | Audit committee presentation | Audit lead | 2027-02-28 | 2027-03-01 | 2 | 0%
12 | Follow-up |  | 2027-03-10 | 2027-08-06 | 150 | 0%
12.1 | Remediation tracking | Audit manager | 2027-03-10 | 2027-07-07 | 120 | 0%
12.2 | Verification testing of closed actions | Auditor | 2027-05-29 | 2027-07-07 | 40 | 0%
12.3 | Overdue actions reported to committee | Audit lead | 2027-07-08 | 2027-07-22 | 15 | 0%
13 | Follow-up cycle closed |  | 2027-08-07 | 2027-08-07 | — | —