## Gantt
Internal Audit Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9
1 | Annual planning |  | 2026-08-02 | 2026-09-30 | 60
1.1 | Risk assessment | Audit lead | 2026-08-02 | 2026-08-26 | 25
1.2 | Audit universe refresh | Audit lead | 2026-08-12 | 2026-08-31 | 20
1.3 | Stakeholder interviews | Audit lead | 2026-08-17 | 2026-09-05 | 20
1.4 | Resource & budget plan | Audit lead | 2026-09-01 | 2026-09-15 | 15
1.5 | Draft annual plan | Audit lead | 2026-09-11 | 2026-09-25 | 15
2 | ◆ Plan approved by committee |  | 2026-10-01 | 2026-10-01 | [9 empty] | ◆
3 | Engagement scoping |  | 2026-10-01 | 2026-11-04 | 35
3.1 | Engagement announcement | Audit manager | 2026-10-01 | 2026-10-03 | 3
3.2 | Background research & data request | Auditor | 2026-10-04 | 2026-10-18 | 15
3.3 | Process walkthroughs | Auditor | 2026-10-13 | 2026-10-27 | 15
3.4 | Risk & control matrix | Auditor | 2026-10-21 | 2026-11-01 | 12
4 | ◆ Terms of reference agreed |  | 2026-11-05 | 2026-11-05 | [14 empty] | ◆
5 | Fieldwork & testing |  | 2026-11-05 | 2026-12-19 | 45
5.1 | Control design assessment | Auditor | 2026-11-05 | 2026-11-16 | 12
5.2 | Sample selection | Auditor | 2026-11-13 | 2026-11-20 | 8
5.3 | Substantive testing | Auditor | 2026-11-20 | 2026-12-14 | 25
5.4 | Working papers & evidence | Auditor | 2026-11-15 | 2026-12-19 | 35
6 | ◆ Fieldwork complete |  | 2026-12-20 | 2026-12-20 | [21 empty] | ◆
7 | Findings & validation |  | 2026-12-15 | 2027-01-13 | 30
7.1 | Draft observations | Auditor | 2026-12-15 | 2026-12-26 | 12
7.2 | Factual accuracy check | Process owner | 2026-12-27 | 2027-01-05 | 10
7.3 | Rating & prioritization | Audit manager | 2027-01-04 | 2027-01-09 | 6
7.4 | Closing meeting | Audit manager | 2027-01-12 | 2027-01-13 | 2
8 | ◆ Closing meeting held |  | 2027-01-14 | 2027-01-14 | [24 empty] | ◆
9 | Management response |  | 2027-01-14 | 2027-02-07 | 25
9.1 | Agree actions & owners | Management | 2027-01-14 | 2027-01-28 | 15
9.2 | Target dates confirmed | Management | 2027-01-24 | 2027-02-02 | 10
9.3 | Escalate accepted risks | Audit lead | 2027-01-29 | 2027-02-07 | 10
10 | Reporting |  | 2027-02-03 | 2027-03-09 | 35
10.1 | Draft report | Audit manager | 2027-02-03 | 2027-02-14 | 12
10.2 | Quality review | Audit lead | 2027-02-15 | 2027-02-22 | 8
11 | ◆ Final report issued |  | 2027-02-26 | 2027-02-26 | [30 empty] | ◆
11.1 | Audit committee presentation | Audit lead | 2027-02-28 | 2027-03-01 | 2
12 | Follow-up |  | 2027-03-10 | 2027-08-06 | 150
12.1 | Remediation tracking | Audit manager | 2027-03-10 | 2027-07-07 | 120
12.2 | Verification testing of closed actions | Auditor | 2027-05-29 | 2027-07-07 | 40
12.3 | Overdue actions reported to committee | Audit lead | 2027-07-08 | 2027-07-22 | 15
13 | ◆ Follow-up cycle closed |  | 2027-08-07 | 2027-08-07 | [53 empty] | ◆