## Slide 1
ISO 27001 Certification Plan
Free Gantt chart template · gantts.app

## Slide 2
ISO 27001 Certification Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Scope & gap analysis
Define ISMS scope & boundaries
Interested parties & legal register
Gap analysis against Annex A
Certification body selection & audit booking
◆ Scope and gap baseline agreed
Risk assessment & SoA
Risk assessment methodology
Asset & information inventory
Risk identification & evaluation
Risk treatment plan
Statement of Applicability drafted
◆ SoA and risk treatment approved
Control implementation
ISMS policy set & topic policies
Access control & identity hardening
Supplier & cloud security controls
Secure development & change control
Physical & people controls
Incident management & continuity procedures
◆ Controls implemented
Operate & accumulate records
Staff awareness training
Operate controls & collect evidence
Access reviews & log monitoring cycles
Supplier reviews & risk register updates
Incident & continuity exercise
◆ Three months of records available
Internal audit & management review
Internal audit programme & auditor selection
Internal audit fieldwork
Internal audit report & nonconformities
Corrective actions from internal audit
Management review meeting
◆ Internal audit and management review complete
Stage 1 & Stage 2 audit
Stage 1 documentation audit
Stage 1 findings & readiness report
Corrective action window before Stage 2
Evidence pack refresh for Stage 2
Stage 2 certification audit
Stage 2 nonconformity closure
◆ Certificate issued
Surveillance audit year 1 planning
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Scope & gap analysis |  | 2026-08-02 | 2026-09-20 | 50 | 100%
1.1 | Define ISMS scope & boundaries | CISO | 2026-08-02 | 2026-08-16 | 15 | 100%
1.2 | Interested parties & legal register | Compliance | 2026-08-12 | 2026-08-31 | 20 | 100%
1.3 | Gap analysis against Annex A | Consultant | 2026-08-22 | 2026-09-15 | 25 | 100%
1.4 | Certification body selection & audit booking | CISO | 2026-09-01 | 2026-09-20 | 20 | 100%
2 | Scope and gap baseline agreed |  | 2026-09-21 | 2026-09-21 | — | —
3 | Risk assessment & SoA |  | 2026-09-21 | 2026-11-19 | 60 | 90%
3.1 | Risk assessment methodology | Risk lead | 2026-09-21 | 2026-10-05 | 15 | 100%
3.2 | Asset & information inventory | IT | 2026-09-21 | 2026-10-15 | 25 | 100%
3.3 | Risk identification & evaluation | Risk lead | 2026-10-11 | 2026-11-04 | 25 | 90%
3.4 | Risk treatment plan | CISO | 2026-10-31 | 2026-11-19 | 20 | 70%
3.5 | Statement of Applicability drafted | Compliance | 2026-11-10 | 2026-11-19 | 10 | 50%
4 | SoA and risk treatment approved |  | 2026-11-20 | 2026-11-20 | — | —
5 | Control implementation |  | 2026-11-20 | 2027-02-17 | 90 | 40%
5.1 | ISMS policy set & topic policies | Compliance | 2026-11-20 | 2026-12-29 | 40 | 60%
5.2 | Access control & identity hardening | IT | 2026-11-30 | 2027-01-23 | 55 | 40%
5.3 | Supplier & cloud security controls | IT & procurement | 2026-12-10 | 2027-01-28 | 50 | 30%
5.4 | Secure development & change control | Engineering | 2026-12-20 | 2027-02-02 | 45 | 20%
5.5 | Physical & people controls | HR & facilities | 2026-12-30 | 2027-02-02 | 35 | 10%
5.6 | Incident management & continuity procedures | CISO | 2027-01-09 | 2027-02-17 | 40 | 0%
6 | Controls implemented |  | 2027-02-18 | 2027-02-18 | — | —

## Slide 4
7 | Operate & accumulate records |  | 2027-02-18 | 2027-06-07 | 110 | 0%
7.1 | Staff awareness training | HR | 2027-02-18 | 2027-03-19 | 30 | 0%
7.2 | Operate controls & collect evidence | All owners | 2027-02-18 | 2027-06-02 | 105 | 0%
7.3 | Access reviews & log monitoring cycles | IT | 2027-03-05 | 2027-06-02 | 90 | 0%
7.4 | Supplier reviews & risk register updates | Compliance | 2027-03-20 | 2027-05-28 | 70 | 0%
7.5 | Incident & continuity exercise | CISO | 2027-04-19 | 2027-05-03 | 15 | 0%
8 | Three months of records available |  | 2027-06-03 | 2027-06-03 | — | —
9 | Internal audit & management review |  | 2027-05-04 | 2027-08-06 | 95 | 0%
9.1 | Internal audit programme & auditor selection | Compliance | 2027-05-04 | 2027-05-23 | 20 | 0%
9.2 | Internal audit fieldwork | Internal auditor | 2027-06-03 | 2027-06-27 | 25 | 0%
9.3 | Internal audit report & nonconformities | Internal auditor | 2027-06-28 | 2027-07-09 | 12 | 0%
9.4 | Corrective actions from internal audit | Control owners | 2027-07-10 | 2027-08-01 | 23 | 0%
9.5 | Management review meeting | Exec | 2027-08-02 | 2027-08-06 | 5 | 0%
10 | Internal audit and management review complete |  | 2027-08-07 | 2027-08-07 | — | —
11 | Stage 1 & Stage 2 audit |  | 2027-08-07 | 2027-11-14 | 100 | 0%
11.1 | Stage 1 documentation audit | Certification body | 2027-08-12 | 2027-08-14 | 3 | 0%
11.2 | Stage 1 findings & readiness report | Certification body | 2027-08-15 | 2027-08-21 | 7 | 0%
11.3 | Corrective action window before Stage 2 | Control owners | 2027-08-22 | 2027-09-25 | 35 | 0%
11.4 | Evidence pack refresh for Stage 2 | Compliance | 2027-09-16 | 2027-09-30 | 15 | 0%
11.5 | Stage 2 certification audit | Certification body | 2027-10-01 | 2027-10-05 | 5 | 0%
11.6 | Stage 2 nonconformity closure | Control owners | 2027-10-06 | 2027-10-30 | 25 | 0%
12 | Certificate issued |  | 2027-11-03 | 2027-11-03 | — | —
12.1 | Surveillance audit year | Compliance | 2027-11-03 | 2027-11-12 | 10 | 0%

## Slide 5
 | 1 planning |  |  |  |  |