## Gantt
ISO 27001 Certification Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15
1 | Scope & gap analysis |  | 2026-08-02 | 2026-09-20 | 50
1.1 | Define ISMS scope & boundaries | CISO | 2026-08-02 | 2026-08-16 | 15
1.2 | Interested parties & legal register | Compliance | 2026-08-12 | 2026-08-31 | 20
1.3 | Gap analysis against Annex A | Consultant | 2026-08-22 | 2026-09-15 | 25
1.4 | Certification body selection & audit booking | CISO | 2026-09-01 | 2026-09-20 | 20
2 | ◆ Scope and gap baseline agreed |  | 2026-09-21 | 2026-09-21 | [8 empty] | ◆
3 | Risk assessment & SoA |  | 2026-09-21 | 2026-11-19 | 60
3.1 | Risk assessment methodology | Risk lead | 2026-09-21 | 2026-10-05 | 15
3.2 | Asset & information inventory | IT | 2026-09-21 | 2026-10-15 | 25
3.3 | Risk identification & evaluation | Risk lead | 2026-10-11 | 2026-11-04 | 25
3.4 | Risk treatment plan | CISO | 2026-10-31 | 2026-11-19 | 20
3.5 | Statement of Applicability drafted | Compliance | 2026-11-10 | 2026-11-19 | 10
4 | ◆ SoA and risk treatment approved |  | 2026-11-20 | 2026-11-20 | [16 empty] | ◆
5 | Control implementation |  | 2026-11-20 | 2027-02-17 | 90
5.1 | ISMS policy set & topic policies | Compliance | 2026-11-20 | 2026-12-29 | 40
5.2 | Access control & identity hardening | IT | 2026-11-30 | 2027-01-23 | 55
5.3 | Supplier & cloud security controls | IT & procurement | 2026-12-10 | 2027-01-28 | 50
5.4 | Secure development & change control | Engineering | 2026-12-20 | 2027-02-02 | 45
5.5 | Physical & people controls | HR & facilities | 2026-12-30 | 2027-02-02 | 35
5.6 | Incident management & continuity procedures | CISO | 2027-01-09 | 2027-02-17 | 40
6 | ◆ Controls implemented |  | 2027-02-18 | 2027-02-18 | [29 empty] | ◆
7 | Operate & accumulate records |  | 2027-02-18 | 2027-06-07 | 110
7.1 | Staff awareness training | HR | 2027-02-18 | 2027-03-19 | 30
7.2 | Operate controls & collect evidence | All owners | 2027-02-18 | 2027-06-02 | 105
7.3 | Access reviews & log monitoring cycles | IT | 2027-03-05 | 2027-06-02 | 90
7.4 | Supplier reviews & risk register updates | Compliance | 2027-03-20 | 2027-05-28 | 70
7.5 | Incident & continuity exercise | CISO | 2027-04-19 | 2027-05-03 | 15
8 | ◆ Three months of records available |  | 2027-06-03 | 2027-06-03 | [44 empty] | ◆
9 | Internal audit & management review |  | 2027-05-04 | 2027-08-06 | 95
9.1 | Internal audit programme & auditor selection | Compliance | 2027-05-04 | 2027-05-23 | 20
9.2 | Internal audit fieldwork | Internal auditor | 2027-06-03 | 2027-06-27 | 25
9.3 | Internal audit report & nonconformities | Internal auditor | 2027-06-28 | 2027-07-09 | 12
9.4 | Corrective actions from internal audit | Control owners | 2027-07-10 | 2027-08-01 | 23
9.5 | Management review meeting | Exec | 2027-08-02 | 2027-08-06 | 5
10 | ◆ Internal audit and management review complete |  | 2027-08-07 | 2027-08-07 | [53 empty] | ◆
11 | Stage 1 & Stage 2 audit |  | 2027-08-07 | 2027-11-14 | 100
11.1 | Stage 1 documentation audit | Certification body | 2027-08-12 | 2027-08-14 | 3
11.2 | Stage 1 findings & readiness report | Certification body | 2027-08-15 | 2027-08-21 | 7
11.3 | Corrective action window before Stage 2 | Control owners | 2027-08-22 | 2027-09-25 | 35
11.4 | Evidence pack refresh for Stage 2 | Compliance | 2027-09-16 | 2027-09-30 | 15
11.5 | Stage 2 certification audit | Certification body | 2027-10-01 | 2027-10-05 | 5
11.6 | Stage 2 nonconformity closure | Control owners | 2027-10-06 | 2027-10-30 | 25
12 | ◆ Certificate issued |  | 2027-11-03 | 2027-11-03 | [66 empty] | ◆
12.1 | Surveillance audit year 1 planning | Compliance | 2027-11-03 | 2027-11-12 | 10